## Gantt_Schedule
BASF LMP Harmonization — Wave Delivery Schedule (Gantt task list)
Cadence: 3-week sprints, cutover every 3 months (13 weeks). Waves overlap by 3 weeks (stabilisation of wave N runs into initiation of wave N+1). Import-ready for MS Project / Smartsheet.
WBS | Task Name | Level | Wave | Start | Finish | Duration (days) | Predecessor (WBS) | Milestone | Applications | Effort (hrs) | Complexity Band
1 | PROGRAMME — Harmonization Wave Delivery | 1 |  | 2026-10-05 | 2029-01-22 | 840 |  |  | 479 | 365420.6
1.1 | WAVE 1 | 2 | 1 | 2026-10-05 | 2027-01-25 | 112 |  |  | 62 | 16408.1 | Simple + Medium only
1.1.1 | Wave Initiation | 3 | 1 | 2026-10-05 | 2026-10-12 | 7
1.1.2 | Assessment - Target State (1 sprint) | 3 | 1 | 2026-10-12 | 2026-11-02 | 21 | 1.1.1
1.1.3 | Migration (2 sprints) | 3 | 1 | 2026-11-02 | 2026-12-14 | 42 | 1.1.2 |  | 62 | 16408.1
1.1.4 | Testing & Validation (1 sprint) | 3 | 1 | 2026-12-14 | 2027-01-04 | 21 | 1.1.3
1.1.5 | ★ CUTOVER — Wave 1 Go-Live | 3 | 1 | 2027-01-04 | 2027-01-04 | 0 | 1.1.4 | Yes | 62
1.1.6 | Stabilisation / Hypercare (1 sprint) | 3 | 1 | 2027-01-04 | 2027-01-25 | 21 | 1.1.5
1.1.7 | ◆ Gate Review — Wave 1 Acceptance | 3 | 1 | 2027-01-25 | 2027-01-25 | 0 | 1.1.6 | Yes
1.2 | WAVE 2 | 2 | 2 | 2027-01-04 | 2027-04-26 | 112 | 1.1.2 |  | 62 | 19486.1 | Simple + Medium only
1.2.1 | Wave Initiation | 3 | 2 | 2027-01-04 | 2027-01-11 | 7
1.2.2 | Assessment - Target State (1 sprint) | 3 | 2 | 2027-01-11 | 2027-02-01 | 21 | 1.2.1
1.2.3 | Migration (2 sprints) | 3 | 2 | 2027-02-01 | 2027-03-15 | 42 | 1.2.2 |  | 62 | 19486.1
1.2.4 | Testing & Validation (1 sprint) | 3 | 2 | 2027-03-15 | 2027-04-05 | 21 | 1.2.3
1.2.5 | ★ CUTOVER — Wave 2 Go-Live | 3 | 2 | 2027-04-05 | 2027-04-05 | 0 | 1.2.4 | Yes | 62
1.2.6 | Stabilisation / Hypercare (1 sprint) | 3 | 2 | 2027-04-05 | 2027-04-26 | 21 | 1.2.5
1.2.7 | ◆ Gate Review — Wave 2 Acceptance | 3 | 2 | 2027-04-26 | 2027-04-26 | 0 | 1.2.6 | Yes
1.3 | WAVE 3 | 2 | 3 | 2027-04-05 | 2027-07-26 | 112 | 1.2.2 |  | 62 | 32658.9 | Simple, Medium, Complex
1.3.1 | Wave Initiation | 3 | 3 | 2027-04-05 | 2027-04-12 | 7
1.3.2 | Assessment - Target State (1 sprint) | 3 | 3 | 2027-04-12 | 2027-05-03 | 21 | 1.3.1
1.3.3 | Migration (2 sprints) | 3 | 3 | 2027-05-03 | 2027-06-14 | 42 | 1.3.2 |  | 62 | 32658.9
1.3.4 | Testing & Validation (1 sprint) | 3 | 3 | 2027-06-14 | 2027-07-05 | 21 | 1.3.3
1.3.5 | ★ CUTOVER — Wave 3 Go-Live | 3 | 3 | 2027-07-05 | 2027-07-05 | 0 | 1.3.4 | Yes | 62
1.3.6 | Stabilisation / Hypercare (1 sprint) | 3 | 3 | 2027-07-05 | 2027-07-26 | 21 | 1.3.5
1.3.7 | ◆ Gate Review — Wave 3 Acceptance | 3 | 3 | 2027-07-26 | 2027-07-26 | 0 | 1.3.6 | Yes
1.4 | WAVE 4 | 2 | 4 | 2027-07-05 | 2027-10-25 | 112 | 1.3.2 |  | 62 | 39507.1 | Simple, Medium, Complex
1.4.1 | Wave Initiation | 3 | 4 | 2027-07-05 | 2027-07-12 | 7
1.4.2 | Assessment - Target State (1 sprint) | 3 | 4 | 2027-07-12 | 2027-08-02 | 21 | 1.4.1
1.4.3 | Migration (2 sprints) | 3 | 4 | 2027-08-02 | 2027-09-13 | 42 | 1.4.2 |  | 62 | 39507.1
1.4.4 | Testing & Validation (1 sprint) | 3 | 4 | 2027-09-13 | 2027-10-04 | 21 | 1.4.3
1.4.5 | ★ CUTOVER — Wave 4 Go-Live | 3 | 4 | 2027-10-04 | 2027-10-04 | 0 | 1.4.4 | Yes | 62
1.4.6 | Stabilisation / Hypercare (1 sprint) | 3 | 4 | 2027-10-04 | 2027-10-25 | 21 | 1.4.5
1.4.7 | ◆ Gate Review — Wave 4 Acceptance | 3 | 4 | 2027-10-25 | 2027-10-25 | 0 | 1.4.6 | Yes
1.5 | WAVE 5 | 2 | 5 | 2027-10-04 | 2028-01-24 | 112 | 1.4.2 |  | 62 | 44837.8 | Simple, Medium, Complex
1.5.1 | Wave Initiation | 3 | 5 | 2027-10-04 | 2027-10-11 | 7
1.5.2 | Assessment - Target State (1 sprint) | 3 | 5 | 2027-10-11 | 2027-11-01 | 21 | 1.5.1
1.5.3 | Migration (2 sprints) | 3 | 5 | 2027-11-01 | 2027-12-13 | 42 | 1.5.2 |  | 62 | 44837.8
1.5.4 | Testing & Validation (1 sprint) | 3 | 5 | 2027-12-13 | 2028-01-03 | 21 | 1.5.3
1.5.5 | ★ CUTOVER — Wave 5 Go-Live | 3 | 5 | 2028-01-03 | 2028-01-03 | 0 | 1.5.4 | Yes | 62
1.5.6 | Stabilisation / Hypercare (1 sprint) | 3 | 5 | 2028-01-03 | 2028-01-24 | 21 | 1.5.5
1.5.7 | ◆ Gate Review — Wave 5 Acceptance | 3 | 5 | 2028-01-24 | 2028-01-24 | 0 | 1.5.6 | Yes
1.6 | WAVE 6 | 2 | 6 | 2028-01-03 | 2028-04-24 | 112 | 1.5.2 |  | 62 | 59706.7 | All complexities incl. Very Complex
1.6.1 | Wave Initiation | 3 | 6 | 2028-01-03 | 2028-01-10 | 7
1.6.2 | Assessment - Target State (1 sprint) | 3 | 6 | 2028-01-10 | 2028-01-31 | 21 | 1.6.1
1.6.3 | Migration (2 sprints) | 3 | 6 | 2028-01-31 | 2028-03-13 | 42 | 1.6.2 |  | 62 | 59706.7
1.6.4 | Testing & Validation (1 sprint) | 3 | 6 | 2028-03-13 | 2028-04-03 | 21 | 1.6.3
1.6.5 | ★ CUTOVER — Wave 6 Go-Live | 3 | 6 | 2028-04-03 | 2028-04-03 | 0 | 1.6.4 | Yes | 62
1.6.6 | Stabilisation / Hypercare (1 sprint) | 3 | 6 | 2028-04-03 | 2028-04-24 | 21 | 1.6.5
1.6.7 | ◆ Gate Review — Wave 6 Acceptance | 3 | 6 | 2028-04-24 | 2028-04-24 | 0 | 1.6.6 | Yes
1.7 | WAVE 7 | 2 | 7 | 2028-04-03 | 2028-07-24 | 112 | 1.6.2 |  | 62 | 77385.7 | All complexities incl. Very Complex
1.7.1 | Wave Initiation | 3 | 7 | 2028-04-03 | 2028-04-10 | 7
1.7.2 | Assessment - Target State (1 sprint) | 3 | 7 | 2028-04-10 | 2028-05-01 | 21 | 1.7.1
1.7.3 | Migration (2 sprints) | 3 | 7 | 2028-05-01 | 2028-06-12 | 42 | 1.7.2 |  | 62 | 77385.7
1.7.4 | Testing & Validation (1 sprint) | 3 | 7 | 2028-06-12 | 2028-07-03 | 21 | 1.7.3
1.7.5 | ★ CUTOVER — Wave 7 Go-Live | 3 | 7 | 2028-07-03 | 2028-07-03 | 0 | 1.7.4 | Yes | 62
1.7.6 | Stabilisation / Hypercare (1 sprint) | 3 | 7 | 2028-07-03 | 2028-07-24 | 21 | 1.7.5
1.7.7 | ◆ Gate Review — Wave 7 Acceptance | 3 | 7 | 2028-07-24 | 2028-07-24 | 0 | 1.7.6 | Yes
1.8 | WAVE 8 | 2 | 8 | 2028-07-03 | 2028-10-23 | 112 | 1.7.2 |  | 42 | 69066.2 | All complexities incl. Very Complex
1.8.1 | Wave Initiation | 3 | 8 | 2028-07-03 | 2028-07-10 | 7
1.8.2 | Assessment - Target State (1 sprint) | 3 | 8 | 2028-07-10 | 2028-07-31 | 21 | 1.8.1
1.8.3 | Migration (2 sprints) | 3 | 8 | 2028-07-31 | 2028-09-11 | 42 | 1.8.2 |  | 42 | 69066.2
1.8.4 | Testing & Validation (1 sprint) | 3 | 8 | 2028-09-11 | 2028-10-02 | 21 | 1.8.3
1.8.5 | ★ CUTOVER — Wave 8 Go-Live | 3 | 8 | 2028-10-02 | 2028-10-02 | 0 | 1.8.4 | Yes | 42
1.8.6 | Stabilisation / Hypercare (1 sprint) | 3 | 8 | 2028-10-02 | 2028-10-23 | 21 | 1.8.5
1.8.7 | ◆ Gate Review — Wave 8 Acceptance | 3 | 8 | 2028-10-23 | 2028-10-23 | 0 | 1.8.6 | Yes
1.9 | WAVE 9 | 2 | 9 | 2028-10-02 | 2029-01-22 | 112 | 1.8.2 |  | 3 | 6364 | All complexities incl. Very Complex
1.9.1 | Wave Initiation | 3 | 9 | 2028-10-02 | 2028-10-09 | 7
1.9.2 | Assessment - Target State (1 sprint) | 3 | 9 | 2028-10-09 | 2028-10-30 | 21 | 1.9.1
1.9.3 | Migration (2 sprints) | 3 | 9 | 2028-10-30 | 2028-12-11 | 42 | 1.9.2 |  | 3 | 6364
1.9.4 | Testing & Validation (1 sprint) | 3 | 9 | 2028-12-11 | 2029-01-01 | 21 | 1.9.3
1.9.5 | ★ CUTOVER — Wave 9 Go-Live | 3 | 9 | 2029-01-01 | 2029-01-01 | 0 | 1.9.4 | Yes | 3
1.9.6 | Stabilisation / Hypercare (1 sprint) | 3 | 9 | 2029-01-01 | 2029-01-22 | 21 | 1.9.5
1.9.7 | ◆ Gate Review — Wave 9 Acceptance | 3 | 9 | 2029-01-22 | 2029-01-22 | 0 | 1.9.6 | Yes

## Gantt_View
Wave Delivery Gantt — monthly view
Bars show stage duration. Overlap between waves is intentional: stabilisation of one wave runs concurrently with initiation of the next.
Task | Wave | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27 | Nov 27 | Dec 27 | Jan 28 | Feb 28 | Mar 28 | Apr 28 | May 28 | Jun 28 | Jul 28 | Aug 28 | Sep 28 | Oct 28 | Nov 28 | Dec 28 | Jan 29
WAVE 1 | 1
Wave Initiation | 1
Assessment - Target State (1 sprint) | 1
Migration (2 sprints) | 1
Testing & Validation (1 sprint) | 1
★ CUTOVER — Wave 1 Go-Live | 1 |  |  |  | ◆
Stabilisation / Hypercare (1 sprint) | 1
◆ Gate Review — Wave 1 Acceptance | 1 |  |  |  | ◆
WAVE 2 | 2
Wave Initiation | 2
Assessment - Target State (1 sprint) | 2
Migration (2 sprints) | 2
Testing & Validation (1 sprint) | 2
★ CUTOVER — Wave 2 Go-Live | 2 | [6 empty] | ◆
Stabilisation / Hypercare (1 sprint) | 2
◆ Gate Review — Wave 2 Acceptance | 2 | [6 empty] | ◆
WAVE 3 | 3
Wave Initiation | 3
Assessment - Target State (1 sprint) | 3
Migration (2 sprints) | 3
Testing & Validation (1 sprint) | 3
★ CUTOVER — Wave 3 Go-Live | 3 | [9 empty] | ◆
Stabilisation / Hypercare (1 sprint) | 3
◆ Gate Review — Wave 3 Acceptance | 3 | [9 empty] | ◆
WAVE 4 | 4
Wave Initiation | 4
Assessment - Target State (1 sprint) | 4
Migration (2 sprints) | 4
Testing & Validation (1 sprint) | 4
★ CUTOVER — Wave 4 Go-Live | 4 | [12 empty] | ◆
Stabilisation / Hypercare (1 sprint) | 4
◆ Gate Review — Wave 4 Acceptance | 4 | [12 empty] | ◆
WAVE 5 | 5
Wave Initiation | 5
Assessment - Target State (1 sprint) | 5
Migration (2 sprints) | 5
Testing & Validation (1 sprint) | 5
★ CUTOVER — Wave 5 Go-Live | 5 | [15 empty] | ◆
Stabilisation / Hypercare (1 sprint) | 5
◆ Gate Review — Wave 5 Acceptance | 5 | [15 empty] | ◆
WAVE 6 | 6
Wave Initiation | 6
Assessment - Target State (1 sprint) | 6
Migration (2 sprints) | 6
Testing & Validation (1 sprint) | 6
★ CUTOVER — Wave 6 Go-Live | 6 | [18 empty] | ◆
Stabilisation / Hypercare (1 sprint) | 6
◆ Gate Review — Wave 6 Acceptance | 6 | [18 empty] | ◆
WAVE 7 | 7
Wave Initiation | 7
Assessment - Target State (1 sprint) | 7
Migration (2 sprints) | 7
Testing & Validation (1 sprint) | 7
★ CUTOVER — Wave 7 Go-Live | 7 | [21 empty] | ◆
Stabilisation / Hypercare (1 sprint) | 7
◆ Gate Review — Wave 7 Acceptance | 7 | [21 empty] | ◆
WAVE 8 | 8
Wave Initiation | 8
Assessment - Target State (1 sprint) | 8
Migration (2 sprints) | 8
Testing & Validation (1 sprint) | 8
★ CUTOVER — Wave 8 Go-Live | 8 | [24 empty] | ◆
Stabilisation / Hypercare (1 sprint) | 8
◆ Gate Review — Wave 8 Acceptance | 8 | [24 empty] | ◆
WAVE 9 | 9
Wave Initiation | 9
Assessment - Target State (1 sprint) | 9
Migration (2 sprints) | 9
Testing & Validation (1 sprint) | 9
★ CUTOVER — Wave 9 Go-Live | 9 | [27 empty] | ◆
Stabilisation / Hypercare (1 sprint) | 9
◆ Gate Review — Wave 9 Acceptance | 9 | [27 empty] | ◆
Legend
Wave Initiation
Assessment - Target State
Migration
Testing & Validation
Stabilisation / Hypercare
Milestone (cutover / gate review)

## Wave_Summary
Wave Summary — scope, effort and complexity ramp
Wave | Start | Cutover | Stabilisation Ends | Applications | Effort (hrs) | Quick Wins | Topics | Simple | Medium | Complex | Very Complex | Permitted Complexity
1 | 2026-10-05 | 2027-01-04 | 2027-01-25 | 62 | 16408.1 | 62 | 11 | 21 | 41 | 0 | 0 | Simple + Medium only
2 | 2027-01-04 | 2027-04-05 | 2027-04-26 | 62 | 19486.1 | 10 | 14 | 33 | 29 | 0 | 0 | Simple + Medium only
3 | 2027-04-05 | 2027-07-05 | 2027-07-26 | 62 | 32658.9 | 0 | 13 | 16 | 44 | 2 | 0 | Simple, Medium, Complex
4 | 2027-07-05 | 2027-10-04 | 2027-10-25 | 62 | 39507.1 | 0 | 11 | 6 | 38 | 18 | 0 | Simple, Medium, Complex
5 | 2027-10-04 | 2028-01-03 | 2028-01-24 | 62 | 44837.8 | 0 | 12 | 3 | 26 | 33 | 0 | Simple, Medium, Complex
6 | 2028-01-03 | 2028-04-03 | 2028-04-24 | 62 | 59706.7 | 0 | 14 | 1 | 15 | 40 | 6 | All complexities incl. Very Complex
7 | 2028-04-03 | 2028-07-03 | 2028-07-24 | 62 | 77385.7 | 0 | 14 | 0 | 2 | 42 | 18 | All complexities incl. Very Complex
8 | 2028-07-03 | 2028-10-02 | 2028-10-23 | 42 | 69066.2 | 0 | 10 | 0 | 1 | 5 | 36 | All complexities incl. Very Complex
9 | 2028-10-02 | 2029-01-01 | 2029-01-22 | 3 | 6364 | 0 | 1 | 0 | 0 | 1 | 2 | All complexities incl. Very Complex
TOTAL |  |  |  | 479 | 365420.6 | 72

## Mapping_Logic
How the wave rules translate into the Gantt
3-week sprint | The atomic scheduling unit. Every stage duration is a multiple of 3 weeks, so stage boundaries always fall on a sprint boundary.
3-month cutover | Wave cadence = 13 weeks. Wave N starts 13 weeks after wave N-1. This is the bar spacing on the Gantt.
Wave internal shape | Initiation 1 wk -> Assessment 3 wks (Sprint 1) -> Migration 6 wks (Sprints 2-3) -> Testing 3 wks (Sprint 4) -> Cutover at week 13 -> Stabilisation 3 wks.
Why waves overlap | A wave runs 16 weeks but a new one starts every 13 weeks. Stabilisation/hypercare of wave N therefore overlaps initiation and assessment of wave N+1. This overlap is the defining feature of the chart and must be resourced - the same team cannot be fully committed to both.
Complexity ramp | Waves 1-2 admit Simple and Medium only. Waves 3-5 add Complex. Waves 6+ admit Very Complex. On the Gantt this appears as bars growing longer and heavier over time even though application counts stay flat.
Quick wins | Concentrated in wave 1 to produce demonstrable value before the first gate review.
Dependencies | Application-level dependencies are enforced as wave ordering: a dependency must complete in a strictly earlier wave. On the Gantt this is a finish-to-start link between wave bars.
Milestones | Two per wave: Cutover (week 13) and Gate Review (week 16, after stabilisation). Gate Review is the entry condition for accepting the next wave scope.
Programme duration | 9 waves x 13 weeks + 3 weeks stabilisation = 120 weeks (~28 months), 2026-10-05 to 2029-01-22.
CAUTION - 24 month ceiling | The stated programme window is 3-24 months. Nine waves exceed it (~27 months). Eight waves (24 months) fits the ceiling; the ninth wave carries only 3 applications and should be folded into wave 8.
CAUTION - capacity | Total effort across assigned applications is ~365,000 hrs against a configured 4,000 hrs per wave. Wave_Parameters capacity and max-apps-per-wave must be reset to the real delivery plan before this schedule is credible.