## Instructions
BASF LMP — Harmonization Wave Plan: Data Collection Workbook
Tech Mahindra ¦ Input pack for the AI-driven Wave Plan tool
PURPOSE
What this workbook is | The single data collection instrument for Harmonization Wave Plan creation. It captures the per-application attributes the AI-driven tool needs to generate, sequence and cost a wave plan.
Where the data comes from | Pre-populated from Business_applications_Categorized.xlsx (3,785 applications; 572 categorized across 21 topics). Business Capability is carried over from column P "Capabilities" of that source and must be CONFIRMED in workshop.
What happens next | Completed workbook is validated and loaded to the wave-planning database, then consumed by the AI-driven tool to produce the Generated Wave Plan, which is adjusted with BASF calendar/exception inputs and approved.
HOW TO USE
Step 1 | Filter Wave_Plan_Input by Topic. Run one workshop per topic.
Step 2 | Confirm the pre-filled Business Capability and record the Business Rationale.
Step 3 | Complete every yellow column. Use the dropdowns — free text will fail load validation.
Step 4 | Assessment effort calculates automatically once Size and Complexity are set.
Step 5 | Set wave calendar and capacity on Wave_Parameters; set sequencing weights on Scoring_Rules.
Step 6 | Check Topic_Summary for completeness before submitting.
LEGEND
Yellow cells | You fill these in. Every yellow column is mandatory unless marked optional.
Grey cells | Pre-populated from source data or reference tables — do not edit.
White cells with formulas | Calculated. Do not overwrite.
Row 2 of Wave_Plan_Input | EXAMPLE ROW showing expected format. Delete before submission.
SHEETS
Wave_Plan_Input | One row per application. The primary data collection sheet.
Reference_Lists | Permitted values and their definitions. Source for all dropdowns.
Effort_Model | Assessment effort by T-shirt size x complexity, from LMP_Estimation_Sheet.
Wave_Parameters | Wave calendar, sprint cadence, capacity and blackout windows.
Scoring_Rules | Weights and thresholds the AI tool uses to sequence applications into waves.
Topic_Summary | Per-topic counts, effort roll-up and completeness tracking.
ASSUMPTIONS
Assessment effort | Source: LMP_Estimation_Sheet.xlsx, sheet "Effort-Technical Assessment". Effort = Common effort + (Application mapping + Process assessment + Categorisation + Target-architecture alignment). Reconciles to the "Assessment" column of sheet "Effort -Harmonisation Services" (e.g. Simple/XXS = 10.4 + 4x2 = 18.4 hrs).
Migration effort | NOT included as a formula. The Mapping / ETL / Transformation / Testing / Decommissioning columns were blank in the source estimation sheet, so Migration Effort is a manual entry column pending that model being finalised.
Wave cadence | 3-week sprints with cutover every 3 months, per the Harmonization approach slide. Programme window 3-24 months. Set actual dates on Wave_Parameters.
Topic scope | 572 applications carry a Categorization value in the source file and are loaded here. The remaining 3,213 rows are uncategorized and out of scope for wave planning until categorized.

## Reference_Lists
Reference Lists — permitted values
T-Shirt Size | Definition
XXS | Basic utility with minimal data; ~10 tables, ~100K records
XS | Simple application with limited scope; 10-30 tables, ~1M records
S | Standard departmental application; 30-50 tables, ~5M records
M | Multi-functional business application; 50-75 tables, ~100M records
L | Enterprise-grade system; 75-150 tables, ~1K million records
XL | Comprehensive enterprise platform; 150-200 tables, ~10K million records
XXL | Strategic global-scale platform; 300+ tables, very high volume
Complexity | Definition
Simple | Clean, well-structured data; standard formats; minimal transformation
Medium | Moderate data quality issues; some custom transformation required
Complex | Significant data cleansing required; non-standard structures
Very Complex | Legacy or unstructured data; heavy remediation and transformation
Migration Type | Definition
Data Migration Only | Data moved to the target platform; no functional rebuild
Functional Migration | Functionality re-implemented on the BASF standard platform
Modernization | Application re-architected or replatformed
Disposition | Definition
Harmonize | Consolidate onto the BASF standard platform for the topic
Modernize | Re-architect / replatform
AMS | Operational responsibility transfers to the supplier
Retain | Remain as-is for this programme
Retire | Decommission without replacement
Change Impact | Definition
Low | Few users, single site, minimal process change
Medium | Single business unit or region; moderate process change
High | Multi-region; significant process and role change
Very High | Global; major process redesign and org change
Risk | Definition
Low | Well understood, low coupling, no regulatory exposure
Medium | Some unknowns or moderate integration coupling
High | Significant unknowns, high coupling, or plant-critical
Critical | Safety, regulatory or production-stopping exposure
Business Criticality | Definition
Low | Outage tolerable for days
Medium | Outage tolerable for hours
High | Outage tolerable for minutes; significant business impact
Mission Critical | No tolerable outage; plant or safety impact
Quick Win | Definition
Yes | Low effort, low risk, early demonstrable value — candidate for Wave 1
No | Not a quick win
Yes/No | Definition
Yes
No
Sign-off Status | Definition
Not Started
In Workshop
Pending BASF Review
Approved
Disputed

## Effort_Model
Technical Assessment Effort Model (hours per application)
Source: LMP_Estimation_Sheet.xlsx > "Effort-Technical Assessment". Total = Common effort + (Mapping + Process assessment + Categorisation + Target-architecture alignment).
Key | T-Shirt Size | Complexity | Common Effort (hrs) | Application Mapping (hrs) | Process Assessment (hrs) | Categorisation (hrs) | Target Arch Alignment (hrs) | Total Assessment (hrs)
XXS¦Simple | XXS | Simple | 10.4 | 2 | 2 | 2 | 2 | 18.4
XS¦Simple | XS | Simple | 10.4 | 4 | 4 | 4 | 4 | 26.4
S¦Simple | S | Simple | 10.4 | 8 | 8 | 8 | 8 | 42.4
M¦Simple | M | Simple | 10.4 | 16 | 16 | 16 | 16 | 74.4
L¦Simple | L | Simple | 10.4 | 24 | 24 | 24 | 24 | 106.4
XL¦Simple | XL | Simple | 10.4 | 32 | 32 | 32 | 32 | 138.4
XXL¦Simple | XXL | Simple | 10.4 | 40 | 40 | 40 | 40 | 170.4
XXS¦Medium | XXS | Medium | 13 | 4 | 4 | 4 | 4 | 29
XS¦Medium | XS | Medium | 13 | 8 | 8 | 8 | 8 | 45
S¦Medium | S | Medium | 13 | 16 | 16 | 16 | 16 | 77
M¦Medium | M | Medium | 13 | 32 | 32 | 32 | 32 | 141
L¦Medium | L | Medium | 13 | 48 | 48 | 48 | 48 | 205
XL¦Medium | XL | Medium | 13 | 64 | 64 | 64 | 64 | 269
XXL¦Medium | XXL | Medium | 13 | 80 | 80 | 80 | 80 | 333
XXS¦Complex | XXS | Complex | 17.3333 | 6 | 6 | 6 | 6 | 41.3333
XS¦Complex | XS | Complex | 17.3333 | 12 | 12 | 12 | 12 | 65.3333
S¦Complex | S | Complex | 17.3333 | 24 | 24 | 24 | 24 | 113.3333
M¦Complex | M | Complex | 17.3333 | 48 | 48 | 48 | 48 | 209.3333
L¦Complex | L | Complex | 17.3333 | 72 | 72 | 72 | 72 | 305.3333
XL¦Complex | XL | Complex | 17.3333 | 96 | 96 | 96 | 96 | 401.3333
XXL¦Complex | XXL | Complex | 17.3333 | 120 | 120 | 120 | 120 | 497.3333
XXS¦Very Complex | XXS | Very Complex | 17.3333 | 8 | 8 | 8 | 8 | 49.3333
XS¦Very Complex | XS | Very Complex | 17.3333 | 16 | 16 | 16 | 16 | 81.3333
S¦Very Complex | S | Very Complex | 17.3333 | 32 | 32 | 32 | 32 | 145.3333
M¦Very Complex | M | Very Complex | 17.3333 | 64 | 64 | 64 | 64 | 273.3333
L¦Very Complex | L | Very Complex | 17.3333 | 96 | 96 | 96 | 96 | 401.3333
XL¦Very Complex | XL | Very Complex | 17.3333 | 128 | 128 | 128 | 128 | 529.3333
XXL¦Very Complex | XXL | Very Complex | 17.3333 | 160 | 160 | 160 | 160 | 657.3333
Programme-level assessment activities (per topic, not per application)
Workshop | 80
Data Review | 80
Target Architecture for Topic | 160
Wave plan creation | 40
Business Case creation | 80
Gate Review | 80

## Wave_Parameters
Wave Parameters — calendar, cadence and capacity
Yellow cells are inputs to the AI-driven wave planning tool.
Parameter | Value | Notes
Programme start date | 2026-10-01 | First day of Wave 1 initiation
Programme end date | 2028-12-31 | Programme window is 3 to 24 months per topic
Sprint length (weeks) | 3 | Delivery organised in 3-week sprints
Cutover cadence (months) | 3 | Cutover every 3 months = one wave
Number of waves | 9 | Derived from programme window / cutover cadence
Max applications per wave | 25 | Hard ceiling regardless of effort capacity
Available capacity per wave (hrs) | 4000 | Total delivery hours available per wave
Max Very High change-impact apps per wave | 3 | Change saturation guard
Max Critical-risk apps per wave | 2 | Risk concentration guard
Max Mission Critical apps per wave | 4 | Business continuity guard
Quick wins target in Wave 1 (%) | 40% | Share of Wave 1 reserved for quick wins
Blackout window 1 (start) | 2026-12-15 | Year-end freeze — no cutovers
Blackout window 1 (end) | 2027-01-05
Blackout window 2 (start) |  | Add plant turnaround windows as advised by BASF
Blackout window 2 (end)
Site turnaround constraint applies | Yes | If Yes, apps flagged plant-critical avoid turnaround windows

## Scoring_Rules
Wave Sequencing Rules — weights and scores
The AI-driven tool computes a Wave Eligibility Score per application. Higher score = earlier wave. Adjust weights to re-shape the plan.
Factor Weights (must total 100%) | Weight | Interpretation
Quick win | 25% | Front-loads early demonstrable value
Effort (lower is earlier) | 20% | Smaller applications sequence earlier
Risk (lower is earlier) | 20% | Defers high-risk applications to later waves
Change impact (lower is earlier) | 15% | Protects the organisation from change saturation
Dependency readiness | 15% | Applications whose predecessors are done sequence earlier
Business criticality (lower is earlier) | 5% | Defers mission-critical systems
Total | 100% | Must equal 100%
Risk score (lower risk scores higher) | Score
Low | 100
Medium | 70
High | 35
Critical | 0
Change impact score | Score
Low | 100
Medium | 70
High | 35
Very High | 0
Business criticality score | Score
Low | 100
Medium | 70
High | 35
Mission Critical | 0
Effort score by T-shirt size | Score
XXS | 100
XS | 90
S | 75
M | 55
L | 35
XL | 20
XXL | 0
Quick win score | Score
Yes | 100
No | 0
Dependency readiness score | Score
No dependencies | 100
Dependencies in earlier wave | 70
Dependencies in same wave | 30
Dependencies unresolved | 0

## Wave_Plan_Input
App ID | Application Name | Topic (Categorization) | Business Capability (from source col P) | Migration Type | Capability Confirmed? | Business Rationale | Disposition | Target Platform | Migration Type | T-Shirt Size | Complexity | # Tables | Data Volume (records) | Change Impact | Risk | Quick Win | Business Criticality | Department | Business Owner | Install Type | Site / Region | Dependencies (App IDs) | Dependency Readiness | Earliest Start | Latest Finish | Regulatory Hold? | Assessment Effort (hrs) | Migration Effort (hrs) | Total Effort (hrs) | Wave Eligibility Score | Proposed Wave | SME / Owner | Workshop Date | Sign-off Status | Comments
APM0000000 | EXAMPLE ROW — delete before submission | Harmonize MES-Solutions | Production Execution (Provides) | Functional Migration Only | Yes | Site MES duplicates standard platform capability; consolidate to reduce licence and support cost. | Harmonize | BASF Standard MES | Functional Migration | M | Medium | 60 | 100000000 | High | Medium | No | High | GBW/PPX | J. Example | On Premise | Ludwigshafen | APM0001111; APM0002222 | Dependencies in earlier wave |  |  | No | 74.4 | 320 | 394.4 | 42.5 | 3 | A. Musterfrau |  | Not Started | Turnaround window at site must be avoided.
APM0003414 | A30_PERSONAL | AMS for Oracle APEX | Provide Facility Services (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Simple | 37 | 3558151 | Medium | Medium | No | Low | ESO/BL | Tanja Kerner | On Premise | Freeport |  | No dependencies | 2027-01-28 |  | No | 18.4 | 168.4 | 210.8 | 59.5 |  | Oracle SME 1 | 2026-12-27 | In Workshop
APM0003413 | AGBALANCE LIVESTOCK OPTI | AMS for Oracle APEX | Product, Production Process and System Innovation Management (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Medium | 10 | 1258807 | Low | Medium | No | Low | BVC | Michaela Kemper | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 26.4 | 142.9 | 187.9 | 67 |  | Oracle SME 2 | 2026-10-10 | In Workshop
APM0003415 | AGRO-DB | AMS for Oracle APEX | Manage Product Information (Provides), Collect and Manage Competitor Information (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | L | Simple | 121 | 1077352145 | Medium | Low | No | Medium | E-CIE/DD | Ruediger Reingruber | On Premise | Antwerp | APM0003414 | Dependencies in earlier wave |  |  | No | 18.4 | 540.5 | 646.9 | 51.5 |  | Oracle SME 3 | 2027-01-02 | Not Started
APM0010573 | APEX - Fernando (BASF Antwerp) | AMS for Oracle APEX | Check-In (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Simple | 35 | 4849040 | Medium | High | No | Low | ESA/LP | Maarten Misschaert | On Premise | Ludwigshafen | APM0003414; APM0003415 | Dependencies in same wave |  | 2028-05-17 | No | 18.4 | 176.9 | 219.3 | 42 |  | Oracle SME 4 | 2026-12-26 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0003452 | APLAERM | AMS for Oracle APEX | Occupational Health (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XXS | Medium | 9 | 76274 | Low | High | No | Medium | ESE/ML | Markus Hammermann | On Premise | Ludwigshafen |  | No dependencies | 2026-10-25 |  | No | 18.4 | 74.3 | 103.3 | 60.5 |  | Oracle SME 1 | 2026-12-31 | Approved
APM0004323 | ARCAD | AMS for Oracle APEX | Provide Plant Maintenance (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Medium | 24 | 1029114 | Low | Critical | No | Mission Critical | ESI/ES | Manfred Penner | On Premise | Schwarzheide |  | No dependencies |  |  | No | 26.4 | 134.7 | 179.7 | 48 |  | Oracle SME 2 | 2026-12-02 | Approved
APM0003416 | AVISOR APEX ADMIN TOOL | AMS for Oracle APEX | Provide Other Technical Services (Provides), Manage Purchase Order (Provides), Accept Goods/Services (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | L | Medium | 139 | 1412627839 | High | Low | No | High | GDD/DA | Jan Horst Markus Grieser | On Premise | Tarragona | APM0003452; APM0004323 | Dependencies in same wave |  | 2028-07-05 | No | 106.4 | 824.7 | 1029.7 | 38.5 |  | Oracle SME 3 | 2026-11-13 | Approved
APM0012205 | Abwasser DEKA | AMS for Oracle APEX | Manage Water Protection (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | M | Complex | 52 | 123190759 | High | Critical | No | High | CIP/AD | Frauke Thrun | On Premise | Ludwigshafen |  | No dependencies | 2027-06-28 |  | No | 74.4 | 600.7 | 810.0333 | 33 |  | Oracle SME 4 | 2026-12-13 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0010765 | Abwasser Kammerbetriebe | AMS for Oracle APEX | Manage Water Supply + Network (Provides) | Data Migration Only | No | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Simple | 41 | 4752400 | Low | Low | No | Medium | CI/CD | Andreas Giel | On Premise | Antwerp |  | No dependencies |  | 2027-08-29 | No | 18.4 | 177.6 | 220 | 68.5 |  | Oracle SME 1 | 2027-01-23 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0010764 | Abwasser Spezial-Amin | AMS for Oracle APEX | Manage Water Supply + Network (Provides) | Data Migration Only | No | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Medium | 27 | 632311 | Medium | Medium | No | High | CIP/AS | Nina Gertrud Bandur | On Premise | Singapore |  | No dependencies | 2027-05-09 |  | No | 26.4 | 145.3 | 190.3 | 59.3 |  | Oracle SME 2 | 2026-10-11 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0003469 | Atemschutzweb | AMS for Oracle APEX | Provide Site Fire Brigade (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | XXS | Medium | 5 | 74865 | Low | Medium | No | Low | ESE/EC | Gerhard Woelk | On Premise | Antwerp | APM0012205; APM0010765; APM0003413 | Dependencies in earlier wave |  |  | No | 18.4 | 89.3 | 118.3 | 64.5 |  | Oracle SME 3 | 2026-10-26 | Approved | Awaiting confirmation of site-local process variations.
APM0012334 | BASANT DIVA | AMS for Oracle APEX | Calculate utility optimized production scenarios (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Medium | 22 | 502155 | Medium | High | No | Low | ESP/IT | Felix Guo | On Premise | Antwerp |  | No dependencies |  |  | No | 26.4 | 148 | 193 | 55.5 |  | Oracle SME 4 | 2026-11-01 | Not Started
APM0002201 | BASANT MIDAS ANTWERP | AMS for Oracle APEX | Manage Emissions (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Simple | 46 | 6677548 | Medium | Low | No | Medium | ESA/VIS | Tom Hugens | On Premise | Global | APM0010573 | Dependencies in earlier wave |  |  | No | 18.4 | 169 | 211.4 | 59.5 |  | Oracle SME 1 | 2026-12-28 | Pending BASF Review
APM0010473 | BASANT PANDA ASSET | AMS for Oracle APEX | Manage specification limits for products (Provides), Determine plant capacities and limits (Provides), Detail manufacturing order data (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | M | Simple | 57 | 76561451 | Medium | Medium | No | Low | ESA/VID | Pieter Nuyens | On Premise | Global |  | No dependencies |  |  | Yes | 18.4 | 307.4 | 381.8 | 55.5 |  | Oracle SME 2 | 2026-12-08 | Approved | Awaiting confirmation of site-local process variations.
APM0012302 | BASANT PANDA CLARIFY | AMS for Oracle APEX | Evaluate production progress, quality and efficacy (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | M | Complex | 61 | 78498739 | Medium | High | No | Medium | ESA/VIS | Tom Hugens | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 675.4 | 884.7333 | 47 |  | Oracle SME 3 | 2026-10-22 | Approved
APM0010775 | BASANT PANDA DOMS | AMS for Oracle APEX | Define recipes for production procedures (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Simple | 36 | 5870448 | Low | Medium | No | Low | ESP/TIS | Veerle Hertling | On Premise | Nanjing |  | No dependencies | 2027-05-05 |  | No | 18.4 | 169.2 | 211.6 | 64 |  | Oracle SME 4 | 2026-10-21 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0002252 | BASANT PANDA OAPEX PLATFORM | AMS for Oracle APEX | Compliantly record and store manufacturing data (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XXS | Medium | 10 | 92768 | Medium | Low | No | Low | ESA/VIS | Tom Hugens | On Premise | Global |  | No dependencies |  |  | No | 18.4 | 73.8 | 102.8 | 70.5 |  | Oracle SME 1 | 2027-01-14 | Disputed | Historical data volume to be re-measured prior to sizing sign-off.
APM0010570 | BASANT PANDA SAPSCAN | AMS for Oracle APEX | Manage assignment of materials to process operations (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | M | Medium | 53 | 85367863 | Very High | High | No | Medium | ESP/CL | Pum Van De Ven | On Premise | Singapore |  | No dependencies | 2027-11-14 |  | No | 74.4 | 501 | 642 | 36.5 |  | Oracle SME 2 | 2027-01-07 | Not Started
APM0003484 | BASPACK - Packaging | AMS for Oracle APEX | Material Master Data Management (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Complex | 37 | 4067222 | High | Medium | No | Medium | GPI/PP | Alexander Rothmund | On Premise | Global | APM0012302; APM0012334 | Dependencies in earlier wave |  | 2028-01-13 | No | 42.4 | 333.7 | 447.0333 | 48.3 |  | Oracle SME 3 | 2026-10-13 | Not Started | Data retention requirement to be validated before decommissioning.
APM0003418 | CALLCENTER | AMS for Oracle APEX | Telephony Management (Provides), Knowledge Management (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Medium | 27 | 831149 | Low | High | No | Low | GDA/GH | Mareike Theissinger | On Premise | Freeport |  | No dependencies |  |  | No | 26.4 | 158.7 | 203.7 | 60 |  | Oracle SME 4 | 2026-12-09 | Approved | Awaiting confirmation of site-local process variations.
APM0003439 | CARE CHEMICALS MASS-BALANCE-TOOL | AMS for Oracle APEX | Manage Mass Balance (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Medium | 10 | 1019920 | Very High | Medium | No | High | G-EM/OE | Laila Glehn | On Premise | Singapore | APM0003469 | Dependencies in earlier wave | 2027-03-03 |  | No | 26.4 | 154.4 | 199.4 | 44.3 |  | Oracle SME 1 | 2027-01-02 | Approved | Data retention requirement to be validated before decommissioning.
APM0003446 | CP JService | AMS for Oracle APEX | Data Integration (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XXS | Medium | 8 | 117731 | Low | Medium | No | High | CPM/LI | Christine Schaedel | On Premise | Freeport | APM0010473 | Dependencies in same wave |  |  | No | 18.4 | 84.4 | 113.4 | 55.3 |  | Oracle SME 2 | 2027-01-14 | Not Started | Historical data volume to be re-measured prior to sizing sign-off.
APM0003443 | CP Monitoring | AMS for Oracle APEX | Data Integration (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Simple | 49 | 4340753 | High | Medium | No | High | CPM/LI | Christine Schaedel | On Premise | Antwerp | APM0012205 | Dependencies unresolved |  |  | No | 18.4 | 207.6 | 250 | 36 |  | Oracle SME 3 | 2027-01-04 | Pending BASF Review
APM0003444 | CP SAP Connector | AMS for Oracle APEX | Data Integration (Provides) | Data Migration Only | No | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Simple | 13 | 1278420 | Medium | Medium | No | Low | CPM/LI | Christine Schaedel | On Premise | Nanjing |  | No dependencies | 2026-12-08 |  | No | 18.4 | 114.4 | 140.8 | 62.5 |  | Oracle SME 4 | 2026-12-20 | Approved
APM0003445 | CP SPC Planning Reports | AMS for Oracle APEX | SC S&OP and Supply Planning (Provides), BI, Reporting & Analytics (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Medium | 46 | 4706963 | Low | Medium | No | High | CPM/LI | Christine Schaedel | On Premise | Global |  | No dependencies |  |  | No | 42.4 | 273.6 | 350.6 | 60.8 |  | Oracle SME 1 | 2026-11-04 | Approved | Awaiting confirmation of site-local process variations.
APM0003420 | ELIAS-EU-SITE-LOG | AMS for Oracle APEX | Provide Plant Maintenance (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Simple | 47 | 3322310 | Low | Low | No | Low | ESL/WM | Michael Sahler | On Premise | Ludwigshafen |  | No dependencies |  | 2028-09-02 | No | 18.4 | 185 | 227.4 | 70 |  | Oracle SME 2 | 2027-01-02 | Approved | Awaiting confirmation of site-local process variations.
APM0002719 | EMD PRODUKTSPEZIFIKATIONEN | AMS for Oracle APEX | Product, Production Process and System Innovation Management (Provides), Manage Product Compliance Master Data (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Complex | 19 | 1253475 | Medium | Critical | No | High | EMX/QA | Lukas Nattmann | On Premise | Singapore |  | No dependencies |  |  | No | 26.4 | 195 | 260.3333 | 45.3 |  | Oracle SME 3 | 2026-11-17 | Pending BASF Review
APM0002165 | EV PRODUCT SPECIFICATIONS | AMS for Oracle APEX | Product, Production Process and System Innovation Management (Provides) | Data Migration Only | No | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Complex | 34 | 6922887 | Medium | Critical | No | Medium | G-EVP/QM | Alexander-Klaus Adleff | On Premise | Tarragona | APM0012302 | Dependencies in earlier wave |  |  | No | 42.4 | 328.7 | 442.0333 | 39.5 |  | Oracle SME 4 | 2026-11-09 | In Workshop
APM0003810 | EV QM ANWENDUNGEN | AMS for Oracle APEX | Manage BASF QM Process Documentation (Provides) | Data Migration Only | No | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Medium | 27 | 552085 | Low | Low | No | High | EVM/ET | Eric Jandura | On Premise | Global | APM0012205 | Dependencies in earlier wave | 2026-12-04 |  | Yes | 26.4 | 134.8 | 179.8 | 65.3 |  | Oracle SME 1 | 2026-12-03 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0003488 | GELAG AND MINIPLANT | AMS for Oracle APEX | Laboratory Infrastructure (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XXS | Medium | 10 | 121835 | Low | Low | No | Medium | ESL/WM | Silvio Montini | On Premise | Freeport |  | No dependencies |  |  | No | 18.4 | 89.6 | 118.6 | 73.5 |  | Oracle SME 2 | 2026-12-19 | Pending BASF Review
APM0003453 | GUDWH | AMS for Oracle APEX | Manage Water Protection (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | XXS | Medium | 10 | 110041 | Medium | Critical | No | Low | ESE/MW | Thomas Hoffelder | On Premise | Geismar |  | No dependencies |  |  | No | 18.4 | 87.8 | 116.8 | 50.5 |  | Oracle SME 3 | 2026-10-18 | Approved | Interface inventory to be confirmed with integration team.
APM0003450 | NOTFALLSYSTEM PASSAGE LIEFERSCHEINE | AMS for Oracle APEX | Manage Site Security (Provides), Check-Out (Provides) | Data Migration Only | No | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Complex | 34 | 4741948 | Low | Critical | No | Medium | ESM/OD | Gerald Ebisch | On Premise | Sao Paulo |  | No dependencies |  |  | No | 42.4 | 323 | 436.3333 | 48.5 |  | Oracle SME 4 | 2027-01-19 | Not Started
APM0009146 | ORACLE_APEX_SHARED | AMS for Oracle APEX | Low-Code Application Development (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | M | Simple | 69 | 116818847 | Medium | Low | No | Low | GDD/DD | Anke Erdenberger | On Premise | Nanjing |  | No dependencies |  |  | No | 18.4 | 371 | 445.4 | 61.5 |  | Oracle SME 1 | 2026-12-10 | Not Started | Historical data volume to be re-measured prior to sizing sign-off.
APM0003401 | PARTIEKARTENSYSTEM PKS | AMS for Oracle APEX | Laboratory Data specific Systems (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Simple | 17 | 1190609 | Medium | Low | No | Medium | E-EDE/OD | Juergen Zimpelmann | On Premise | Ludwigshafen | APM0003418; APM0003444 | Dependencies in earlier wave |  |  | No | 18.4 | 105.5 | 131.9 | 62.5 |  | Oracle SME 2 | 2026-11-08 | Approved
APM0003423 | PARTIKELMESSTECHN | AMS for Oracle APEX | Product, Production Process and System Innovation Management (Provides) | Data Migration Only | Yes | Stable application with no functional change planned; operational responsibility transfers to the supplier under AMS. | AMS | Oracle APEX Managed Service | Data Migration Only | XXS | Medium | 9 | 145087 | Medium | Low | No | Medium | RGS/BM | Kai Bergner | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 87.5 | 116.5 | 69 |  | Oracle SME 3 | 2026-11-20 | Approved
APM0004317 | SPEZIALGASE-LAGERVERWALTUNG (SPEZGASL) | AMS for Oracle APEX | Analysis (Warehouse Operations) (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | S | Simple | 31 | 6897179 | Low | Medium | No | Medium | ESL/WM | Eva Saffert | Hybrid | Global |  | No dependencies |  |  | No | 18.4 | 187.3 | 229.7 | 62.5 |  | Oracle SME 4 | 2026-10-11 | Approved
APM0011143 | Sample tracking Basant | AMS for Oracle APEX | Manage product quality specifications (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | XXS | Simple | 8 | 57408 | Low | Low | No | Medium | ESP/IA | Senne Van Alphen | Mobile App | Freeport | APM0012205; APM0004317; APM0002719 | Dependencies in earlier wave |  |  | No | 18.4 | 59.3 | 77.7 | 69 |  | Oracle SME 1 | 2027-01-23 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0003456 | WISS | AMS for Oracle APEX | Manage Water Protection (Provides) | Data Migration Only | Yes | Low change frequency and well-documented support model; move to AMS to release internal capacity. | AMS | Oracle APEX Managed Service | Data Migration Only | XS | Medium | 29 | 1460108 | Medium | High | No | Low | ESE/MW | Marcus Wilke | On Premise | Antwerp | APM0004317 | Dependencies in earlier wave |  |  | Yes | 26.4 | 141.1 | 186.1 | 51 |  | Oracle SME 2 | 2027-01-03 | Approved
APM0001011 | BASANT MICROSTATION | Harmonize 2D Plant Design Tooling | Provide Construction (Provides) | Data Migration Only | No | Application delivers a subset of AutoCAD Standard Tooling capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AutoCAD Standard Tooling | Data Migration Only | XXS | Simple | 10 | 108978 | Low | Low | Yes | Low | ESA/VIO | Peter Verhoeven | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 64.7 | 83.1 | 100 | 1 | 2D SME 1 | 2026-11-30 | Approved
APM0006394 | BPC Smart P&ID | Harmonize 2D Plant Design Tooling | Provide Process Engineering (Provides) | Functional Migration Only | Yes | Fragmented 2d plant design tooling landscape drives inconsistent data and duplicated interfaces; consolidation onto AutoCAD Standard Tooling is the agreed target state. | Harmonize | AutoCAD Standard Tooling | Functional Migration | M | Very Complex | 66 | 103998156 | High | High | No | High | CPK/ST | Muhamad Taufik Muhamad Mudzaffar | On Premise | Ludwigshafen | APM0001011 | Dependencies in earlier wave |  | 2027-12-26 | No | 74.4 | 1242.3 | 1515.6333 | 35.5 | 8 | 2D SME 2 | 2026-11-09 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0003602 | BYC SMARTPLANT PID | Harmonize 2D Plant Design Tooling | Provide Process Engineering (Provides) | Data Migration Only | No | Site-local 2d plant design tooling duplicates capability already provided by AutoCAD Standard Tooling; consolidate to reduce licence, hosting and support cost. | Harmonize | AutoCAD Standard Tooling | Data Migration Only | S | Medium | 32 | 4880041 | Medium | Low | Yes | Low | ACN CTE/DD | Wei HU | On Premise | Tarragona |  | No dependencies | 2026-11-15 |  | No | 42.4 | 245.6 | 322.6 | 90.5 | 1 | 2D SME 3 | 2026-11-25 | Not Started
APM0008860 | Bluebeam Revu | Harmonize 2D Plant Design Tooling | Provide Piping Engineering (Provides), Provide Construction (Provides), Provide Civil Engineering (Provides) | Functional Migration Only | Yes | Site-local 2d plant design tooling duplicates capability already provided by AutoCAD Standard Tooling; consolidate to reduce licence, hosting and support cost. | Harmonize | AutoCAD Standard Tooling | Functional Migration | S | Medium | 43 | 3216816 | Low | Medium | Yes | Medium | GEM/EC | Thomas Drommer | On Premise | Ludwigshafen | APM0006394; APM0001011 | Dependencies in same wave |  |  | No | 42.4 | 391.8 | 468.8 | 77 | 2 | 2D SME 4 | 2026-11-26 | Approved
APM0010488 | DELME GPM Autocad P&ID | Harmonize 2D Plant Design Tooling | Provide Process Engineering (Provides), Provide Process Engineering (Provides) | Functional Migration Only | Yes | Application delivers a subset of AutoCAD Standard Tooling capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AutoCAD Standard Tooling | Functional Migration | S | Simple | 45 | 6730612 | Medium | Low | Yes | Medium | GEC/GPM | Konstantin Kroeger | On Premise | Ludwigshafen | APM0006394 | Dependencies in same wave |  |  | No | 18.4 | 335.7 | 378.1 | 78.5 | 1 | 2D SME 1 | 2027-01-18 | Approved | Turnaround window at site must be avoided during cutover.
APM0013442 | Digital Plant Topology | Harmonize 2D Plant Design Tooling | Manage Machine Learning (Provides) | Data Migration Only | Yes | Overlapping 2d plant design tooling functionality across sites; harmonising onto AutoCAD Standard Tooling removes redundant support effort and standardises process. | Harmonize | AutoCAD Standard Tooling | Data Migration Only | M | Medium | 71 | 98964034 | Medium | Medium | No | Low | GDD/EA | Julen Barriga | Cloud | Nanjing | APM0006394 | Dependencies in same wave |  | 2028-10-26 | No | 74.4 | 481.6 | 622.6 | 45 | 3 | 2D SME 2 | 2026-11-23 | Disputed | Awaiting confirmation of site-local process variations.
APM0003851 | SMARTPLANT P&ID | Harmonize 2D Plant Design Tooling | Provide Piping Engineering (Provides) | Data Migration Only | Yes | Application delivers a subset of AutoCAD Standard Tooling capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AutoCAD Standard Tooling | Data Migration Only | S | Simple | 46 | 6861414 | Very High | Low | Yes | High | GE/DI | Noopur Chaturvedi | Hybrid | Ludwigshafen |  | No dependencies | 2027-11-05 |  | No | 18.4 | 182.6 | 225 | 76.8 | 1 | 2D SME 3 | 2026-12-27 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0011404 | SPID - ZVS | Harmonize 2D Plant Design Tooling | Provide Process Engineering (Provides) | Functional Migration Only | Yes | Application delivers a subset of AutoCAD Standard Tooling capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AutoCAD Standard Tooling | Functional Migration | M | Complex | 62 | 145413959 | Medium | High | No | Medium | GEA/TE | Amit Roy | On Premise | Antwerp |  | No dependencies |  | 2027-10-08 | No | 74.4 | 1040.4 | 1249.7333 | 47 | 6 | 2D SME 4 | 2026-10-17 | Approved | Awaiting confirmation of site-local process variations.
APM0002064 | SPPID - Asia Pacific | Harmonize 2D Plant Design Tooling | Provide Process Analytical Technology (Provides), Provide Engineering Material Master Data (Provides) | Data Migration Only | Yes | Application delivers a subset of AutoCAD Standard Tooling capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AutoCAD Standard Tooling | Data Migration Only | L | Simple | 112 | 858463342 | Medium | Medium | No | Medium | GEA/OC | Ming Wu XIA | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 571.2 | 677.6 | 50 | 3 | 2D SME 1 | 2026-12-25 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0004010 | AUTODESK INVENTOR | Harmonize 3D Plant Design & Site Scanning | Provide Mechanical Design (Provides) | Data Migration Only | Yes | Fragmented 3d plant design & site scanning landscape drives inconsistent data and duplicated interfaces; consolidation onto AVEVA E3D / Site Scanning is the agreed target state. | Harmonize | AVEVA E3D / Site Scanning | Data Migration Only | L | Very Complex | 134 | 1401209423 | High | High | No | Medium | ESO/MP | Falk Gehrhardt | On Premise | Tarragona |  | No dependencies |  |  | No | 106.4 | 1195 | 1596.3333 | 37.8 | 8 | 3D SME 1 | 2026-12-05 | Approved | Interface inventory to be confirmed with integration team.
APM0004013 | AVEVA E3D | Harmonize 3D Plant Design & Site Scanning | Provide Piping Engineering (Provides), Provide E&I Engineering (Provides), Provide Construction (Provides), Provide Civil Engineering (Provides) | Data Migration Only | Yes | No active users identified during discovery; retire and archive the M dataset. | Modernize | AVEVA E3D / Site Scanning | Data Migration Only | M | Complex | 72 | 79523075 | High | Medium | No | High | GE/DI | Torsten Bierz | On Premise | Schwarzheide |  | No dependencies |  |  | No | 74.4 | 671.4 | 880.7333 | 47 |  | 3D SME 2 | 2027-01-15 | Approved | Data retention requirement to be validated before decommissioning.
APM0003747 | Aveva Everything 3D - PORTH ARTHUR | Harmonize 3D Plant Design & Site Scanning | ProvideTechnical Inspection (Provides), Provide Process Engineering (Provides), Provide Plant Maintenance (Provides), Provide Piping Engineering (Provides), Provide E&I Engineering (Provides), Provide Construction (Provides), Provide Civil Engineering (Provides) | Functional Migration Only | Yes | Application delivers a subset of AVEVA E3D / Site Scanning capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AVEVA E3D / Site Scanning | Functional Migration | S | Medium | 38 | 5711057 | Very High | Medium | No | High | N-CPN/PTE | Darrell Evans | On Premise | Antwerp |  | No dependencies |  | 2028-04-27 | No | 42.4 | 393.3 | 470.3 | 45.8 | 4 | 3D SME 3 | 2026-10-30 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0008391 | Aveva Point Cloud Manager and 3DVS-Viewer | Harmonize 3D Plant Design & Site Scanning | Provide Process Engineering (Provides) | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | AVEVA E3D / Site Scanning | Data Migration Only | M | Very Complex | 58 | 141404895 | Very High | High | No | Mission Critical | ESO/ES | Axel Franke | Cloud | Sao Paulo |  | No dependencies |  |  | No | 74.4 | 815.1 | 1088.4333 | 33 |  | 3D SME 4 | 2026-11-24 | Not Started
APM0005009 | BASANT LUCIAD | Harmonize 3D Plant Design & Site Scanning | Provide Civil Engineering (Provides) | Functional Migration Only | Yes | Application delivers a subset of AVEVA E3D / Site Scanning capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AVEVA E3D / Site Scanning | Functional Migration | XS | Complex | 18 | 1036572 | High | High | No | High | ESA/VIO | Peter Verhoeven | On Premise | Global | APM0004010 | Dependencies in same wave |  |  | No | 26.4 | 328 | 393.3333 | 36.5 | 6 | 3D SME 1 | 2026-12-03 | Not Started | Turnaround window at site must be avoided during cutover.
APM0005033 | BPC Smart 3D | Harmonize 3D Plant Design & Site Scanning | Provide Piping Engineering (Provides) | Data Migration Only | Yes | Fragmented 3d plant design & site scanning landscape drives inconsistent data and duplicated interfaces; consolidation onto AVEVA E3D / Site Scanning is the agreed target state. | Harmonize | AVEVA E3D / Site Scanning | Data Migration Only | M | Medium | 51 | 144626153 | Low | High | No | Low | CPK/ST | Muhamad Taufik Muhamad Mudzaffar | On Premise | Nanjing |  | No dependencies |  |  | No | 74.4 | 485.7 | 626.7 | 53 | 4 | 3D SME 2 | 2026-11-27 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0009339 | BYC Smart 3D | Harmonize 3D Plant Design & Site Scanning | Provide Piping Engineering (Provides) | Functional Migration Only | Yes | Site-local 3d plant design & site scanning duplicates capability already provided by AVEVA E3D / Site Scanning; consolidate to reduce licence, hosting and support cost. | Harmonize | AVEVA E3D / Site Scanning | Functional Migration | M | Very Complex | 58 | 53271628 | Medium | Critical | No | Mission Critical | ACN CTE/DD | Wei HU | On Premise | Schwarzheide |  | No dependencies |  |  | No | 74.4 | 1158.1 | 1431.4333 | 36.5 | 8 | 3D SME 3 | 2027-01-21 | In Workshop
APM0009955 | Bentley PlantSight | Harmonize 3D Plant Design & Site Scanning | Establishment/Maintenance of Guidelines, Standards, Methods & Tools (Provides) | Functional Migration Only | Yes | Overlapping 3d plant design & site scanning functionality across sites; harmonising onto AVEVA E3D / Site Scanning removes redundant support effort and standardises process. | Harmonize | AVEVA E3D / Site Scanning | Functional Migration | L | Complex | 77 | 550578510 | Very High | Medium | No | High | GEC/GEX | Benjamin Simon | Cloud | Freeport |  | No dependencies |  |  | No | 106.4 | 1724.5 | 2029.8333 | 37.8 | 7 | 3D SME 4 | 2026-11-09 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0007184 | DP_GlobalIT Hub | Harmonize 3D Plant Design & Site Scanning | Provide Process Engineering (Provides) | Data Migration Only | Yes | Site-local 3d plant design & site scanning duplicates capability already provided by AVEVA E3D / Site Scanning; consolidate to reduce licence, hosting and support cost. | Harmonize | AVEVA E3D / Site Scanning | Data Migration Only | XXL | Complex | 344 | 66488952183 | High | High | No | Medium | GEA/OSI | Kunalkumar Sheth | On Premise | Ludwigshafen | APM0009339 | Dependencies in same wave |  |  | No | 170.4 | 2166.9 | 2664.2333 | 20.3 | 8 | 3D SME 1 | 2026-12-08 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0013543 | NavVis 3D model system with e-DMS in Yeosu site, Korea. | Harmonize 3D Plant Design & Site Scanning | Support Cooperation between all E&M Units in the Technical Community (Provides) | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | AVEVA E3D / Site Scanning | Data Migration Only | L | Very Complex | 113 | 958042522 | Medium | High | No | Low | GEA/OST | Yon Uk Kang | Cloud | Schwarzheide |  | No dependencies | 2026-11-11 |  | No | 106.4 | 1179.3 | 1580.6333 | 44.5 |  | 3D SME 2 | 2026-12-23 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0010133 | NavVis Ivion CM Antwerp | Harmonize 3D Plant Design & Site Scanning | Manage and control production assets and their status (Provides) | Data Migration Only | Yes | Application delivers a subset of AVEVA E3D / Site Scanning capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AVEVA E3D / Site Scanning | Data Migration Only | M | Complex | 59 | 95371541 | High | High | No | High | ESA/VIO | Isabel Teschke | Cloud | Singapore |  | No dependencies |  |  | No | 74.4 | 588.3 | 797.6333 | 40 | 7 | 3D SME 3 | 2026-11-27 | In Workshop | Vendor licence expires mid-programme; align cutover accordingly.
APM0008679 | PID/S3D | Harmonize 3D Plant Design & Site Scanning | Establishment/Maintenance of Guidelines, Standards, Methods & Tools (Provides) | Functional Migration Only | Yes | Fragmented 3d plant design & site scanning landscape drives inconsistent data and duplicated interfaces; consolidation onto AVEVA E3D / Site Scanning is the agreed target state. | Harmonize | AVEVA E3D / Site Scanning | Functional Migration | M | Complex | 61 | 145359251 | Medium | Low | No | Low | A-CMA/CM | Yan YANG | On Premise | Singapore |  | No dependencies | 2027-07-15 |  | No | 74.4 | 1019.2 | 1228.5333 | 61.5 | 4 | 3D SME 4 | 2026-12-29 | Not Started | Turnaround window at site must be avoided during cutover.
APM0001692 | SMART 3D CN | Harmonize 3D Plant Design & Site Scanning | Provide Process Engineering (Provides), Provide Piping Engineering (Provides) | Functional Migration Only | Yes | Site-local 3d plant design & site scanning duplicates capability already provided by AVEVA E3D / Site Scanning; consolidate to reduce licence, hosting and support cost. | Harmonize | AVEVA E3D / Site Scanning | Functional Migration | XL | Complex | 168 | 11004100912 | Medium | High | No | Medium | GEA/OC | Bo LU | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 138.4 | 2535.7 | 2937.0333 | 40 | 7 | 3D SME 1 | 2027-01-11 | In Workshop | Interface inventory to be confirmed with integration team.
APM0001386 | SMART 3D DE | Harmonize 3D Plant Design & Site Scanning | Provide Piping Engineering (Provides) | Functional Migration Only | Yes | Application delivers a subset of AVEVA E3D / Site Scanning capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AVEVA E3D / Site Scanning | Functional Migration | M | Complex | 72 | 76744772 | Low | Medium | No | Medium | GE/DI | Torsten Bierz | On Premise | Global |  | No dependencies | 2027-08-21 |  | No | 74.4 | 883.3 | 1092.6333 | 58.5 | 5 | 3D SME 2 | 2026-11-22 | Approved | Data retention requirement to be validated before decommissioning.
APM0008973 | SMART 3D US | Harmonize 3D Plant Design & Site Scanning | Provide Piping Engineering (Provides) | Data Migration Only | Yes | Fragmented 3d plant design & site scanning landscape drives inconsistent data and duplicated interfaces; consolidation onto AVEVA E3D / Site Scanning is the agreed target state. | Harmonize | AVEVA E3D / Site Scanning | Data Migration Only | S | Medium | 40 | 6107342 | Medium | Low | No | Low | GEC/OD | Jonathan McKeough | On Premise | Antwerp |  | No dependencies |  |  | No | 42.4 | 272.2 | 349.2 | 65.5 | 2 | 3D SME 3 | 2026-11-29 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0004034 | SMARTPLANT SYSTEM - GOLDEN ISLAND p1 | Harmonize 3D Plant Design & Site Scanning | Provide Construction (Provides) | Data Migration Only | Yes | Site-local 3d plant design & site scanning duplicates capability already provided by AVEVA E3D / Site Scanning; consolidate to reduce licence, hosting and support cost. | Harmonize | AVEVA E3D / Site Scanning | Data Migration Only | M | Medium | 57 | 89526339 | Low | Low | No | Medium | GEA/OC | Ming Wu XIA | On Premise | Antwerp | APM0008679 | Dependencies in same wave |  |  | No | 74.4 | 465.5 | 606.5 | 54 | 2 | 3D SME 4 | 2026-11-19 | Approved
APM0013587 | Smart 3D Automation Toolkit | Harmonize 3D Plant Design & Site Scanning | Provide Piping Engineering (Provides) | Functional Migration Only | Yes | Application delivers a subset of AVEVA E3D / Site Scanning capability with no differentiating function; retire after migration to the standard platform. | Harmonize | AVEVA E3D / Site Scanning | Functional Migration | M | Complex | 52 | 136211001 | Medium | Medium | No | High | CPK/ST | Mohammed Zaffir Junid | On Premise | Ludwigshafen | APM0008973; APM0001386 | Dependencies in earlier wave |  | 2028-09-18 | No | 74.4 | 1000.1 | 1074.5 | 47.8 | 6 | 3D SME 1 | 2026-11-24 | Not Started | Vendor licence expires mid-programme; align cutover accordingly.
APM0004513 | ALARM DATABASE STEAMCRACKER ANTWERP | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Functional Migration Only | Yes | Site-local alarm management solutions duplicates capability already provided by Standard Alarm Management Suite; consolidate to reduce licence, hosting and support cost. | Harmonize | Standard Alarm Management Suite | Functional Migration | XS | Complex | 12 | 1010483 | High | High | No | Mission Critical | ESA/VID | Petra Roefs | On Premise | Sao Paulo |  | No dependencies |  |  | No | 26.4 | 293.8 | 359.1333 | 45.3 | 6 | Alarm SME 1 | 2027-01-10 | In Workshop | Data retention requirement to be validated before decommissioning.
APM0008351 | AMDUS | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Functional Migration Only | Yes | Fragmented alarm management solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto Standard Alarm Management Suite is the agreed target state. | Harmonize | Standard Alarm Management Suite | Functional Migration | XS | Complex | 25 | 963953 | Medium | High | No | High | EMX/HS | Sabine Piana-Diefenbach | On Premise | Global | APM0004513 | Dependencies in same wave |  |  | No | 26.4 | 299.7 | 365.0333 | 41.8 | 6 | Alarm SME 2 | 2026-12-08 | Approved
APM0001975 | BASANT EMERSON AMS | Harmonize Alarm Management Solutions | Maintenance Operations Management (ISA 95) (Provides) | Data Migration Only | Yes | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | Standard Alarm Management Suite | Data Migration Only | S | Simple | 32 | 5578665 | Medium | Medium | No | Medium | ESP/TWO | Jan Heyselbergs | On Premise | Freeport |  | No dependencies | 2027-11-19 |  | No | 18.4 | 175.8 | 218.2 | 58 |  | Alarm SME 3 | 2026-12-08 | Approved | Data retention requirement to be validated before decommissioning.
APM0004514 | BASANT MES ALARM MNGMT ANTWERP | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Functional Migration Only | Yes | Application delivers a subset of Standard Alarm Management Suite capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Standard Alarm Management Suite | Functional Migration | S | Complex | 40 | 6929542 | Very High | High | No | Low | ESA/VID | Petra Roefs | On Premise | Freeport |  | No dependencies |  |  | No | 42.4 | 583.2 | 696.5333 | 42 | 7 | Alarm SME 4 | 2026-10-11 | In Workshop | Interface inventory to be confirmed with integration team.
APM0001728 | BASANT OPERATIONAL INTELLIGENCE | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides), Compare batches based on historic data (Provides) | Functional Migration Only | Yes | Application delivers a subset of Standard Alarm Management Suite capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Standard Alarm Management Suite | Functional Migration | XXS | Simple | 10 | 88656 | Low | High | No | Mission Critical | ESA/VID | Pieter Nuyens | Hybrid | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 99.7 | 118.1 | 57 | 2 | Alarm SME 1 | 2027-01-03 | Not Started
APM0002275 | BYC ALARM PSS SYSTEM | Harmonize Alarm Management Solutions | Archive plant data long-term (Provides) | Functional Migration Only | No | Overlapping alarm management solutions functionality across sites; harmonising onto Standard Alarm Management Suite removes redundant support effort and standardises process. | Harmonize | Standard Alarm Management Suite | Functional Migration | S | Complex | 40 | 6252739 | Medium | High | No | High | ACN CTA/SA | Yuan ZHANG | On Premise | Tarragona |  | No dependencies |  |  | No | 42.4 | 509.7 | 623.0333 | 49.3 | 6 | Alarm SME 2 | 2026-12-06 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0009228 | BYC AM CPM | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Functional Migration Only | Yes | Fragmented alarm management solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto Standard Alarm Management Suite is the agreed target state. | Harmonize | Standard Alarm Management Suite | Functional Migration | XS | Medium | 13 | 1007689 | High | Medium | No | High | ACN CTA/SA | Yuan ZHANG | On Premise | Freeport | APM0002275 | Dependencies in same wave | 2027-05-13 | 2028-07-07 | No | 26.4 | 247.7 | 292.7 | 43.5 | 4 | Alarm SME 3 | 2026-11-30 | Pending BASF Review
APM0013496 | Monaca Dynamo Alarm Monitoring | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Functional Migration Only | Yes | Site-local alarm management solutions duplicates capability already provided by Standard Alarm Management Suite; consolidate to reduce licence, hosting and support cost. | Harmonize | Standard Alarm Management Suite | Functional Migration | XS | Medium | 25 | 1403974 | High | Medium | No | High | N-EDN/OM | Robert Hull | On Premise | Nanjing |  | No dependencies |  |  | No | 26.4 | 258.9 | 303.9 | 54 | 3 | Alarm SME 4 | 2026-12-05 | Not Started | Turnaround window at site must be avoided during cutover.
APM0001816 | PLANT STATE SUITE - GEISMAR | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Data Migration Only | Yes | Site-local alarm management solutions duplicates capability already provided by Standard Alarm Management Suite; consolidate to reduce licence, hosting and support cost. | Harmonize | Standard Alarm Management Suite | Data Migration Only | M | Medium | 53 | 78506301 | Medium | Medium | No | Mission Critical | NAG/M | Timothy Smith | On Premise | Global | APM0002275 | Dependencies in same wave |  |  | No | 74.4 | 446.5 | 587.5 | 40 | 4 | Alarm SME 1 | 2026-11-02 | Approved
APM0001819 | PLANT STATE SUITE - WYANDOTTE | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Functional Migration Only | Yes | Application delivers a subset of Standard Alarm Management Suite capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Standard Alarm Management Suite | Functional Migration | M | Complex | 75 | 64604930 | High | High | No | High | N-EDN/O | Kenneth Moll | On Premise | Nanjing |  | No dependencies | 2027-01-19 |  | No | 74.4 | 990.7 | 1200.0333 | 40 | 7 | Alarm SME 2 | 2026-12-11 | Approved
APM0001815 | PLANTSTATE SUITE | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Data Migration Only | Yes | Site-local alarm management solutions duplicates capability already provided by Standard Alarm Management Suite; consolidate to reduce licence, hosting and support cost. | Harmonize | Standard Alarm Management Suite | Data Migration Only | XS | Medium | 30 | 1293899 | Low | High | No | Mission Critical | GEC/DE | Clarence Smith | On Premise | Nanjing | APM0009228 | Dependencies in same wave |  |  | No | 26.4 | 154.5 | 199.5 | 44.5 | 3 | Alarm SME 3 | 2026-11-20 | Approved
APM0003268 | PLANTSTATE SUITE AND INTEGRITY | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Functional Migration Only | Yes | Fragmented alarm management solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto Standard Alarm Management Suite is the agreed target state. | Harmonize | Standard Alarm Management Suite | Functional Migration | XS | Medium | 30 | 886881 | Low | Low | No | High | GEC/DE | Clarence Smith | On Premise | Ludwigshafen |  | No dependencies | 2027-03-30 |  | No | 26.4 | 255.5 | 300.5 | 69.8 | 2 | Alarm SME 4 | 2027-01-12 | Pending BASF Review
APM0003671 | PROCESS CTRL MCQ | Harmonize Alarm Management Solutions |  | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | Standard Alarm Management Suite | Data Migration Only | S | Complex | 32 | 5864180 | High | Medium | No | Low | G-EV/RMA | Abdel Chouai | On Premise | Global | APM0009228 | Dependencies unresolved |  |  | No | 42.4 | 316.6 | 429.9333 | 39.3 |  | Alarm SME 1 | 2027-01-12 | Approved
APM0008854 | PSS SPA | Harmonize Alarm Management Solutions | Evaluate alarm event and message lists (Provides) | Functional Migration Only | Yes | Application delivers a subset of Standard Alarm Management Suite capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Standard Alarm Management Suite | Functional Migration | XS | Complex | 23 | 1389486 | Medium | Critical | No | High | EMX/WS | Grant Hummel | On Premise | Nanjing |  | No dependencies |  |  | No | 26.4 | 284.8 | 350.1333 | 45.3 | 6 | Alarm SME 2 | 2027-01-18 | Approved
APM0001566 | SYSTEM 1 - PLANT STATE SUITE - PORT ARTHUR | Harmonize Alarm Management Solutions | ProvideTechnical Inspection (Provides), Evaluate alarm event and message lists (Provides) | Data Migration Only | Yes | Site-local alarm management solutions duplicates capability already provided by Standard Alarm Management Suite; consolidate to reduce licence, hosting and support cost. | Harmonize | Standard Alarm Management Suite | Data Migration Only | XS | Simple | 19 | 945915 | High | Low | No | High | N-CPN/PS | Joshua Bourque | On Premise | Tarragona |  | No dependencies |  | 2028-08-18 | No | 18.4 | 106.4 | 132.8 | 60 | 2 | Alarm SME 3 | 2026-12-30 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0012255 | ZVS Site Alarm Management AlarmInsight | Harmonize Alarm Management Solutions | Monitor and analyse production (Provides) | Functional Migration Only | Yes | Application delivers a subset of Standard Alarm Management Suite capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Standard Alarm Management Suite | Functional Migration | XS | Complex | 24 | 534798 | Medium | Medium | No | High | GEA/TI | Jian Lie LI | On Premise | Tarragona |  | No dependencies |  |  | No | 26.4 | 322.4 | 387.7333 | 59.3 | 4 | Alarm SME 4 | 2026-11-24 | Approved | Awaiting confirmation of site-local process variations.
APM0002902 | ARCHIV DMSEE | Harmonize Archiving Solutions | Provide Piping Engineering (Provides), Archiving and Records Management (Provides) | Data Migration Only | No | Application delivers a subset of BASF Archiving Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Archiving Platform | Data Migration Only | S | Simple | 45 | 5070981 | Medium | Medium | No | High | GDB/ZH | Martin Keller | On Premise | Schwarzheide |  | No dependencies |  | 2027-09-13 | No | 18.4 | 187.8 | 230.2 | 56.3 | 2 | Archiving SME 1 | 2026-11-30 | Disputed
APM0004289 | ARCHIVING | Harmonize Archiving Solutions | Archiving and Records Management (Provides) | Functional Migration Only | Yes | Overlapping archiving solutions functionality across sites; harmonising onto BASF Archiving Platform removes redundant support effort and standardises process. | Harmonize | BASF Archiving Platform | Functional Migration | M | Complex | 67 | 104217136 | High | Critical | No | High | GDB/ZH | Andreas Grosche | On Premise | Sao Paulo |  | No dependencies |  | 2028-11-16 | No | 74.4 | 867.9 | 1077.2333 | 33 | 7 | Archiving SME 2 | 2026-11-21 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0010785 | DCTM2SAP | Harmonize Archiving Solutions | Manage Shipment Visibility (Provides), Document Management (Provides) | Functional Migration Only | Yes | Overlapping archiving solutions functionality across sites; harmonising onto BASF Archiving Platform removes redundant support effort and standardises process. | Harmonize | BASF Archiving Platform | Functional Migration | M | Simple | 72 | 121886965 | Very High | Low | No | High | GDE/FB | Andreas Cron | On Premise | Tarragona |  | No dependencies |  |  | No | 18.4 | 580.6 | 655 | 47.8 | 3 | Archiving SME 3 | 2026-10-28 | In Workshop
APM0002813 | DMSEE | Harmonize Archiving Solutions | Archiving and Records Management (Provides) | Data Migration Only | Yes | Site-local archiving solutions duplicates capability already provided by BASF Archiving Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Archiving Platform | Data Migration Only | M | Very Complex | 51 | 133139080 | Medium | Critical | No | Low | GDB/ZH | Martin Keller | On Premise | Global |  | No dependencies | 2027-01-09 |  | No | 74.4 | 791.5 | 1064.8333 | 41.5 | 8 | Archiving SME 4 | 2026-11-12 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0004892 | ADAM | Harmonize E+I Tool Landscape | Analyze manufacturing plan versus actual (Provides) | Functional Migration Only | Yes | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Functional Migration | S | Simple | 34 | 3684802 | Low | High | No | Medium | ESI/EK | Franz Kreissl | On Premise | Global |  | No dependencies |  |  | No | 18.4 | 286.8 | 329.2 | 55.5 | 2 | E+I SME 1 | 2026-12-17 | Approved | Data retention requirement to be validated before decommissioning.
APM0009314 | BASANT CCT | Harmonize E+I Tool Landscape | Provide Process Engineering (Provides) | Data Migration Only | No | Application delivers a subset of E+I Standard Toolset capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+I Standard Toolset | Data Migration Only | S | Complex | 39 | 5567629 | Medium | Medium | No | High | ESP/TE13 | Wouter Smets | Cloud | Schwarzheide | APM0004892 | Dependencies in earlier wave |  |  | No | 42.4 | 361.2 | 474.5333 | 51.8 | 5 | E+I SME 2 | 2026-11-25 | Approved | Data retention requirement to be validated before decommissioning.
APM0009132 | BPC Smart Instrumentation | Harmonize E+I Tool Landscape | Provide E&I Engineering (Provides) | Data Migration Only | Yes | Fragmented e+i tool landscape landscape drives inconsistent data and duplicated interfaces; consolidation onto E+I Standard Toolset is the agreed target state. | Harmonize | E+I Standard Toolset | Data Migration Only | S | Medium | 33 | 4069886 | Medium | Medium | Yes | Medium | CPK/ST | Muhamad Taufik Muhamad Mudzaffar | On Premise | Global | APM0009314 | Dependencies in same wave |  |  | No | 42.4 | 279.8 | 356.8 | 72.5 | 1 | E+I SME 3 | 2026-10-16 | Not Started | Shadow IT usage suspected; confirm true user base in workshop.
APM0009003 | BYC SMARTPLANT INSTRUMENTATION | Harmonize E+I Tool Landscape | Provide E&I Engineering (Provides) | Functional Migration Only | Yes | Fragmented e+i tool landscape landscape drives inconsistent data and duplicated interfaces; consolidation onto E+I Standard Toolset is the agreed target state. | Harmonize | E+I Standard Toolset | Functional Migration | XL | Medium | 172 | 5486581329 | High | Medium | No | High | ACN CTE/DD | Wei HU | On Premise | Ludwigshafen | APM0009314 | Dependencies in earlier wave |  |  | No | 138.4 | 1801.1 | 2070.1 | 35.5 | 6 | E+I SME 4 | 2026-12-14 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0001181 | CAD_CAE_APPL | Harmonize E+I Tool Landscape | Provide Piping Engineering (Provides) | Functional Migration Only | Yes | Fragmented e+i tool landscape landscape drives inconsistent data and duplicated interfaces; consolidation onto E+I Standard Toolset is the agreed target state. | Harmonize | E+I Standard Toolset | Functional Migration | S | Complex | 38 | 6301245 | Medium | Low | No | Low | GE/DI | Johannes Thiessen | On Premise | Global |  | No dependencies | 2027-08-05 |  | No | 42.4 | 547.2 | 660.5333 | 65.5 | 4 | E+I SME 1 | 2026-10-22 | In Workshop
APM0008372 | CET_CADBAS | Harmonize E+I Tool Landscape | Provide Online Self-Service Experiences (Provides) | Data Migration Only | Yes | Fragmented e+i tool landscape landscape drives inconsistent data and duplicated interfaces; consolidation onto E+I Standard Toolset is the agreed target state. | Harmonize | E+I Standard Toolset | Data Migration Only | S | Simple | 34 | 4311863 | Medium | High | No | Mission Critical | G-PM/AMV | Carsten Schulte | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 204.4 | 246.8 | 47.5 | 3 | E+I SME 2 | 2026-12-30 | Approved | Awaiting confirmation of site-local process variations.
APM0004824 | COMOS LUDWIGSHAFEN | Harmonize E+I Tool Landscape | Provide Construction (Provides), Manage Equipments (Provides) | Functional Migration Only | Yes | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Functional Migration | S | Complex | 50 | 3106588 | Medium | High | No | High | GE/DI | Simon Josef Blitzner | On Premise | Schwarzheide |  | No dependencies |  |  | No | 42.4 | 592 | 705.3333 | 49.3 | 6 | E+I SME 3 | 2026-12-31 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0001494 | COMOS SA | Harmonize E+I Tool Landscape | Manage Equipments (Provides) | Data Migration Only | Yes | Application delivers a subset of E+I Standard Toolset capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+I Standard Toolset | Data Migration Only | XS | Medium | 23 | 651431 | High | High | No | High | GE/OSTE | Alexander Tomiyama | On Premise | Singapore | APM0009314 | Dependencies in same wave |  |  | No | 26.4 | 164.8 | 209.8 | 36.5 | 4 | E+I SME 4 | 2026-12-12 | Approved
APM0007397 | ENGINEERING & MAINTENANCE PUBLIC SOFTWARE UTILITIES | Harmonize E+I Tool Landscape | Provide Piping Engineering (Provides) | Functional Migration Only | Yes | Application delivers a subset of E+I Standard Toolset capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+I Standard Toolset | Functional Migration | M | Complex | 71 | 114330909 | Medium | Medium | No | Medium | GE/DI | Frowin Bier | On Premise | Antwerp |  | No dependencies |  |  | No | 74.4 | 1027.4 | 1236.7333 | 54 | 5 | E+I SME 1 | 2026-11-18 | Pending BASF Review | Awaiting confirmation of site-local process variations.
APM0004167 | ENORM | Harmonize E+I Tool Landscape | Provide Technical Documentation + Standards (Provides) | Data Migration Only | Yes | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | E+I Standard Toolset | Data Migration Only | XS | Medium | 27 | 879694 | High | High | No | High | GE/DG | Isabell Keck-Steinmann | Cloud | Antwerp | APM0008372; APM0001494 | Dependencies in earlier wave |  |  | No | 26.4 | 140.3 | 185.3 | 42.5 |  | E+I SME 2 | 2026-11-08 | Approved
APM0011086 | EPLAN Cloud | Harmonize E+I Tool Landscape | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Application delivers a subset of E+I Standard Toolset capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+I Standard Toolset | Data Migration Only | XS | Complex | 26 | 725671 | Medium | High | No | Medium | GEC/GPM | Sebastian Rohlfs | Cloud | Ludwigshafen |  | No dependencies | 2027-08-31 |  | No | 26.4 | 216 | 281.3333 | 54 | 5 | E+I SME 3 | 2026-10-30 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0010413 | GEA SI | Harmonize E+I Tool Landscape | Provide E&I Engineering (Provides) | Functional Migration Only | Yes | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Functional Migration | S | Complex | 32 | 5609194 | Very High | Low | No | High | GEA/D | Zheng LI | On Premise | Geismar |  | No dependencies | 2027-04-22 |  | No | 42.4 | 506 | 619.3333 | 51.8 | 5 | E+I SME 4 | 2026-11-11 | Not Started | Historical data volume to be re-measured prior to sizing sign-off.
APM0003901 | NIN Online Enterprise | Harmonize E+I Tool Landscape | Establishment/Maintenance of Guidelines, Standards, Methods & Tools (Provides) | Data Migration Only | Yes | No active users identified during discovery; retire and archive the XS dataset. | Modernize | E+I Standard Toolset | Data Migration Only | XS | Complex | 20 | 784561 | High | High | No | Medium | EVM/EKU | Gerold Schmid | Cloud | Global |  | No dependencies | 2026-12-23 |  | No | 26.4 | 205 | 270.3333 | 48.8 |  | E+I SME 1 | 2026-10-06 | In Workshop
APM0009630 | NIN Toolbox | Harmonize E+I Tool Landscape | Establishment/Maintenance of Guidelines, Standards, Methods & Tools (Provides) | Functional Migration Only | Yes | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Functional Migration | S | Complex | 35 | 5443817 | Medium | Medium | No | Medium | EVM/EKU | Gerold Schmid | Cloud | Ludwigshafen |  | No dependencies |  | 2028-07-26 | No | 42.4 | 512.5 | 625.8333 | 58 | 5 | E+I SME 2 | 2026-11-16 | Approved | Interface inventory to be confirmed with integration team.
APM0011402 | SI - ZVS | Harmonize E+I Tool Landscape | Provide E&I Engineering (Provides) | Data Migration Only | Yes | Fragmented e+i tool landscape landscape drives inconsistent data and duplicated interfaces; consolidation onto E+I Standard Toolset is the agreed target state. | Harmonize | E+I Standard Toolset | Data Migration Only | XS | Medium | 17 | 562124 | High | Medium | No | Medium | GEA/TE | Amit Roy | On Premise | Antwerp | APM0001181; APM0008372 | Dependencies in same wave | 2026-12-18 |  | No | 26.4 | 165.9 | 210.9 | 45.3 | 4 | E+I SME 3 | 2027-01-02 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0001061 | SIGRAPH.CAE | Harmonize E+I Tool Landscape | Provide Process Engineering (Provides) | Functional Migration Only | Yes | Fragmented e+i tool landscape landscape drives inconsistent data and duplicated interfaces; consolidation onto E+I Standard Toolset is the agreed target state. | Harmonize | E+I Standard Toolset | Functional Migration | M | Complex | 56 | 126185961 | High | High | No | High | ESI/EK | Markus Queva | On Premise | Geismar |  | No dependencies |  |  | No | 74.4 | 909.2 | 1118.5333 | 40 | 7 | E+I SME 4 | 2026-10-26 | Approved
APM0007742 | SIVENT | Harmonize E+I Tool Landscape | Provide Valves and Fittings (Provides), Process Safety (Provides) | Data Migration Only | Yes | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Data Migration Only | XS | Medium | 28 | 988827 | Low | Low | No | Low | RGR/BE | Oliver Flieger | Cloud | Freeport |  | No dependencies | 2027-02-08 |  | No | 26.4 | 157.3 | 202.3 | 73 | 2 | E+I SME 1 | 2026-10-10 | Approved | Turnaround window at site must be avoided during cutover.
APM0009088 | SIVENT FC GI | Harmonize E+I Tool Landscape | Provide Engineering Material Master Data (Provides) | Functional Migration Only | Yes | Overlapping e+i tool landscape functionality across sites; harmonising onto E+I Standard Toolset removes redundant support effort and standardises process. | Harmonize | E+I Standard Toolset | Functional Migration | S | Simple | 45 | 3126939 | High | High | No | High | GEA/TE | Mao Jun HE | On Premise | Geismar |  | No dependencies |  |  | No | 18.4 | 294.9 | 337.3 | 44 | 3 | E+I SME 2 | 2026-12-28 | Not Started | Vendor licence expires mid-programme; align cutover accordingly.
APM0008947 | Smart Instrumentation - GI | Harmonize E+I Tool Landscape | Provide Construction (Provides) | Data Migration Only | Yes | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Data Migration Only | M | Medium | 55 | 149284677 | High | High | No | Mission Critical | GEA/OC | Ming Wu XIA | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 429.2 | 570.2 | 38.3 | 5 | E+I SME 3 | 2026-10-24 | Approved
APM0008390 | Smart Instrumentation AP Test | Harmonize E+I Tool Landscape | Provide Construction (Provides) | Data Migration Only | Yes | Overlapping e+i tool landscape functionality across sites; harmonising onto E+I Standard Toolset removes redundant support effort and standardises process. | Harmonize | E+I Standard Toolset | Data Migration Only | XXS | Complex | 9 | 126605 | Low | Medium | No | Medium | GEA/OC | Chao LIANG | On Premise | Freeport |  | No dependencies |  |  | No | 18.4 | 101.1 | 142.4333 | 67.5 | 3 | E+I SME 4 | 2027-01-23 | In Workshop
APM0004962 | Smart Instrumentation_NA | Harmonize E+I Tool Landscape | Provide E&I Engineering (Provides) | Functional Migration Only | No | Application delivers a subset of E+I Standard Toolset capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+I Standard Toolset | Functional Migration | S | Medium | 48 | 4275614 | Low | Medium | No | Medium | GEC/OD | Wayne Sterling | On Premise | Antwerp | APM0008947 | Dependencies in same wave |  |  | No | 42.4 | 410 | 487 | 52 | 3 | E+I SME 1 | 2026-12-26 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0009112 | TMDS system | Harmonize E+I Tool Landscape | Provide Maintenance Master Data (Provides) | Data Migration Only | Yes | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Data Migration Only | M | Medium | 59 | 87646018 | High | Medium | No | High | GEA/TM | Fan Fan PENG | On Premise | Sao Paulo |  | No dependencies |  |  | No | 74.4 | 418.7 | 559.7 | 47 | 4 | E+I SME 2 | 2026-10-31 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0001549 | TS FOR FT TEAM BR | Harmonize E+I Tool Landscape | Provide Engineering Material Master Data (Provides), Establishment/Maintenance of Guidelines, Standards, Methods & Tools (Provides) | Data Migration Only | No | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Data Migration Only | L | Complex | 86 | 1035635536 | Low | High | No | Medium | GE/OSTE | Alexander Tomiyama | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 937.6 | 1242.9333 | 47.5 | 6 | E+I SME 3 | 2026-11-12 | Not Started | Awaiting confirmation of site-local process variations.
APM0009540 | basf vdi2770 editor | Harmonize E+I Tool Landscape | Provide Technical Documentation + Standards (Provides) | Functional Migration Only | No | Application delivers a subset of E+I Standard Toolset capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+I Standard Toolset | Functional Migration | XS | Simple | 13 | 1246879 | Medium | Medium | Yes | High | GDD/DE | Christoph Attila Kun | Cloud | Antwerp | APM0004962 | Dependencies in same wave |  |  | No | 18.4 | 159 | 185.4 | 73.8 | 1 | E+I SME 4 | 2026-12-04 | In Workshop | Vendor licence expires mid-programme; align cutover accordingly.
APM0012791 | engineering-tools | Harmonize E+I Tool Landscape | Provide Engineering Material Master Data (Provides) | Functional Migration Only | Yes | Fragmented e+i tool landscape landscape drives inconsistent data and duplicated interfaces; consolidation onto E+I Standard Toolset is the agreed target state. | Harmonize | E+I Standard Toolset | Functional Migration | L | Medium | 127 | 545715447 | High | Medium | No | Low | GE/DI | Simon Josef Blitzner | Cloud | Schwarzheide | APM0001494 | Dependencies in earlier wave |  |  | No | 106.4 | 1263.3 | 1468.3 | 41.8 | 5 | E+I SME 1 | 2027-01-18 | Pending BASF Review
APM0012952 | pmdataservice | Harmonize E+I Tool Landscape | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Site-local e+i tool landscape duplicates capability already provided by E+I Standard Toolset; consolidate to reduce licence, hosting and support cost. | Harmonize | E+I Standard Toolset | Functional Migration | S | Complex | 41 | 3677062 | High | High | No | High | GDD/DA | Zhen Hua SHEN | On Premise | Ludwigshafen | APM0009112; APM0009314 | Dependencies in earlier wave |  |  | No | 42.4 | 574.4 | 687.7333 | 39.5 | 7 | E+I SME 2 | 2026-12-08 | Approved
APM0004003 | AUTODESK VAULT | Harmonize E+M Data Integration & Viewing Tools | Provide Mechanical Design (Provides) | Data Migration Only | Yes | Site-local e+m data integration & viewing tools duplicates capability already provided by E+M Data Integration Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | E+M Data Integration Platform | Data Migration Only | M | Complex | 69 | 141275145 | Low | Medium | No | Medium | ESO/ES | Michael Riemer | On Premise | Schwarzheide |  | No dependencies |  |  | No | 74.4 | 641.1 | 850.4333 | 58.5 | 5 | E+M SME 1 | 2026-10-27 | Approved | Data retention requirement to be validated before decommissioning.
APM0010685 | AddIns for 3D Viewer | Harmonize E+M Data Integration & Viewing Tools | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Overlapping e+m data integration & viewing tools functionality across sites; harmonising onto E+M Data Integration Platform removes redundant support effort and standardises process. | Harmonize | E+M Data Integration Platform | Data Migration Only | S | Medium | 49 | 5105823 | Medium | Medium | No | Medium | GDD/DK | Fannie Tesiana | On Premise | Global | APM0004003 | Dependencies in same wave |  | 2028-07-22 | No | 42.4 | 248.9 | 325.9 | 47.5 | 3 | E+M SME 2 | 2026-12-25 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0001955 | BASANT GEODATA & 3D PLATFORM ANTWERP | Harmonize E+M Data Integration & Viewing Tools | Provide Maintenance Master Data (Provides) | Functional Migration Only | Yes | Site-local e+m data integration & viewing tools duplicates capability already provided by E+M Data Integration Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | E+M Data Integration Platform | Functional Migration | XS | Very Complex | 30 | 1284376 | Low | High | No | Low | ESA/VIO | Peter Verhoeven | On Premise | Ludwigshafen |  | No dependencies |  | 2027-09-14 | No | 26.4 | 422.7 | 504.0333 | 60 | 6 | E+M SME 3 | 2026-12-13 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0010108 | BIG RCM platform | Harmonize E+M Data Integration & Viewing Tools | Provide Mechanical Design (Provides) | Functional Migration Only | Yes | Application delivers a subset of E+M Data Integration Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+M Data Integration Platform | Functional Migration | XS | Complex | 16 | 1087036 | Low | Low | No | Medium | GEA/TC | Qi Yong CHEN | Cloud | Antwerp |  | No dependencies |  |  | No | 26.4 | 336.2 | 401.5333 | 71.5 | 3 | E+M SME 4 | 2027-01-01 | In Workshop
APM0011100 | BMS (BUILDING MANAGEMENT SYSTEM) | Harmonize E+M Data Integration & Viewing Tools | Manage Equipments (Provides) | Functional Migration Only | Yes | Application delivers a subset of E+M Data Integration Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+M Data Integration Platform | Functional Migration | XXS | Medium | 5 | 84059 | Low | High | No | Medium | GEA/TS | Juan WANG | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 127.5 | 156.5 | 60.5 | 3 | E+M SME 1 | 2026-12-28 | Approved
APM0009004 | BYC SMARTPLANT REFERENCE DATA | Harmonize E+M Data Integration & Viewing Tools | Provide E&I Engineering (Provides) | Functional Migration Only | Yes | Site-local e+m data integration & viewing tools duplicates capability already provided by E+M Data Integration Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | E+M Data Integration Platform | Functional Migration | M | Complex | 52 | 76797203 | Medium | Medium | No | Low | ACN CTE/DD | Wei HU | On Premise | Ludwigshafen |  | No dependencies |  | 2027-09-27 | No | 74.4 | 905.7 | 1115.0333 | 55.5 | 5 | E+M SME 2 | 2026-12-15 | Pending BASF Review
APM0008624 | BYC SmartPlant Foundation | Harmonize E+M Data Integration & Viewing Tools | Provide Process Engineering (Provides) | Functional Migration Only | Yes | Site-local e+m data integration & viewing tools duplicates capability already provided by E+M Data Integration Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | E+M Data Integration Platform | Functional Migration | XXS | Medium | 5 | 109692 | Medium | Medium | No | Low | ACN CTE/DD | Wei HU | On Premise | Freeport |  | No dependencies |  |  | No | 18.4 | 119.3 | 148.3 | 64.5 | 2 | E+M SME 3 | 2026-11-08 | Pending BASF Review | Awaiting confirmation of site-local process variations.
APM0004828 | CAE-ADAPTER | Harmonize E+M Data Integration & Viewing Tools | Provide Other Technical Services (Provides), Provide Construction (Provides) | Data Migration Only | No | Overlapping e+m data integration & viewing tools functionality across sites; harmonising onto E+M Data Integration Platform removes redundant support effort and standardises process. | Harmonize | E+M Data Integration Platform | Data Migration Only | XS | Medium | 19 | 984231 | Medium | Medium | Yes | Medium | GE/DI | Torsten Bierz | On Premise | Ludwigshafen | APM0001955; APM0011100; APM0010108 | Dependencies in same wave |  |  | No | 26.4 | 161.3 | 206.3 | 75.5 | 1 | E+M SME 4 | 2026-10-22 | Approved
APM0012644 | COMOS Engineering | Harmonize E+M Data Integration & Viewing Tools | Provide Process Engineering (Provides) | Functional Migration Only | Yes | Fragmented e+m data integration & viewing tools landscape drives inconsistent data and duplicated interfaces; consolidation onto E+M Data Integration Platform is the agreed target state. | Harmonize | E+M Data Integration Platform | Functional Migration | S | Medium | 42 | 6874900 | Low | Medium | Yes | Medium | GDD/DC | Bin Zhou | On Premise | Sao Paulo |  | No dependencies |  |  | No | 42.4 | 414.9 | 491.9 | 87.5 | 1 | E+M SME 1 | 2026-12-14 | Approved | Awaiting confirmation of site-local process variations.
APM0013006 | Dokumentenverschlagwortung für MyPlant | Harmonize E+M Data Integration & Viewing Tools | Provide Maintenance Master Data (Provides) | Functional Migration Only | Yes | Site-local e+m data integration & viewing tools duplicates capability already provided by E+M Data Integration Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | E+M Data Integration Platform | Functional Migration | L | Medium | 112 | 1331281808 | Medium | Medium | No | High | ESO/ES | Andrea Kaluza | On Premise | Antwerp | APM0008624 | Dependencies in earlier wave |  |  | No | 106.4 | 1180.8 | 1385.8 | 43.8 | 4 | E+M SME 2 | 2027-01-01 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0013063 | EDM Spider | Harmonize E+M Data Integration & Viewing Tools | Provide Maintenance Master Data (Provides) | Data Migration Only | Yes | Fragmented e+m data integration & viewing tools landscape drives inconsistent data and duplicated interfaces; consolidation onto E+M Data Integration Platform is the agreed target state. | Harmonize | E+M Data Integration Platform | Data Migration Only | M | Medium | 75 | 103690598 | Medium | Medium | No | High | GDD/DK | Marko Friedrich | Hybrid | Tarragona | APM0008624; APM0009004; APM0013006 | Dependencies in same wave |  |  | No | 74.4 | 465.4 | 606.4 | 41.8 | 3 | E+M SME 3 | 2026-11-02 | Approved
APM0008521 | Information Exchange Platform | Harmonize E+M Data Integration & Viewing Tools | Manage Equipments (Provides) | Data Migration Only | Yes | No active users identified during discovery; retire and archive the S dataset. | Modernize | E+M Data Integration Platform | Data Migration Only | S | Complex | 46 | 3602979 | High | Medium | No | Medium | GDD/DE | Carl-Philipp Ding | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 365.3 | 478.6333 | 52.8 |  | E+M SME 4 | 2026-11-18 | Pending BASF Review
APM0001796 | LIVEDOK | Harmonize E+M Data Integration & Viewing Tools | Provide Plant Maintenance (Provides), Provide E&I Engineering (Provides) | Data Migration Only | Yes | Overlapping e+m data integration & viewing tools functionality across sites; harmonising onto E+M Data Integration Platform removes redundant support effort and standardises process. | Harmonize | E+M Data Integration Platform | Data Migration Only | M | Medium | 52 | 80026408 | High | Medium | No | High | GE/DI | Frowin Bier | On Premise | Ludwigshafen |  | No dependencies | 2026-12-21 |  | No | 74.4 | 450.9 | 591.9 | 47 | 4 | E+M SME 1 | 2027-01-15 | Approved | Awaiting confirmation of site-local process variations.
APM0004669 | MERIDIAN | Harmonize E+M Data Integration & Viewing Tools | Provide Construction (Provides) | Data Migration Only | Yes | Application delivers a subset of E+M Data Integration Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+M Data Integration Platform | Data Migration Only | XS | Complex | 22 | 529192 | Medium | Medium | No | Medium | G-EDJ/OH | Rene Baron | On Premise | Ludwigshafen |  | No dependencies | 2026-11-22 |  | No | 26.4 | 199.8 | 265.1333 | 61 | 4 | E+M SME 2 | 2026-10-30 | Approved | Awaiting confirmation of site-local process variations.
APM0002612 | MYPLANT AIP | Harmonize E+M Data Integration & Viewing Tools | Provide Process Engineering (Provides) | Data Migration Only | Yes | Overlapping e+m data integration & viewing tools functionality across sites; harmonising onto E+M Data Integration Platform removes redundant support effort and standardises process. | Harmonize | E+M Data Integration Platform | Data Migration Only | M | Medium | 70 | 81340411 | Medium | Medium | No | Low | ESO/ES | Andrea Kaluza | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 74.4 | 478 | 619 | 55.5 | 3 | E+M SME 3 | 2026-11-04 | Approved | Data retention requirement to be validated before decommissioning.
APM0013593 | MyPlant_Document-Transfer-Tool | Harmonize E+M Data Integration & Viewing Tools | Provide Maintenance Master Data (Provides) | Data Migration Only | No | Overlapping e+m data integration & viewing tools functionality across sites; harmonising onto E+M Data Integration Platform removes redundant support effort and standardises process. | Harmonize | E+M Data Integration Platform | Data Migration Only | S | Simple | 42 | 4672956 | Medium | Medium | No | Medium | ESO/ES | Andrea Kaluza | Cloud | Global |  | No dependencies | 2027-03-11 |  | No | 18.4 | 195.4 | 237.8 | 58 | 2 | E+M SME 4 | 2026-10-06 | Pending BASF Review
APM0004778 | PLANTSUITE | Harmonize E+M Data Integration & Viewing Tools | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Fragmented e+m data integration & viewing tools landscape drives inconsistent data and duplicated interfaces; consolidation onto E+M Data Integration Platform is the agreed target state. | Harmonize | E+M Data Integration Platform | Functional Migration | M | Very Complex | 66 | 115306976 | Medium | High | No | High | E-CMP/OA | David Schoettel | Hybrid | Freeport |  | No dependencies | 2027-01-24 |  | No | 74.4 | 1151.6 | 1424.9333 | 45.3 | 7 | E+M SME 1 | 2027-01-08 | In Workshop
APM0010640 | PSV Digital HUB | Harmonize E+M Data Integration & Viewing Tools | Provide Maintenance Master Data (Provides) | Functional Migration Only | Yes | Site-local e+m data integration & viewing tools duplicates capability already provided by E+M Data Integration Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | E+M Data Integration Platform | Functional Migration | S | Medium | 47 | 6293131 | Medium | Medium | No | Low | CPK/SR | Azmawi Mohamad | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 405.4 | 447.8 | 59.5 | 3 | E+M SME 2 | 2027-01-17 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0004006 | SMARTPLANT FOUNDATION | Harmonize E+M Data Integration & Viewing Tools | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Application delivers a subset of E+M Data Integration Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+M Data Integration Platform | Functional Migration | M | Medium | 75 | 123761298 | High | Medium | No | High | ESA/VIO | Marc Van Gool | On Premise | Singapore |  | No dependencies |  |  | No | 74.4 | 751.5 | 892.5 | 47 | 4 | E+M SME 3 | 2027-01-03 | Approved
APM0001753 | Smart Reference Data (MARIAN) | Harmonize E+M Data Integration & Viewing Tools | Provide Piping Engineering (Provides), Provide Engineering Material Master Data (Provides) | Functional Migration Only | Yes | Application delivers a subset of E+M Data Integration Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+M Data Integration Platform | Functional Migration | XL | Medium | 193 | 13151809058 | Medium | Low | No | Medium | GE/DI | Basem Hassani | On Premise | Tarragona |  | No dependencies | 2027-03-14 |  | No | 138.4 | 1882.3 | 2151.3 | 53 | 3 | E+M SME 4 | 2026-12-06 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0001213 | TECHNICAL HANDBOOKS LUDWIGSHAFEN | Harmonize E+M Data Integration & Viewing Tools | Provide Civil Engineering (Provides) | Data Migration Only | No | Application delivers a subset of E+M Data Integration Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | E+M Data Integration Platform | Data Migration Only | M | Medium | 52 | 113362776 | Very High | Low | No | Medium | ESO/BG | Simon Schmidt | On Premise | Geismar |  | No dependencies | 2027-11-01 |  | No | 74.4 | 414.2 | 555.2 | 49.5 | 4 | E+M SME 1 | 2026-12-25 | Pending BASF Review
APM0001914 | TMMS | Harmonize E+M Data Integration & Viewing Tools | Provide Engineering Material Master Data (Provides), Material Master Data Management (Provides), Manage Procurement Master Data (Provides) | Data Migration Only | Yes | Site-local e+m data integration & viewing tools duplicates capability already provided by E+M Data Integration Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | E+M Data Integration Platform | Data Migration Only | L | Complex | 125 | 717829935 | Medium | High | No | Medium | GEM/TI | Oliver Wendel | On Premise | Freeport |  | No dependencies |  |  | No | 106.4 | 898.8 | 1204.1333 | 43 | 7 | E+M SME 2 | 2027-01-13 | In Workshop
APM0012197 | Trimble SiteVision | Harmonize E+M Data Integration & Viewing Tools | Provide Process Engineering (Provides) | Data Migration Only | Yes | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | E+M Data Integration Platform | Data Migration Only | XS | Very Complex | 24 | 956518 | High | Critical | No | Medium | GDD/DC | Kristoffer Karl Licht | Mobile App | Global | APM0012644; APM0001955 | Dependencies in earlier wave |  |  | No | 26.4 | 232.7 | 314.0333 | 37.3 |  | E+M SME 3 | 2026-11-13 | In Workshop | Awaiting confirmation of site-local process variations.
APM0003622 | UniversalPlantViewer | Harmonize E+M Data Integration & Viewing Tools | Provide Piping Engineering (Provides) | Data Migration Only | Yes | Overlapping e+m data integration & viewing tools functionality across sites; harmonising onto E+M Data Integration Platform removes redundant support effort and standardises process. | Harmonize | E+M Data Integration Platform | Data Migration Only | S | Medium | 36 | 4907226 | High | Low | No | High | GDD/DK | Fannie Tesiana | On Premise | Global |  | No dependencies | 2027-04-15 | 2027-10-12 | No | 42.4 | 232.1 | 309.1 | 57 | 3 | E+M SME 4 | 2026-11-12 | Approved
APM0004429 | Viewport | Harmonize E+M Data Integration & Viewing Tools | Manage Equipments (Provides) | Functional Migration Only | Yes | Fragmented e+m data integration & viewing tools landscape drives inconsistent data and duplicated interfaces; consolidation onto E+M Data Integration Platform is the agreed target state. | Harmonize | E+M Data Integration Platform | Functional Migration | M | Complex | 52 | 103050827 | High | High | No | Medium | G-EDJ/OH | Rene Baron | On Premise | Ludwigshafen |  | No dependencies |  | 2027-10-10 | No | 74.4 | 894.6 | 1103.9333 | 41.8 | 7 | E+M SME 1 | 2027-01-06 | Approved | Awaiting confirmation of site-local process variations.
APM0013226 | ddc_app | Harmonize E+M Data Integration & Viewing Tools | Provide Maintenance Master Data (Provides) | Functional Migration Only | Yes | Overlapping e+m data integration & viewing tools functionality across sites; harmonising onto E+M Data Integration Platform removes redundant support effort and standardises process. | Harmonize | E+M Data Integration Platform | Functional Migration | S | Simple | 38 | 5578482 | Very High | Low | Yes | High | GDD/DE | Peter Geiger | Cloud | Global |  | No dependencies |  |  | No | 18.4 | 296.1 | 338.5 | 76.8 | 1 | E+M SME 2 | 2027-01-13 | Not Started
APM0012484 | trinamiX Autodesk Vault | Harmonize E+M Data Integration & Viewing Tools | Organizational Data Management (Provides) | Functional Migration Only | Yes | Overlapping e+m data integration & viewing tools functionality across sites; harmonising onto E+M Data Integration Platform removes redundant support effort and standardises process. | Harmonize | E+M Data Integration Platform | Functional Migration | S | Simple | 45 | 5552329 | Low | Low | Yes | Low | TRINAMIX | Edgar Matevosyan | Cloud | Sao Paulo |  | No dependencies | 2027-05-30 |  | No | 18.4 | 323.7 | 366.1 | 95 | 1 | E+M SME 3 | 2026-10-13 | Approved
APM0010981 | FEP Product Database CP | Harmonize Enterprise Portal (Fasihi) | Manage Product Information (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XXS | Simple | 9 | 78648 | Medium | Low | Yes | Medium | CPM/LI | Frank Gottfried | On Premise | Ludwigshafen |  | No dependencies | 2027-01-13 |  | No | 18.4 | 88.1 | 106.5 | 94 | 1 | Enterprise SME 1 | 2026-12-19 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0007759 | FEP ANV-Portal der BASF Digital Solutions GmbH | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Medium | 17 | 557905 | Low | Medium | No | Medium | GD/HA | Dirk Austen | On Premise | Singapore | APM0010981 | Dependencies in earlier wave |  |  | No | 26.4 | 156.4 | 201.4 | 61 | 2 | Enterprise SME 2 | 2026-10-21 | In Workshop
APM0007760 | FEP Advanced Materials & Systems Research Portal | Harmonize Enterprise Portal (Fasihi) | R&D Portfolio and Competencies Management (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Simple | 40 | 6228431 | Low | Medium | Yes | High | COM/EE | Timo Gehrlein | On Premise | Geismar |  | No dependencies |  |  | No | 18.4 | 171.9 | 214.3 | 85.8 | 1 | Enterprise SME 3 | 2027-01-05 | Approved
APM0007761 | FEP Alsachimie Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XXS | Complex | 6 | 54598 | Low | Critical | No | Low | E-CMP/OA | Virginie Schaeffer | On Premise | Sao Paulo |  | No dependencies |  |  | No | 18.4 | 190 | 231.3333 | 55 | 5 | Enterprise SME 4 | 2027-01-18 | Approved
APM0007638 | FEP Antwerpen Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Functional Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XXS | Medium | 5 | 67934 | Medium | Low | Yes | Mission Critical | ESA/OM | Anja Verschueren | On Premise | Global | APM0010981 | Dependencies in earlier wave |  |  | No | 18.4 | 121.6 | 150.6 | 86 | 2 | Enterprise SME 1 | 2026-12-07 | Disputed
APM0007786 | FEP App Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | No | Business-differentiating capability not covered by Fasihi Enterprise Portal; retain as-is for this programme and reassess at the next portfolio review. | Modernize | Fasihi Enterprise Portal | Data Migration Only | S | Medium | 37 | 3602265 | Medium | Medium | No | Low | GDB/DF | Peter Scott Olech | On Premise | Schwarzheide | APM0007761 | Dependencies in same wave | 2027-06-29 |  | No | 42.4 | 251.6 | 328.6 | 49 |  | Enterprise SME 2 | 2026-10-23 | In Workshop
APM0007762 | FEP Arbeitsschutz Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XXS | Simple | 8 | 120084 | Low | Low | No | Low | CPM/LI | Frank Gottfried | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 90.5 | 108.9 | 75 | 2 | Enterprise SME 3 | 2027-01-15 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0007818 | FEP BASF Intranet - Home | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Medium | 16 | 636111 | Low | Medium | Yes | Low | COM/EE | Juergen Schwerdtfeger | On Premise | Geismar |  | No dependencies |  |  | No | 26.4 | 133.9 | 178.9 | 92 | 1 | Enterprise SME 4 | 2026-11-12 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0007764 | FEP BASF PETRONAS Intranet Portal | Harmonize Enterprise Portal (Fasihi) | Web content Management (Provides), Communicate Internally (Provides) | Functional Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Complex | 14 | 591212 | Low | High | No | Medium | CPK/FI | Tengku Zaihar Tengku Hamzah | On Premise | Global | APM0007818 | Dependencies in earlier wave | 2026-11-22 |  | No | 26.4 | 289.4 | 354.7333 | 54 | 5 | Enterprise SME 1 | 2027-01-19 | In Workshop | Data retention requirement to be validated before decommissioning.
APM0007765 | FEP BASF Strategie Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by Fasihi Enterprise Portal; retain as-is for this programme and reassess at the next portfolio review. | Modernize | Fasihi Enterprise Portal | Data Migration Only | XXS | Complex | 7 | 118628 | High | High | No | Low | COM/EE | Juergen Schwerdtfeger | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 97.4 | 138.7333 | 52.3 |  | Enterprise SME 2 | 2027-01-16 | Approved | Data retention requirement to be validated before decommissioning.
APM0007766 | FEP BASF-YPC Company Limited Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides), Business Processes (Provides) | Data Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | M | Simple | 63 | 132168540 | Medium | Low | No | High | ACN CGA/I | Mingxing CHEN | On Premise | Ludwigshafen | APM0010981; APM0007761 | Dependencies in same wave |  |  | No | 18.4 | 306.4 | 380.8 | 47.8 | 2 | Enterprise SME 3 | 2026-11-27 | Approved
APM0007767 | FEP Bioscience Research Portal | Harmonize Enterprise Portal (Fasihi) | R&D Portfolio and Competencies Management (Provides) | Functional Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Functional Migration | S | Complex | 30 | 6957614 | High | High | No | Medium | GBW/PK | Joshua Dunn | On Premise | Nanjing |  | No dependencies |  |  | No | 42.4 | 599.2 | 712.5333 | 45.8 | 6 | Enterprise SME 4 | 2026-10-12 | In Workshop | Vendor licence expires mid-programme; align cutover accordingly.
APM0007780 | FEP CL Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | S | Medium | 37 | 6895919 | High | High | No | Medium | CDE/OI | Isabel Ibanez Klein | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 396.1 | 473.1 | 45.8 | 4 | Enterprise SME 1 | 2027-01-21 | Approved
APM0007768 | FEP CM Intranet Portal | Harmonize Enterprise Portal (Fasihi) | Compliantly record and store manufacturing data (Provides), Compliantly (cGMP) create, release and control documents (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | S | Complex | 41 | 6655920 | Medium | High | No | Mission Critical | CM/CS | Christian Kaspar | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 545.9 | 659.2333 | 47.5 | 6 | Enterprise SME 2 | 2026-11-03 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0007642 | FEP COM Extranet Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Data Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Simple | 36 | 6225781 | Low | Medium | Yes | High | CDE/OI | Manuel Agrikola | On Premise | Schwarzheide | APM0007764 | Dependencies in same wave |  |  | No | 18.4 | 185.2 | 227.6 | 75.3 | 1 | Enterprise SME 3 | 2026-11-12 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0007769 | FEP COM Portal | Harmonize Enterprise Portal (Fasihi) | Define Communication Needs (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Medium | 50 | 6842648 | Very High | High | No | Mission Critical | COM/EE | Juergen Schwerdtfeger | On Premise | Singapore | APM0007760 | Dependencies in earlier wave |  |  | No | 42.4 | 225.8 | 302.8 | 32.5 | 5 | Enterprise SME 4 | 2026-12-17 | Approved
APM0007771 | FEP Care Chemicals Portal | Harmonize Enterprise Portal (Fasihi) | Manage assignment of process units to operations (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XXS | Simple | 9 | 72089 | Low | Medium | No | Low | EM/CB | Eric Tobschall | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 104.9 | 123.3 | 69 | 2 | Enterprise SME 1 | 2026-11-07 | Approved
APM0007772 | FEP Catalysts Portal | Harmonize Enterprise Portal (Fasihi) | Track employee training and match it to operational requirements (Provides), Support Travel Planning (Provides), Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Complex | 10 | 548147 | High | Medium | No | Low | G-EVC/OD | Marina Leitz | On Premise | Geismar |  | No dependencies |  |  | No | 26.4 | 336.4 | 401.7333 | 57.3 | 5 | Enterprise SME 2 | 2026-12-01 | Approved | Data retention requirement to be validated before decommissioning.
APM0007776 | FEP Corporate Center Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Simple | 12 | 841808 | Very High | High | No | Low | COM/EE | Juergen Schwerdtfeger | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 114.1 | 140.5 | 45 | 3 | Enterprise SME 3 | 2026-11-29 | Approved
APM0007777 | FEP Corporate Development Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Very Complex | 23 | 1197196 | Low | High | No | Medium | CDE/OI | Martin Baer | On Premise | Ludwigshafen |  | No dependencies | 2027-04-03 | 2027-09-27 | No | 26.4 | 384.8 | 466.1333 | 58.5 | 6 | Enterprise SME 4 | 2026-12-20 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0007778 | FEP Corporate Finance Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XXS | Simple | 5 | 97357 | Low | High | No | Medium | CDE/OI | Pius Kiefel | On Premise | Tarragona |  | No dependencies |  |  | No | 18.4 | 85.5 | 103.9 | 60.5 | 2 | Enterprise SME 1 | 2026-11-07 | Approved
APM0007779 | FEP Corporate Quality Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Simple | 33 | 3342829 | Medium | Medium | No | Mission Critical | COR/RQ | Thorsten Guenzel | On Premise | Sao Paulo |  | No dependencies |  |  | No | 18.4 | 207.4 | 249.8 | 54.5 | 2 | Enterprise SME 2 | 2026-10-15 | Approved | Data retention requirement to be validated before decommissioning.
APM0007781 | FEP Dispersions & Resins Portal | Harmonize Enterprise Portal (Fasihi) | Manage Operational Quality System aligned with EHS (Provides), Document Management (Provides), Communicate Internally (Provides) | Data Migration Only | No | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Complex | 28 | 1177534 | Very High | Medium | No | High | EDG/LB | Tobias Mueller-Goetz | Cloud | Global |  | No dependencies |  |  | No | 26.4 | 194.9 | 260.2333 | 48.8 | 6 | Enterprise SME 3 | 2026-12-24 | Approved
APM0007782 | FEP EMEA PORTAL | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Medium | 12 | 587027 | Very High | Medium | Yes | High | GBE/OK-K | Lydia Wartewig | On Premise | Schwarzheide |  | No dependencies | 2026-12-16 |  | No | 26.4 | 242.6 | 287.6 | 73.8 | 2 | Enterprise SME 4 | 2026-10-17 | Not Started
APM0007783 | FEP EN Intranet Portal | Harmonize Enterprise Portal (Fasihi) | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | S | Complex | 41 | 6511574 | Low | High | No | Medium | EN/CD | Sibylle Gruner | On Premise | Geismar |  | No dependencies |  |  | No | 42.4 | 597 | 710.3333 | 55.5 | 5 | Enterprise SME 1 | 2026-10-11 | In Workshop | Vendor licence expires mid-programme; align cutover accordingly.
APM0007784 | FEP EVO Portal | Harmonize Enterprise Portal (Fasihi) | Track employee training and match it to operational requirements (Provides), Manage Site Landscape (Provides), Manage Risk Assessment/Processes (Provides), Distribute Newsletters (Provides), Business Processes (Provides) | Functional Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Functional Migration | M | Simple | 59 | 81094929 | Medium | High | No | High | EV/CED | Heike Lorenz | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 557.7 | 632.1 | 45.3 | 3 | Enterprise SME 2 | 2026-11-30 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0007820 | FEP Environmental Protection Health and Safety Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Medium | 41 | 6284069 | Low | Medium | No | Medium | COR | Lena Arnold | On Premise | Global | APM0007762 | Dependencies in earlier wave |  |  | No | 42.4 | 269.1 | 346.1 | 58 | 3 | Enterprise SME 3 | 2027-01-18 | Pending BASF Review
APM0007785 | FEP European Site & Verbund Management Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | No | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | S | Medium | 41 | 4955146 | Low | Medium | No | Medium | ESM/OD | Marion Grauer | On Premise | Antwerp |  | No dependencies | 2026-10-26 |  | No | 42.4 | 417.5 | 494.5 | 62.5 | 2 | Enterprise SME 4 | 2027-01-22 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0007789 | FEP Global Engineering & Maintenance Portal | Harmonize Enterprise Portal (Fasihi) | Provide Technical Documentation + Standards (Provides) | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | Fasihi Enterprise Portal | Data Migration Only | S | Simple | 30 | 6458519 | Low | Low | No | High | GE/DI | Daniel Scheidel | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 199.7 | 242.1 | 66.8 |  | Enterprise SME 1 | 2026-11-09 | Approved | Data retention requirement to be validated before decommissioning.
APM0007641 | FEP Global Technical Community Extranet Portal / FT Extranet Portal | Harmonize Enterprise Portal (Fasihi) | Provide Technical Documentation + Standards (Provides) | Functional Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | M | Medium | 56 | 96669801 | Medium | Low | No | Medium | GE/DI | Sebastian Wolf | On Premise | Tarragona |  | No dependencies |  |  | No | 74.4 | 698.9 | 839.9 | 60 | 3 | Enterprise SME 2 | 2026-10-13 | Approved
APM0007790 | FEP Human Resources Portal | Harmonize Enterprise Portal (Fasihi) | HR Service Management (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by Fasihi Enterprise Portal; retain as-is for this programme and reassess at the next portfolio review. | Modernize | Fasihi Enterprise Portal | Data Migration Only | S | Complex | 38 | 5624478 | Medium | Medium | No | High | GBT/OT-G | Stefan Battschinger | On Premise | Antwerp | APM0007784; APM0007777 | Dependencies in earlier wave | 2026-10-14 |  | No | 42.4 | 382.8 | 496.1333 | 51.8 |  | Enterprise SME 3 | 2026-11-27 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0008010 | FEP Human Resources Portal - Impact Tool | Harmonize Enterprise Portal (Fasihi) | HR Service Management (Provides) | Functional Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | S | Very Complex | 36 | 4372668 | Very High | High | No | High | ESM/KS | Desiree Esswein | On Premise | Geismar | APM0007779 | Dependencies in earlier wave | 2026-12-05 |  | No | 42.4 | 737 | 882.3333 | 34.3 | 8 | Enterprise SME 4 | 2026-10-28 | Not Started
APM0008009 | FEP Human Resources Portal - Octopus Application | Harmonize Enterprise Portal (Fasihi) | HR Service Management (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Medium | 39 | 4681890 | Low | Medium | Yes | Medium | GBT/PP-R | Evelin Stein | On Premise | Tarragona |  | No dependencies |  |  | No | 42.4 | 233.1 | 310.1 | 87.5 | 1 | Enterprise SME 1 | 2026-12-11 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0007791 | FEP Iberia Portal | Harmonize Enterprise Portal (Fasihi) | Manage Risk Assessment/Processes (Provides), Manage BASF QM Process Documentation (Provides) | Functional Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | M | Simple | 60 | 90919184 | High | Low | No | Medium | GDA/DG | PEDRO SANCHEZ | On Premise | Singapore |  | No dependencies | 2027-08-21 | 2028-10-04 | No | 18.4 | 514.4 | 588.8 | 54.8 | 2 | Enterprise SME 2 | 2026-10-26 | Pending BASF Review | Interface inventory to be confirmed with integration team.
APM0007663 | FEP Intermediates Portal / CI Portal | Harmonize Enterprise Portal (Fasihi) | Compliantly record and store manufacturing data (Provides), Archiving and Records Management (Provides) | Data Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Medium | 12 | 629405 | Low | Medium | Yes | Medium | CI/CD | Andreas Giel | On Premise | Singapore |  | No dependencies |  |  | No | 26.4 | 131.3 | 176.3 | 90.5 | 1 | Enterprise SME 3 | 2027-01-06 | Approved
APM0007665 | FEP Intranet CP Portal Petrochemicals Portal | Harmonize Enterprise Portal (Fasihi) | Document Management (Provides) | Data Migration Only | No | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Simple | 19 | 667020 | Medium | Medium | Yes | Medium | CPM/LI | Frank Gottfried | On Premise | Global |  | No dependencies |  |  | No | 18.4 | 101.8 | 128.2 | 86 | 1 | Enterprise SME 4 | 2027-01-16 | Approved | Awaiting confirmation of site-local process variations.
APM0008383 | FEP Intranet Elements | Harmonize Enterprise Portal (Fasihi) | Manage Senior Executive Service (Provides) | Data Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Very Complex | 16 | 1234076 | Low | High | No | Medium | COH/SD | Gerhard Josef Mueller | On Premise | Global | APM0007761 | Dependencies in earlier wave | 2026-10-11 | 2027-10-26 | No | 26.4 | 247.9 | 329.2333 | 54 | 6 | Enterprise SME 1 | 2026-12-14 | Approved | Data retention requirement to be validated before decommissioning.
APM0007792 | FEP Intranet Global Business Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Medium | 10 | 801116 | Low | Medium | No | Medium | GBT/OT-G | Stefan Battschinger | On Premise | Ludwigshafen |  | No dependencies | 2026-11-24 |  | No | 26.4 | 243.8 | 288.8 | 65.5 | 2 | Enterprise SME 2 | 2027-01-19 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0007664 | FEP Intranet Paper and Water Chemicals Portal / EV Portal | Harmonize Enterprise Portal (Fasihi) | Track employee training and match it to operational requirements (Provides) | Data Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Medium | 15 | 539405 | Low | Medium | No | Mission Critical | EV/CED | Heike Lorenz | On Premise | Global |  | No dependencies | 2026-11-16 |  | No | 26.4 | 133.4 | 178.4 | 62 | 2 | Enterprise SME 3 | 2026-11-06 | Pending BASF Review
APM0007822 | FEP Intranet Technical Community Portal | Harmonize Enterprise Portal (Fasihi) | Provide Technical Documentation + Standards (Provides) | Functional Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XL | Simple | 156 | 13131784139 | High | Medium | No | Medium | GE/DI | Sebastian Wolf | On Premise | Ludwigshafen |  | No dependencies | 2026-12-10 |  | No | 18.4 | 1208.3 | 1346.7 | 41.8 | 4 | Enterprise SME 4 | 2026-11-30 | Not Started | Shadow IT usage suspected; confirm true user base in workshop.
APM0007793 | FEP Italia Portal | Harmonize Enterprise Portal (Fasihi) | Manage BASF QM Process Documentation (Provides), Communicate Internally (Provides) | Data Migration Only | No | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | M | Simple | 55 | 61383199 | Medium | Medium | No | High | GDA/DE | Massimiliano Ronchi | On Premise | Geismar |  | No dependencies | 2027-10-07 | 2027-12-10 | No | 18.4 | 307.7 | 382.1 | 52.3 | 2 | Enterprise SME 1 | 2026-12-05 | In Workshop | Historical data volume to be re-measured prior to sizing sign-off.
APM0007794 | FEP LEAN Portal | Harmonize Enterprise Portal (Fasihi) | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XXS | Simple | 5 | 136257 | Medium | Low | No | High | GBM/OL | Simon Prokschi | On Premise | Nanjing | APM0010981; APM0007791 | Dependencies in same wave |  |  | No | 18.4 | 99.9 | 118.3 | 56.8 | 2 | Enterprise SME 2 | 2026-12-10 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0007795 | FEP Lemfoerde Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Medium | 25 | 845749 | Very High | Medium | Yes | High | PM/CI | Michael Ngo | On Premise | Tarragona | APM0008010; APM0007766 | Dependencies in same wave |  |  | No | 26.4 | 132.5 | 177.5 | 63.3 | 2 | Enterprise SME 3 | 2026-12-26 | Approved | Data retention requirement to be validated before decommissioning.
APM0007796 | FEP Monheim Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | No | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XXS | Medium | 9 | 94809 | Medium | Medium | Yes | Low | EM/HE | Beatrice Spengler | On Premise | Geismar |  | No dependencies | 2027-08-06 |  | Yes | 18.4 | 83.7 | 112.7 | 89.5 |  | Enterprise SME 4 | 2026-12-15 | Approved
APM0007645 | FEP Neopor Internet Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Functional Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Functional Migration | L | Medium | 103 | 1344317439 | Medium | Medium | No | Medium | CPM/LI | Frank Gottfried | On Premise | Nanjing | APM0010981; APM0007779 | Dependencies in earlier wave |  |  | No | 106.4 | 1173 | 1378 | 45.5 | 4 | Enterprise SME 1 | 2026-10-26 | Pending BASF Review
APM0007646 | FEP Newsapp Portal / Newsapp | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XXS | Medium | 6 | 62074 | Low | Low | No | High | COM/EE | Reinhard Staudacher | On Premise | Ludwigshafen |  | No dependencies | 2027-05-19 |  | No | 18.4 | 82.7 | 111.7 | 71.8 | 2 | Enterprise SME 2 | 2026-12-07 | Approved | Interface inventory to be confirmed with integration team.
APM0007799 | FEP Nordic Baltic Portal | Harmonize Enterprise Portal (Fasihi) | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | No | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Functional Migration | S | Medium | 48 | 4931727 | Medium | Medium | Yes | Low | GBE/UN | Charlotte Breinholt | On Premise | Geismar |  | No dependencies |  |  | No | 42.4 | 457.6 | 534.6 | 84.5 | 1 | Enterprise SME 3 | 2027-01-10 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0007801 | FEP PROFIS Portal | Harmonize Enterprise Portal (Fasihi) | BI, Reporting & Analytics (Provides) | Functional Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | L | Very Complex | 132 | 1304796830 | Very High | High | No | High | CDE/OI | Martin Baer | On Premise | Freeport | APM0007665; APM0007793 | Dependencies in earlier wave |  |  | No | 106.4 | 2269.1 | 2670.4333 | 26.3 | 8 | Enterprise SME 4 | 2027-01-03 | Pending BASF Review
APM0007803 | FEP Performance Materials Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Medium | 20 | 1210352 | Medium | High | No | Medium | PM/CI | Michael Ngo | On Premise | Schwarzheide |  | No dependencies |  |  | No | 26.4 | 209.8 | 254.8 | 54 | 3 | Enterprise SME 1 | 2026-11-22 | Approved | Data retention requirement to be validated before decommissioning.
APM0007770 | FEP Petrochemicals App Portal | Harmonize Enterprise Portal (Fasihi) | Cash Flow Statement (Provides) | Data Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Medium | 15 | 1483532 | Low | High | No | Low | CPM/LI | Frank Gottfried | On Premise | Freeport |  | No dependencies |  |  | No | 26.4 | 150.7 | 195.7 | 60 | 3 | Enterprise SME 2 | 2026-12-26 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0007648 | FEP Petrochemicals Extranet Portal /CP Extranet Portal | Harmonize Enterprise Portal (Fasihi) | Provide Other Technical Services (Provides), Communicate Externally (Provides) | Functional Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Complex | 19 | 1192936 | Medium | High | No | Medium | CPM/LI | Frank Gottfried | On Premise | Global | APM0007780; APM0007822 | Dependencies in earlier wave |  |  | No | 26.4 | 327 | 392.3333 | 49.5 | 6 | Enterprise SME 3 | 2026-11-21 | In Workshop
APM0007650 | FEP Polystyrol Internet Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Data Migration Only | Yes | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | Fasihi Enterprise Portal | Data Migration Only | S | Very Complex | 39 | 4795259 | Medium | Critical | No | Low | CPM/LI | Frank Gottfried | On Premise | Ludwigshafen | APM0007771 | Dependencies in earlier wave |  |  | No | 42.4 | 459 | 604.3333 | 41 |  | Enterprise SME 4 | 2026-10-24 | Not Started | Turnaround window at site must be avoided during cutover.
APM0007816 | FEP Portail France | Harmonize Enterprise Portal (Fasihi) | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Medium | 39 | 4962203 | Medium | Medium | Yes | High | GBE/UF | BRUNO VIGNEAU | On Premise | Ludwigshafen |  | No dependencies |  | 2028-02-11 | No | 42.4 | 280.1 | 357.1 | 81.3 | 1 | Enterprise SME 1 | 2026-11-16 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0007804 | FEP Process Research & Chemical Engineering | Harmonize Enterprise Portal (Fasihi) | Product, Production Process and System Innovation Management (Provides) | Functional Migration Only | No | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | L | Medium | 135 | 1496631082 | High | Medium | No | Low | COM/EE | Timo Gehrlein | On Premise | Global |  | No dependencies |  |  | No | 106.4 | 1157.6 | 1362.6 | 46.3 | 4 | Enterprise SME 2 | 2026-10-19 | Approved | Data retention requirement to be validated before decommissioning.
APM0007805 | FEP Production & Technical Academy Portal | Harmonize Enterprise Portal (Fasihi) | Support Learning Experience (Provides) | Data Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XXS | Medium | 7 | 101430 | Low | Medium | Yes | Medium | ESH/VA | Markus Haas | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 75.4 | 93.8 | 92.5 | 1 | Enterprise SME 3 | 2026-11-01 | Not Started | Vendor licence expires mid-programme; align cutover accordingly.
APM0007806 | FEP R & D Portal | Harmonize Enterprise Portal (Fasihi) | R&D Portfolio and Competencies Management (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | M | Simple | 73 | 127520674 | Medium | Low | No | High | COM/EE | Ulrike Brandt | On Premise | Antwerp | APM0007648 | Dependencies in same wave |  |  | No | 18.4 | 531.9 | 606.3 | 47.8 | 2 | Enterprise SME 4 | 2026-11-25 | Approved
APM0007649 | FEP REACH 22 SC / REACH | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Data Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Medium | 29 | 563237 | Medium | Medium | Yes | High | CPM/LI | Frank Gottfried | On Premise | Schwarzheide |  | No dependencies |  |  | No | 26.4 | 160 | 205 | 84.3 | 1 | Enterprise SME 1 | 2026-10-25 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0007651 | FEP Reec Portal | Harmonize Enterprise Portal (Fasihi) | Track Substance Volumes (Provides), Communicate Externally (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Complex | 47 | 4179913 | High | Critical | No | High | CPM/LI | Frank Gottfried | On Premise | Tarragona |  | No dependencies |  |  | Yes | 42.4 | 304.4 | 417.7333 | 37 |  | Enterprise SME 2 | 2026-11-24 | Pending BASF Review
APM0007807 | FEP Responsible Care Bioscience Research Portal | Harmonize Enterprise Portal (Fasihi) | R&D Portfolio and Competencies Management (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Medium | 21 | 711736 | Medium | Low | Yes | Low | RG/PE | Axel Kleemann | On Premise | Ludwigshafen |  | No dependencies | 2027-10-20 |  | No | 26.4 | 265.8 | 310.8 | 93.5 | 1 | Enterprise SME 3 | 2026-12-14 | Approved
APM0007808 | FEP Schwarzheide Intranet Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | XS | Simple | 20 | 857138 | Low | Low | Yes | Medium | ESS/TTM | Henry Helmut Neufeld | On Premise | Antwerp |  | No dependencies | 2027-07-18 |  | No | 18.4 | 105.2 | 131.6 | 96.5 | 1 | Enterprise SME 4 | 2026-10-05 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0007809 | FEP Schweiz Portal | Harmonize Enterprise Portal (Fasihi) | Web content Management (Provides), Provide Technical Services R&D (Provides), Knowledge Management (Provides), File Conversion (Provides), Enterprise Search (Provides), Document Signing (Provides), Document Management (Provides), Communicate Internally (Provides), Archiving and Records Management (Provides) | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | S | Medium | 38 | 6360440 | Medium | Medium | Yes | High | EVM/EKO | Antonio Ratto | On Premise | Freeport | APM0007804 | Dependencies in same wave |  |  | No | 42.4 | 433.4 | 510.4 | 70.8 | 1 | Enterprise SME 1 | 2027-01-06 | Approved
APM0007811 | FEP Standortportal Ludwigshafen | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | No | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | M | Medium | 68 | 107890078 | High | Low | No | Low | ESM/KI | Maren Carle | On Premise | Freeport |  | No dependencies |  |  | No | 74.4 | 468.9 | 609.9 | 56.3 | 3 | Enterprise SME 2 | 2026-10-22 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0007653 | FEP Styrenics Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Functional Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Medium | 17 | 1347981 | Low | Medium | Yes | Low | CPM/LI | Frank Gottfried | On Premise | Global |  | No dependencies |  |  | No | 26.4 | 229.5 | 274.5 | 92 | 1 | Enterprise SME 3 | 2026-12-06 | Approved
APM0007652 | FEP Styrodur Portal / Styrodur Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Functional Migration Only | Yes | Overlapping enterprise portal (fasihi) functionality across sites; harmonising onto Fasihi Enterprise Portal removes redundant support effort and standardises process. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Medium | 21 | 888093 | Low | Medium | No | Low | CPM/LI | Frank Gottfried | On Premise | Tarragona | APM0007792; APM0007663 | Dependencies in earlier wave |  |  | No | 26.4 | 260.3 | 305.3 | 62.5 | 3 | Enterprise SME 4 | 2026-11-06 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0007654 | FEP Styropor Internet Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Data Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Simple | 45 | 6170629 | Medium | Low | Yes | High | CPM/LI | Frank Gottfried | On Premise | Antwerp | APM0007769 | Dependencies in same wave |  | 2028-11-01 | No | 18.4 | 189 | 231.4 | 76.8 | 1 | Enterprise SME 1 | 2026-12-26 | In Workshop | Vendor licence expires mid-programme; align cutover accordingly.
APM0007656 | FEP TV Service Portal | Harmonize Enterprise Portal (Fasihi) | Web content Management (Provides) | Functional Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Simple | 14 | 1129540 | Low | Low | No | Low | COM/EM | Jens-Georg Fey | On Premise | Freeport |  | No dependencies |  |  | Yes | 18.4 | 166.9 | 193.3 | 73 |  | Enterprise SME 2 | 2026-12-01 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0007813 | FEP Videoload Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Externally (Provides) | Functional Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Functional Migration | M | Simple | 69 | 64271213 | Medium | Low | No | High | GDB/DD | Nico Voelker | On Premise | Schwarzheide |  | No dependencies | 2027-04-12 |  | No | 18.4 | 492.9 | 567.3 | 58.3 | 2 | Enterprise SME 3 | 2027-01-23 | Not Started
APM0007657 | FEP online reporter Portal | Harmonize Enterprise Portal (Fasihi) | Communicate Internally (Provides) | Data Migration Only | Yes | Fragmented enterprise portal (fasihi) landscape drives inconsistent data and duplicated interfaces; consolidation onto Fasihi Enterprise Portal is the agreed target state. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | M | Medium | 55 | 97586918 | Medium | Medium | No | High | COM/EE | Reinhard Staudacher | On Premise | Nanjing | APM0010981 | Dependencies in earlier wave |  |  | No | 74.4 | 444.7 | 585.7 | 47.8 | 4 | Enterprise SME 4 | 2026-12-11 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0013556 | FEP Üchem Portal | Harmonize Enterprise Portal (Fasihi) | Industrial System Infrastructure (Provides) | Data Migration Only | Yes | Application delivers a subset of Fasihi Enterprise Portal capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Fasihi Enterprise Portal | Data Migration Only | S | Simple | 48 | 3390867 | Low | Medium | No | Medium | GDD/PB | Nico Kreutzer | On Premise | Geismar | APM0010981; APM0007813 | Dependencies in earlier wave |  |  | Yes | 18.4 | 181.6 | 224 | 58 |  | Enterprise SME 1 | 2026-10-24 | Approved | Data retention requirement to be validated before decommissioning.
APM0007483 | FEPWEB | Harmonize Enterprise Portal (Fasihi) |  | Functional Migration Only | Yes | Site-local enterprise portal (fasihi) duplicates capability already provided by Fasihi Enterprise Portal; consolidate to reduce licence, hosting and support cost. | Harmonize | Fasihi Enterprise Portal | Functional Migration | XS | Medium | 28 | 865644 | High | Medium | Yes | High | GBW/FFB-OF | Agostina Belen Dreiling | On Premise | Geismar |  | No dependencies |  |  | No | 26.4 | 249.3 | 294.3 | 79 | 1 | Enterprise SME 2 | 2027-01-22 | Not Started
APM0007320 | BASF DEVELOPER PORTAL | Harmonize Integration platform | API Management (Provides) | Functional Migration Only | Yes | Site-local integration platform duplicates capability already provided by BASF Integration Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Integration Platform | Functional Migration | L | Complex | 95 | 600278617 | High | High | No | Mission Critical | GDB/ZI | Matthias Steinhoff | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 1737.9 | 2043.2333 | 34.3 | 7 | Integration SME 1 | 2026-12-20 | Approved
APM0005257 | BASF Integration Hub (BIH) | Harmonize Integration platform | API Management (Provides) | Functional Migration Only | Yes | Overlapping integration platform functionality across sites; harmonising onto BASF Integration Platform removes redundant support effort and standardises process. | Harmonize | BASF Integration Platform | Functional Migration | S | Complex | 49 | 3151021 | High | High | No | High | GDB/ZI | Matthias Steinhoff | Cloud | Freeport |  | No dependencies |  |  | No | 42.4 | 508 | 621.3333 | 44 | 6 | Integration SME 2 | 2027-01-15 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0003548 | KAFKA AWS | Harmonize Kafka Hosting | Data Streaming (Provides) | Functional Migration Only | Yes | Site-local kafka hosting duplicates capability already provided by Managed Kafka Service; consolidate to reduce licence, hosting and support cost. | Harmonize | Managed Kafka Service | Functional Migration | XXS | Complex | 9 | 119844 | Very High | High | No | High | GDB/ZI | Hartmut Zimmermann | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 168.9 | 210.2333 | 43.8 | 6 | Kafka SME 1 | 2026-10-06 | In Workshop
APM0012516 | KAFKA CONFLUENT CLOUD | Harmonize Kafka Hosting | Data Streaming (Provides) | Data Migration Only | Yes | Site-local kafka hosting duplicates capability already provided by Managed Kafka Service; consolidate to reduce licence, hosting and support cost. | Harmonize | Managed Kafka Service | Data Migration Only | XL | Complex | 196 | 13297648024 | High | Medium | No | Mission Critical | GDB/ZI | Patrick Beck | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 138.4 | 1336.6 | 1737.9333 | 38.3 | 7 | Kafka SME 2 | 2026-11-11 | Approved | Turnaround window at site must be avoided during cutover.
APM0001519 | ALMS | Harmonize MES-Solutions | Product, Production Process and System Innovation Management (Provides), Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Functional Migration Only | Yes | Fragmented mes-solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Standard MES Platform is the agreed target state. | Harmonize | BASF Standard MES Platform | Functional Migration | L | Very Complex | 143 | 1313147349 | High | High | No | Mission Critical | RGS/BE | Martin Wende | On Premise | Singapore |  | No dependencies |  |  | No | 106.4 | 2103.7 | 2505.0333 | 34.3 | 8 | MES-Solution SME 1 | 2026-10-19 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0007453 | BASF POLYURETHANE PUR-MES | Harmonize MES-Solutions | Evaluate production progress, quality and efficacy (Provides) | Functional Migration Only | Yes | Overlapping mes-solutions functionality across sites; harmonising onto BASF Standard MES Platform removes redundant support effort and standardises process. | Harmonize | BASF Standard MES Platform | Functional Migration | M | Very Complex | 71 | 120117610 | High | High | No | High | E-PME/OI | Eleonora Gilli | On Premise | Antwerp | APM0001519 | Dependencies in same wave |  |  | No | 74.4 | 1369.6 | 1642.9333 | 29.5 | 8 | MES-Solution SME 2 | 2027-01-08 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0013227 | Bangpoo Thailand MES | Harmonize MES-Solutions | Monitor and analyse production (Provides) | Data Migration Only | Yes | Fragmented mes-solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Standard MES Platform is the agreed target state. | Harmonize | BASF Standard MES Platform | Data Migration Only | M | Medium | 73 | 74205651 | Medium | High | No | Mission Critical | A-PMA/OM | Krit Phetkhlai | On Premise | Singapore | APM0007453 | Dependencies in same wave |  | 2028-11-04 | No | 74.4 | 444.8 | 585.8 | 33 | 5 | MES-Solution SME 3 | 2026-12-17 | Not Started | Data retention requirement to be validated before decommissioning.
APM0004175 | CELLASTO MES - WYANDOTTE | Harmonize MES-Solutions | Compliantly record and store manufacturing data (Provides) | Functional Migration Only | Yes | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Functional Migration | S | Complex | 46 | 4121066 | Medium | High | No | Low | G-PM/AOW | Helbert Ozilio | On Premise | Freeport |  | No dependencies |  |  | No | 42.4 | 609.8 | 723.1333 | 52.5 | 6 | MES-Solution SME 4 | 2026-12-02 | Approved
APM0003985 | CHROMELEON - WYANDOTTE | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Functional Migration Only | Yes | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Functional Migration | XXS | Medium | 9 | 60074 | Low | Low | No | Medium | G-EDJ/OW | Jada Stewart | On Premise | Geismar | APM0004175 | Dependencies in same wave |  |  | No | 18.4 | 119.6 | 148.6 | 63 | 2 | MES-Solution SME 1 | 2026-12-17 | Pending BASF Review
APM0007979 | CNZNG COM TPU MES DB | Harmonize MES-Solutions | Monitor and analyze batch processes (Provides) | Data Migration Only | Yes | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Data Migration Only | L | Very Complex | 146 | 932218751 | Very High | Medium | No | Mission Critical | A-PMA/OT | Tao ZHANG | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 1356.2 | 1757.5333 | 36 | 8 | MES-Solution SME 2 | 2026-11-12 | Approved
APM0007980 | CNZNG TPU PIMS PI | Harmonize MES-Solutions | Compare batches based on historic data (Provides) | Functional Migration Only | Yes | Overlapping mes-solutions functionality across sites; harmonising onto BASF Standard MES Platform removes redundant support effort and standardises process. | Harmonize | BASF Standard MES Platform | Functional Migration | M | Complex | 51 | 71546732 | Medium | High | No | Medium | A-PMA/OT | Tao ZHANG | On Premise | Geismar |  | No dependencies |  |  | No | 74.4 | 944.2 | 1153.5333 | 47 | 6 | MES-Solution SME 3 | 2026-12-21 | Approved | Interface inventory to be confirmed with integration team.
APM0001610 | COMPASS LAB SYSTEM MCINTOSH | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Functional Migration | XXL | Medium | 383 | 150978926022 | High | Medium | No | Mission Critical | EVM/NM | Dawn Johnson | On Premise | Tarragona | APM0007980 | Dependencies in earlier wave |  |  | No | 170.4 | 2845.2 | 3178.2 | 29.8 | 7 | MES-Solution SME 4 | 2026-11-17 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0001869 | EMCE C625 - MES | Harmonize MES-Solutions | Manage and control production assets and their status (Provides) | Functional Migration Only | Yes | Overlapping mes-solutions functionality across sites; harmonising onto BASF Standard MES Platform removes redundant support effort and standardises process. | Harmonize | BASF Standard MES Platform | Functional Migration | M | Complex | 69 | 114464429 | High | High | No | Mission Critical | G-EDM/OE | Christian Gress | On Premise | Global |  | No dependencies | 2027-10-08 |  | No | 74.4 | 920.8 | 1130.1333 | 38.3 | 7 | MES-Solution SME 1 | 2027-01-08 | Approved
APM0009511 | Empower-2-FR-3_DEDUS | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides), Manage BASF QM Process Documentation (Provides) | Data Migration Only | Yes | Overlapping mes-solutions functionality across sites; harmonising onto BASF Standard MES Platform removes redundant support effort and standardises process. | Harmonize | BASF Standard MES Platform | Data Migration Only | M | Simple | 65 | 104843374 | Medium | Low | No | High | EMX/QC | Carolin Warnath | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 322.4 | 396.8 | 58.3 | 2 | MES-Solution SME 2 | 2026-10-21 | Pending BASF Review
APM0003899 | LABWARE_DUS_ANALYTICS | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Functional Migration | XXS | Complex | 7 | 136424 | Low | High | No | Mission Critical | EMX/QC | Carolin Warnath | On Premise | Global |  | No dependencies |  |  | No | 18.4 | 188.4 | 229.7333 | 57 | 4 | MES-Solution SME 3 | 2026-12-25 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0010162 | LABWARE_DUS_ANALYTICS_CO | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Functional Migration | XL | Complex | 164 | 13047077662 | Low | Medium | No | Medium | EMX/QC | Carolin Warnath | On Premise | Sao Paulo |  | No dependencies |  | 2028-11-14 | No | 138.4 | 2614.9 | 3016.2333 | 51.5 | 6 | MES-Solution SME 4 | 2026-10-06 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0001878 | MCINTOSH_WINBLISS_LIMS | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides), Laboratory Data specific Systems (Provides) | Functional Migration Only | No | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Functional Migration | M | Very Complex | 67 | 87364387 | High | Medium | No | High | EVM/NM | Dawn Johnson | On Premise | Geismar |  | No dependencies |  |  | No | 74.4 | 1330.6 | 1603.9333 | 47 | 7 | MES-Solution SME 1 | 2027-01-16 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0004452 | MEGAN | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides), LIMS PIMS Interfaces (Provides) | Data Migration Only | No | Fragmented mes-solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Standard MES Platform is the agreed target state. | Harmonize | BASF Standard MES Platform | Data Migration Only | S | Complex | 38 | 4651615 | Medium | High | No | Medium | GDD/EE | Thomas Leese | On Premise | Antwerp |  | No dependencies | 2026-10-26 |  | No | 42.4 | 302.8 | 416.1333 | 51 | 6 | MES-Solution SME 2 | 2026-11-10 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0008706 | MES INMATION Schwarzheide | Harmonize MES-Solutions | Data Integration (Provides) | Data Migration Only | No | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Data Migration Only | L | Medium | 94 | 514724846 | High | Medium | No | High | ESS/SRT | Torsten Schoenfeld | On Premise | Schwarzheide | APM0001878 | Dependencies in same wave |  | 2028-10-23 | No | 106.4 | 698.2 | 903.2 | 32.5 | 6 | MES-Solution SME 3 | 2026-11-06 | In Workshop | Vendor licence expires mid-programme; align cutover accordingly.
APM0008984 | MES Jobserver | Harmonize MES-Solutions | Compliantly record and store manufacturing data (Provides) | Data Migration Only | Yes | No active users identified during discovery; retire and archive the XS dataset. | Modernize | BASF Standard MES Platform | Data Migration Only | XS | Complex | 17 | 884797 | Low | Critical | No | Medium | ESA/VIS | Tom Hugens | On Premise | Singapore | APM0004175; APM0001610 | Dependencies in earlier wave |  |  | No | 26.4 | 208.8 | 274.1333 | 47 |  | MES-Solution SME 4 | 2026-12-14 | Pending BASF Review
APM0004141 | MES TRENDMINER | Harmonize MES-Solutions | Compliantly record and store manufacturing data (Provides) | Data Migration Only | Yes | Fragmented mes-solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Standard MES Platform is the agreed target state. | Harmonize | BASF Standard MES Platform | Data Migration Only | M | Medium | 61 | 138751957 | Medium | Medium | No | Medium | GEM/TA | Martin Tobias Koersgen | On Premise | Ludwigshafen | APM0001610 | Dependencies in same wave |  |  | No | 74.4 | 469.6 | 610.6 | 43.5 | 3 | MES-Solution SME 1 | 2026-10-16 | Approved
APM0002070 | METROHM | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Data Migration Only | Yes | Overlapping mes-solutions functionality across sites; harmonising onto BASF Standard MES Platform removes redundant support effort and standardises process. | Harmonize | BASF Standard MES Platform | Data Migration Only | XS | Complex | 30 | 560052 | Medium | Medium | No | High | RGS/BE | Martin Wende | On Premise | Antwerp |  | No dependencies |  |  | No | 26.4 | 209.1 | 274.4333 | 59.3 | 4 | MES-Solution SME 2 | 2026-11-22 | Approved
APM0012991 | MYPGU Compounding PM MES | Harmonize MES-Solutions | Define and plan production campaigns (Provides) | Data Migration Only | Yes | Fragmented mes-solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Standard MES Platform is the agreed target state. | Harmonize | BASF Standard MES Platform | Data Migration Only | S | Simple | 47 | 4178858 | Medium | Low | Yes | Medium | A-PMA/OE | Vasyanthan Pandiyan | On Premise | Sao Paulo |  | No dependencies | 2026-12-19 |  | No | 18.4 | 204.6 | 247 | 89 | 1 | MES-Solution SME 3 | 2026-12-02 | Approved
APM0008611 | OM3_LIMS | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides), Laboratory Data specific Systems (Provides) | Functional Migration Only | Yes | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Functional Migration | L | Very Complex | 121 | 1276016567 | High | High | No | High | G-ENP/PO | Sondov Rui | On Premise | Freeport |  | No dependencies |  |  | No | 106.4 | 2130.5 | 2531.8333 | 36 | 8 | MES-Solution SME 4 | 2026-12-10 | Pending BASF Review
APM0003154 | OPENQMLAB | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides), Laboratory Data specific Systems (Provides) | Data Migration Only | No | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Data Migration Only | L | Medium | 79 | 702079028 | High | High | No | High | GDD/EE | Thomas Leese | On Premise | Freeport |  | No dependencies |  |  | No | 106.4 | 678.1 | 883.1 | 36 | 6 | MES-Solution SME 1 | 2026-10-31 | Pending BASF Review
APM0008738 | OSISoft PI System Rudolstadt | Harmonize MES-Solutions | Compliantly record and store manufacturing data (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by BASF Standard MES Platform; retain as-is for this programme and reassess at the next portfolio review. | Modernize | BASF Standard MES Platform | Data Migration Only | M | Complex | 61 | 105801988 | High | Medium | No | High | E-PME/ONM | Ralf Herrmann | On Premise | Sao Paulo | APM0013227 | Dependencies in same wave |  |  | No | 74.4 | 553.4 | 762.7333 | 36.5 |  | MES-Solution SME 2 | 2026-11-23 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0003996 | PI SERVER | Harmonize MES-Solutions | Compare batches based on historic data (Provides), Archive plant data long-term (Provides), Analyse production processes statistically (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Data Migration Only | M | Very Complex | 67 | 124919435 | Medium | High | No | High | GEC/DE | Robert Price | On Premise | Tarragona |  | No dependencies |  |  | No | 74.4 | 751.5 | 1024.8333 | 45.3 | 7 | MES-Solution SME 3 | 2026-12-20 | Approved
APM0003995 | PI SERVER PLANT AUTOMATION | Harmonize MES-Solutions | Compare batches based on historic data (Provides), Archive plant data long-term (Provides), Analyse production processes statistically (Provides) | Functional Migration Only | No | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Functional Migration | XL | Complex | 170 | 13448540149 | High | High | No | Mission Critical | GEC/DE | Robert Price | On Premise | Freeport |  | No dependencies |  |  | No | 138.4 | 2334.6 | 2735.9333 | 31.3 | 7 | MES-Solution SME 4 | 2026-10-05 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0011561 | PM Compounding MES | Harmonize MES-Solutions | Define and plan production campaigns (Provides) | Data Migration Only | Yes | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | BASF Standard MES Platform | Data Migration Only | M | Complex | 59 | 50656882 | High | Medium | No | Medium | A-PMA/OE | Si Qing ZHANG | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 622.5 | 831.8333 | 48.8 |  | MES-Solution SME 1 | 2026-12-02 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0013158 | PM MES Browser | Harmonize MES-Solutions | Monitor and analyse production (Provides) | Data Migration Only | No | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Data Migration Only | S | Very Complex | 37 | 3931976 | High | Critical | No | High | PM/CI | Ulrich Bresch | Mobile App | Schwarzheide |  | No dependencies |  |  | No | 42.4 | 445 | 590.3333 | 37 | 8 | MES-Solution SME 2 | 2026-12-20 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0013299 | PM MES Core | Harmonize MES-Solutions | Schedule plant equipment and assign it to production (Provides) | Data Migration Only | Yes | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Data Migration Only | L | Complex | 85 | 1280121908 | Very High | High | No | Mission Critical | PM/CI | Ulrich Bresch | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 1040.4 | 1345.7333 | 29 | 7 | MES-Solution SME 3 | 2026-10-11 | Approved
APM0007300 | PM MES Ludwigshafen | Harmonize MES-Solutions | Schedule plant equipment and assign it to production (Provides), Report on manufacturing operations (Provides), Monitor and analyze batch processes (Provides), Monitor and analyse production (Provides), Compliantly record and store manufacturing data (Provides) | Data Migration Only | Yes | Fragmented mes-solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Standard MES Platform is the agreed target state. | Harmonize | BASF Standard MES Platform | Data Migration Only | S | Complex | 40 | 5009606 | Medium | Medium | No | High | E-PME/OP | Simon Alexander Gruener | On Premise | Freeport |  | No dependencies |  |  | No | 42.4 | 311.8 | 425.1333 | 56.3 | 5 | MES-Solution SME 4 | 2026-12-17 | In Workshop | Historical data volume to be re-measured prior to sizing sign-off.
APM0008691 | PM MES Schwarzheide | Harmonize MES-Solutions | Schedule plant equipment and assign it to production (Provides) | Data Migration Only | Yes | Fragmented mes-solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Standard MES Platform is the agreed target state. | Harmonize | BASF Standard MES Platform | Data Migration Only | S | Medium | 43 | 6095300 | High | Medium | Yes | High | E-PME/OP | Thomas Ihle | On Premise | Tarragona |  | No dependencies | 2027-11-02 |  | No | 42.4 | 267.9 | 344.9 | 76 | 2 | MES-Solution SME 1 | 2026-10-19 | Pending BASF Review
APM0013157 | PUR MES WHScanner | Harmonize MES-Solutions | Manage and control production assets and their status (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Data Migration Only | M | Medium | 61 | 109387714 | Very High | High | No | Mission Critical | PM/CI | Ulrich Bresch | Mobile App | Nanjing | APM0013299 | Dependencies in same wave | 2027-10-08 |  | No | 74.4 | 416.3 | 557.3 | 22.5 | 6 | MES-Solution SME 2 | 2026-12-23 | Not Started | Shadow IT usage suspected; confirm true user base in workshop.
APM0002857 | PUR-MES MIDDLEWARE | Harmonize MES-Solutions | Schedule plant equipment and assign it to production (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Data Migration Only | XXS | Complex | 5 | 80511 | Medium | Medium | No | High | N-PMN/OO | Zachary Babin | On Premise | Singapore |  | No dependencies |  |  | No | 18.4 | 112.4 | 153.7333 | 61.3 | 4 | MES-Solution SME 3 | 2026-12-28 | Pending BASF Review
APM0003468 | Plant Information Management System (PIMS) BASF Antwerpen | Harmonize MES-Solutions | Archive plant data long-term (Provides) | Functional Migration Only | Yes | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Functional Migration | S | Medium | 49 | 4085125 | Medium | Medium | No | Medium | ESA/VID | Petra Roefs | On Premise | Geismar | APM0008691 | Dependencies in earlier wave |  |  | No | 42.4 | 371 | 448 | 53.5 | 3 | MES-Solution SME 4 | 2027-01-23 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0009832 | QM Toller CoA Cloud | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Data Migration Only | No | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Data Migration Only | S | Complex | 44 | 5242750 | Medium | Medium | No | Mission Critical | GDD/ED | Aurea Trevizanoto | Cloud | Singapore | APM0003996; APM0008611 | Dependencies in same wave |  |  | No | 42.4 | 352.3 | 465.6333 | 44 | 5 | MES-Solution SME 1 | 2027-01-17 | Disputed | Historical data volume to be re-measured prior to sizing sign-off.
APM0008839 | QM Toller CoA via browser | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Data Migration Only | Yes | Overlapping mes-solutions functionality across sites; harmonising onto BASF Standard MES Platform removes redundant support effort and standardises process. | Harmonize | BASF Standard MES Platform | Data Migration Only | S | Medium | 42 | 5627727 | High | High | No | Mission Critical | GDD/ED | Aurea Trevizanoto | On Premise | Antwerp | APM0008611 | Dependencies in same wave |  |  | No | 42.4 | 234.3 | 311.3 | 31.8 | 5 | MES-Solution SME 2 | 2027-01-15 | Approved
APM0002611 | QSIS | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Standard MES Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Standard MES Platform | Functional Migration | S | Complex | 46 | 6638250 | Medium | High | No | High | G-EVP/QM | Alexander-Klaus Adleff | On Premise | Ludwigshafen | APM0001610 | Dependencies in same wave | 2026-10-16 |  | No | 42.4 | 597.1 | 710.4333 | 38.8 | 6 | MES-Solution SME 3 | 2026-11-26 | Approved | Turnaround window at site must be avoided during cutover.
APM0002256 | QUANTOS | Harmonize MES-Solutions | Manage SAP QM Integration (Instruments, MES, PIMS, LIMS, WM) (Provides), LIMS PIMS Interfaces (Provides), Laboratory Data specific Systems (Provides) | Functional Migration Only | Yes | Fragmented mes-solutions landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Standard MES Platform is the agreed target state. | Harmonize | BASF Standard MES Platform | Functional Migration | S | Medium | 34 | 3738985 | Low | Medium | Yes | Medium | ENT/QC | Heiko Schneller | On Premise | Schwarzheide |  | No dependencies |  |  | No | 42.4 | 420.7 | 497.7 | 87.5 | 1 | MES-Solution SME 4 | 2026-11-21 | Approved
APM0004139 | VI FRAMEWORK | Harmonize MES-Solutions | Schedule plant equipment and assign it to production (Provides), Report on manufacturing operations (Provides), Order assignment for running production campaigns (Provides), Monitor and analyse production (Provides), Evaluate production progress, quality and efficacy (Provides) | Functional Migration Only | Yes | Site-local mes-solutions duplicates capability already provided by BASF Standard MES Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Standard MES Platform | Functional Migration | M | Medium | 56 | 72627306 | Medium | Critical | No | Mission Critical | GDD/BB | Christian Fuchs | Hybrid | Schwarzheide | APM0010162 | Dependencies in earlier wave |  |  | No | 74.4 | 703.5 | 844.5 | 32 | 7 | MES-Solution SME 1 | 2026-11-05 | Approved
APM0011034 | Apparatendossier Static | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Functional Migration Only | No | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Complex | 73 | 81289749 | Very High | High | No | High | ESP/TWS | Kristof Bessems | Cloud | Singapore |  | No dependencies |  |  | No | 74.4 | 871.7 | 1081.0333 | 34.8 | 7 | Maintenance SME 1 | 2026-12-10 | Pending BASF Review | Interface inventory to be confirmed with integration team.
APM0013202 | Auma Assistant | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Medium | 70 | 146259231 | Medium | High | No | Mission Critical | ESP/IMA | Kristof Lauman | Mobile App | Ludwigshafen | APM0011034 | Dependencies in same wave | 2027-06-14 | 2027-11-15 | No | 74.4 | 447.2 | 588.2 | 33 | 5 | Maintenance SME 2 | 2026-10-08 | Approved
APM0010434 | BASANT MatMan | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Functional Migration Only | No | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | L | Simple | 116 | 1191717428 | Medium | Low | No | High | ESP/TM | Tamara van Geel | Cloud | Nanjing |  | No dependencies |  |  | No | 18.4 | 898.5 | 1004.9 | 54.3 | 2 | Maintenance SME 3 | 2026-11-22 | Pending BASF Review
APM0001942 | BASANT PLUTOS OAPEX PLATFORM | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | No | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Very Complex | 68 | 137130540 | Low | Critical | No | Medium | ESA/VIS | Tom Hugens | On Premise | Antwerp |  | No dependencies |  |  | No | 74.4 | 856.8 | 1130.1333 | 44.5 | 7 | Maintenance SME 4 | 2026-10-05 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0011224 | BASANT PLUTOS Tankinspecties | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | XXS | Medium | 8 | 104350 | Low | Medium | Yes | Medium | ESA/VIS | Tom Hugens | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 131.4 | 160.4 | 92.5 | 1 | Maintenance SME 1 | 2026-10-11 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0004476 | BASANT SPECTOR | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | No | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Simple | 71 | 107809271 | Very High | Low | No | Medium | ESP/TQI | Anthony Vervisch | On Premise | Ludwigshafen | APM0011224; APM0013202 | Dependencies in same wave |  | 2028-05-01 | No | 18.4 | 325.5 | 399.9 | 39 | 3 | Maintenance SME 2 | 2027-01-17 | Approved
APM0009829 | BASANT SmartKIS | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Data Migration Only | L | Simple | 135 | 634545789 | High | Low | No | High | ESP/TM | Tamara van Geel | Cloud | Tarragona | APM0004476; APM0011224 | Dependencies in same wave |  |  | No | 18.4 | 625.4 | 731.8 | 38.5 | 3 | Maintenance SME 3 | 2026-12-21 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0012888 | BASANT SmartValve | Harmonize Maintenance Management Systems | Provide Valves and Fittings (Provides) | Functional Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Complex | 54 | 111428998 | Very High | High | No | High | ESP/TWI | Maxime Pittomvils | Cloud | Antwerp | APM0011034 | Dependencies in earlier wave | 2027-01-15 |  | No | 74.4 | 1096.5 | 1170.9 | 30.3 | 8 | Maintenance SME 4 | 2026-11-16 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0009774 | BASANT Smaxx | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Data Migration Only | XXS | Medium | 7 | 75441 | Low | High | No | High | ESP/TWO | Dries Jordaens | Cloud | Antwerp |  | No dependencies |  |  | No | 18.4 | 75.1 | 104.1 | 58.8 | 3 | Maintenance SME 1 | 2026-12-30 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0009310 | BASANT TEMAS | Harmonize Maintenance Management Systems | Provide Maintenance Master Data (Provides) | Functional Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Functional Migration | L | Complex | 136 | 655386288 | Very High | High | No | Mission Critical | ESA/VIO | Isabel Teschke | Cloud | Global | APM0004476 | Dependencies in earlier wave |  |  | Yes | 106.4 | 1773.9 | 2079.2333 | 24.5 |  | Maintenance SME 2 | 2026-10-13 | Not Started | Historical data volume to be re-measured prior to sizing sign-off.
APM0003936 | BASANT Ultimo | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Functional Migration | L | Medium | 123 | 1126510847 | Very High | Medium | No | High | ESP/TWC | Freddy Maes | Cloud | Singapore |  | No dependencies | 2027-04-30 | 2028-02-28 | No | 106.4 | 1172.3 | 1377.3 | 37.8 | 5 | Maintenance SME 3 | 2026-11-12 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0009546 | BASF SSAM | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Data Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Data Migration Only | XS | Medium | 11 | 1277790 | Medium | Medium | Yes | Low | GEM/TI | Marcus Steg | Cloud | Global |  | No dependencies |  |  | No | 26.4 | 161.8 | 206.8 | 87.5 | 1 | Maintenance SME 4 | 2026-12-10 | Pending BASF Review | Interface inventory to be confirmed with integration team.
APM0009278 | BPCC E-COST | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides), Provide Maintenance Management (Provides) | Data Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Data Migration Only | S | Simple | 46 | 3463343 | Medium | Critical | No | Mission Critical | A-CMA/CM | Da Gui ZHANG | On Premise | Global | APM0009546; APM0011224 | Dependencies in earlier wave |  |  | No | 18.4 | 176.3 | 218.7 | 36 | 4 | Maintenance SME 1 | 2026-12-12 | Approved | Awaiting confirmation of site-local process variations.
APM0012140 | BPCC Maint.Reliability | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Functional Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Medium | 55 | 77363688 | Medium | Low | No | High | A-CMA/CM | Yang Bin LEI | On Premise | Antwerp | APM0011224; APM0009310 | Dependencies in earlier wave |  |  | No | 74.4 | 724.5 | 865.5 | 53.8 | 3 | Maintenance SME 2 | 2026-12-04 | Not Started
APM0009847 | BSW-Maschinentechnik Cockpit | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Functional Migration | XS | Simple | 23 | 891916 | Medium | Medium | Yes | High | ESS/TTT | Michael Herrich | Cloud | Antwerp | APM0009278; APM0009774 | Dependencies in same wave |  |  | No | 18.4 | 158.8 | 185.2 | 73.8 | 1 | Maintenance SME 3 | 2027-01-02 | Pending BASF Review
APM0012127 | Beamex bMobile | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | SAP PM / Standard MMS | Data Migration Only | S | Complex | 44 | 4882183 | Low | Critical | No | Medium | N-CPN/OR | Yusuff Folahan | Mobile App | Geismar | APM0004476; APM0009278 | Dependencies in same wave |  | 2027-10-23 | No | 42.4 | 329.8 | 443.1333 | 38 |  | Maintenance SME 4 | 2026-10-26 | Approved
APM0008617 | CMX | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Medium | 72 | 129675777 | Medium | Medium | No | High | G-ENP/PO | Martin Terjesen Glosmyr | On Premise | Geismar |  | No dependencies |  |  | No | 74.4 | 706.3 | 847.3 | 52.3 | 3 | Maintenance SME 1 | 2026-12-19 | Approved | Data retention requirement to be validated before decommissioning.
APM0009093 | CMX SQL Server and Client software | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Medium | 72 | 73615431 | Medium | High | No | Mission Critical | EMX/EG | Markus Wittnebel | On Premise | Freeport |  | No dependencies |  |  | No | 74.4 | 509.2 | 650.2 | 43.5 | 4 | Maintenance SME 2 | 2026-10-18 | Pending BASF Review
APM0011282 | COMOS Mobile Worker | Harmonize Maintenance Management Systems | Provide Automation Technology (Provides) | Functional Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Complex | 31 | 3362132 | Low | High | No | Mission Critical | GE/OSTE | Alexander Tomiyama | On Premise | Ludwigshafen | APM0009278 | Dependencies in earlier wave |  |  | No | 42.4 | 520.9 | 634.2333 | 47.5 | 5 | Maintenance SME 3 | 2026-12-30 | Approved | Turnaround window at site must be avoided during cutover.
APM0009197 | CXM Server | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | No | No active users identified during discovery; retire and archive the M dataset. | Modernize | SAP PM / Standard MMS | Data Migration Only | M | Very Complex | 68 | 50811925 | Medium | Medium | No | High | EMX/EG | Markus Wittnebel | Cloud | Geismar |  | No dependencies |  |  | No | 74.4 | 755.6 | 1028.9333 | 52.3 |  | Maintenance SME 4 | 2027-01-23 | Approved
APM0003526 | Cayirova Building Automation | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Data Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Medium | 60 | 121177365 | Low | Low | No | Medium | EMX/ET | Serhan Balkan | On Premise | Freeport |  | No dependencies |  |  | No | 74.4 | 500.1 | 641.1 | 64.5 | 2 | Maintenance SME 1 | 2026-10-06 | Approved
APM0009861 | Comburi | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Functional Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Functional Migration | XS | Very Complex | 14 | 584663 | Medium | Critical | No | High | ESO/M | Markus Weigold | Cloud | Geismar | APM0009093 | Dependencies in earlier wave |  |  | No | 26.4 | 356.9 | 438.2333 | 40.8 | 8 | Maintenance SME 2 | 2027-01-06 | Approved | Turnaround window at site must be avoided during cutover.
APM0012100 | Cumulus | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Complex | 41 | 3133847 | Very High | High | No | High | N-PMN/OO | Nathan Kelley | Mobile App | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 518.2 | 631.5333 | 38.8 | 7 | Maintenance SME 3 | 2026-12-10 | Not Started | Awaiting confirmation of site-local process variations.
APM0006643 | DESIGO ITALY | Harmonize Maintenance Management Systems | Provide Automation Technology (Provides) | Functional Migration Only | No | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Complex | 32 | 5736296 | Medium | Critical | No | High | GBE/WI-Y | Alessandra Cantone | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 527.9 | 641.2333 | 42.3 | 7 | Maintenance SME 4 | 2026-11-11 | Approved | Turnaround window at site must be avoided during cutover.
APM0004861 | DICHTFLAECHEN-DB | Harmonize Maintenance Management Systems | Provide Process Engineering (Provides), Manage Water Protection (Provides) | Data Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Complex | 59 | 122697171 | Low | Medium | No | High | ESO/BP | Sebastian Wiesner | On Premise | Global |  | No dependencies |  | 2028-11-28 | No | 74.4 | 549.8 | 759.1333 | 56.8 | 5 | Maintenance SME 1 | 2026-11-06 | Approved | Awaiting confirmation of site-local process variations.
APM0009626 | Desigo_PM_Italy | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Functional Migration Only | No | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Medium | 33 | 5415286 | Low | Medium | No | High | EVM/EPS | Andrea Cristani | On Premise | Antwerp | APM0013202 | Dependencies in same wave | 2027-11-25 |  | No | 42.4 | 410 | 487 | 50.3 | 3 | Maintenance SME 2 | 2027-01-11 | Approved | Turnaround window at site must be avoided during cutover.
APM0012735 | DevCom HART Communicator | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Medium | 68 | 123436111 | Medium | Low | No | High | ESP/CP | Wim Vermeulen | Mobile App | Geismar | APM0004861; APM0009093 | Dependencies in same wave |  |  | No | 74.4 | 739.8 | 880.8 | 47.8 | 3 | Maintenance SME 3 | 2026-11-10 | Not Started | Data retention requirement to be validated before decommissioning.
APM0013203 | Electrical Calculations | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Medium | 46 | 5731505 | Medium | High | No | High | ESP/IMA | Kristof Lauman | Mobile App | Global |  | No dependencies |  | 2028-08-03 | No | 42.4 | 406.6 | 483.6 | 49.3 | 4 | Maintenance SME 4 | 2026-11-04 | In Workshop
APM0013204 | Endress+Hauser Tools | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Complex | 55 | 81326982 | Medium | Medium | No | Medium | ESP/IMA | Kristof Lauman | Mobile App | Schwarzheide |  | No dependencies |  | 2027-10-02 | No | 74.4 | 546.9 | 756.2333 | 54 | 5 | Maintenance SME 1 | 2027-01-19 | Approved | Interface inventory to be confirmed with integration team.
APM0006500 | Engineering Citrix Applications North America | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Simple | 54 | 87595844 | Medium | Low | No | Mission Critical | GEC/OD | Wayne Sterling | On Premise | Ludwigshafen | APM0010434; APM0003526 | Dependencies in same wave |  |  | No | 18.4 | 565.9 | 640.3 | 46 | 2 | Maintenance SME 2 | 2026-11-06 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0009275 | Engineering Risk Assessment Database | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Simple | 42 | 4330618 | Medium | Low | No | Medium | G-ENN/OX | Thorsten Hauk | Cloud | Tarragona | APM0011224 | Dependencies in earlier wave |  | 2028-09-24 | No | 18.4 | 319.7 | 362.1 | 59.5 | 2 | Maintenance SME 3 | 2026-10-14 | Approved | Interface inventory to be confirmed with integration team.
APM0005091 | GSI_Gen_Ship | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by SAP PM / Standard MMS; retain as-is for this programme and reassess at the next portfolio review. | Modernize | SAP PM / Standard MMS | Data Migration Only | M | Simple | 70 | 114033526 | High | Low | No | High | GEC/OF | Melissa Brigance | On Premise | Global |  | No dependencies |  |  | No | 18.4 | 334.8 | 409.2 | 53 |  | Maintenance SME 4 | 2027-01-12 | In Workshop | Interface inventory to be confirmed with integration team.
APM0009175 | General Electric Asset Performance Management | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Simple | 74 | 98206634 | Medium | Medium | No | High | ESP/TQI | Anthony Vervisch | On Premise | Tarragona |  | No dependencies |  |  | No | 18.4 | 489.2 | 563.6 | 52.3 | 2 | Maintenance SME 1 | 2027-01-11 | Approved
APM0011715 | Horas de Mantenimiento | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Data Migration Only | No | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | XS | Simple | 22 | 1160734 | Low | Medium | No | Medium | ES/TE | JORDI SOLANAS | Cloud | Nanjing | APM0013202 | Dependencies in same wave |  | 2028-05-10 | No | 18.4 | 110 | 136.4 | 55 | 2 | Maintenance SME 2 | 2027-01-16 | Approved | Interface inventory to be confirmed with integration team.
APM0004571 | IDA | Harmonize Maintenance Management Systems | Provide Maintenance Master Data (Provides) | Functional Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Functional Migration | XXS | Simple | 5 | 90550 | High | High | No | High | GDD/DG | Frank Tillwick | On Premise | Freeport |  | No dependencies | 2027-10-12 |  | No | 18.4 | 99.5 | 117.9 | 49 | 3 | Maintenance SME 3 | 2026-12-23 | Approved
APM0003948 | IMAGIC BILDANALYSE | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | No | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | XXS | Complex | 7 | 132073 | High | Medium | No | Mission Critical | GEM/TM | Jens Augspurger | On Premise | Ludwigshafen |  | No dependencies | 2027-01-12 |  | No | 18.4 | 185.7 | 227.0333 | 54.3 | 5 | Maintenance SME 4 | 2026-12-30 | Approved | Interface inventory to be confirmed with integration team.
APM0002055 | INTELATRAC PORT ARTHUR | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by SAP PM / Standard MMS; retain as-is for this programme and reassess at the next portfolio review. | Modernize | SAP PM / Standard MMS | Data Migration Only | XL | Complex | 158 | 8215898859 | Medium | Low | No | Medium | N-CPN/PO | Wendel Langley | On Premise | Ludwigshafen | APM0003936; APM0006643 | Dependencies in earlier wave |  | 2027-10-10 | No | 138.4 | 1579.1 | 1980.4333 | 48.5 |  | Maintenance SME 1 | 2026-11-22 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0001497 | IRS - PORT ARTHUR | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides), Provide Maintenance Master Data (Provides) | Data Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Data Migration Only | L | Medium | 86 | 1206741248 | High | High | No | High | N-CPN/PSR | Charles Huddleston | On Premise | Ludwigshafen | APM0013204 | Dependencies in earlier wave |  | 2027-12-31 | No | 106.4 | 795.4 | 1000.4 | 31.5 | 6 | Maintenance SME 2 | 2026-10-16 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0004331 | ISM ONLINE | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | No active users identified during discovery; retire and archive the S dataset. | Modernize | SAP PM / Standard MMS | Data Migration Only | S | Simple | 37 | 3767611 | High | High | No | Mission Critical | ESP/TWR | Jeroen Dirkx | Third Party Hosted | Global |  | No dependencies |  |  | No | 18.4 | 169.6 | 212 | 42.3 |  | Maintenance SME 3 | 2026-10-24 | Pending BASF Review
APM0004812 | Integrated Condition Monitoring & Maintenance Prediction (ICMP) | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides), Monitoring of conditions (Provides), BI, Reporting & Analytics (Provides) | Data Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Simple | 51 | 55402761 | High | Medium | No | Medium | GDD/EA | Norman Volkert | Cloud | Nanjing | APM0004571 | Dependencies in earlier wave |  | 2028-02-25 | No | 18.4 | 358.1 | 432.5 | 44.3 | 4 | Maintenance SME 4 | 2026-11-15 | Approved | Data retention requirement to be validated before decommissioning.
APM0013466 | KolonnenSteckbrief | Harmonize Maintenance Management Systems | Provide Process Engineering (Provides) | Data Migration Only | No | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | S | Medium | 37 | 5950991 | Medium | Medium | No | Medium | RGR/AE | Juergen Paschold | On Premise | Ludwigshafen |  | No dependencies |  | 2028-01-14 | No | 42.4 | 264.6 | 341.6 | 58 | 3 | Maintenance SME 1 | 2026-10-30 | Approved
APM0004615 | LINSPEC | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides), Provide Plant Maintenance (Provides) | Data Migration Only | No | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Medium | 64 | 95857892 | High | High | No | Mission Critical | E-CMP/OA | Abderrahmane TAICHE | On Premise | Tarragona |  | No dependencies |  |  | No | 74.4 | 413.4 | 554.4 | 38.3 | 5 | Maintenance SME 2 | 2026-12-06 | Not Started
APM0003202 | LUBEIT | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Functional Migration Only | No | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Complex | 58 | 51450385 | Medium | Medium | No | Medium | GEC/OG | Stacie Ocmand | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 872.1 | 1081.4333 | 54 | 5 | Maintenance SME 3 | 2027-01-06 | In Workshop | Awaiting confirmation of site-local process variations.
APM0012156 | Limble CMMS | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Functional Migration Only | No | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Medium | 33 | 4809765 | High | Medium | Yes | Low | GEC/OF | Colin Varner | Cloud | Antwerp |  | No dependencies |  |  | No | 42.4 | 430.4 | 507.4 | 79.3 | 2 | Maintenance SME 4 | 2027-01-08 | Pending BASF Review
APM0004022 | MEX MAINTENANCE | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | S | Simple | 35 | 6159434 | Low | Medium | No | High | G-ENN/OA | Niven Runghen | On Premise | Antwerp | APM0009093 | Dependencies in same wave |  |  | No | 18.4 | 198.4 | 240.8 | 50.3 | 2 | Maintenance SME 1 | 2026-11-16 | In Workshop
APM0001428 | MOBILE EASYKEY | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | No | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Very Complex | 61 | 138797790 | Medium | High | No | High | ESL/RM | Daniel Schneider | On Premise | Freeport | APM0012140; APM0009774 | Dependencies in earlier wave | 2027-06-02 |  | No | 74.4 | 1327 | 1600.3333 | 40.8 | 8 | Maintenance SME 2 | 2027-01-02 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0011156 | Maintenance Connection | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | No | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | S | Very Complex | 43 | 4108581 | Low | High | No | High | E-PME/OW | Richard Portman | Cloud | Schwarzheide |  | No dependencies |  |  | No | 42.4 | 468.5 | 613.8333 | 53.8 | 7 | Maintenance SME 3 | 2027-01-16 | Disputed | Awaiting confirmation of site-local process variations.
APM0008863 | MobilServ | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Functional Migration | XS | Complex | 22 | 1397945 | Medium | Medium | No | Medium | ESP/TWO | Dries Jordaens | Cloud | Nanjing |  | No dependencies |  |  | No | 26.4 | 352.5 | 417.8333 | 61 | 4 | Maintenance SME 4 | 2026-10-21 | Pending BASF Review
APM0006761 | NewLift | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Complex | 39 | 3756242 | Medium | High | No | Mission Critical | ESO/SL | Christoph Glasder | On Premise | Freeport |  | No dependencies |  |  | No | 42.4 | 551.2 | 664.5333 | 47.5 | 6 | Maintenance SME 1 | 2026-12-02 | Approved
APM0004616 | OPTIMU | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Data Migration Only | L | Medium | 108 | 726781938 | Medium | Medium | No | Mission Critical | E-CMP/OA | Damien Stoessel | On Premise | Global |  | No dependencies |  |  | No | 106.4 | 697.1 | 902.1 | 46.5 | 4 | Maintenance SME 2 | 2026-12-29 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0001139 | PEMAC/CALIB ARCHIVE | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Data Migration Only | S | Simple | 34 | 4763554 | Very High | Medium | Yes | High | EVM/EC | Davide Monti | On Premise | Nanjing |  | No dependencies | 2026-10-13 |  | No | 18.4 | 190 | 232.4 | 70.8 | 1 | Maintenance SME 3 | 2026-12-02 | Not Started
APM0012422 | Plant Service Suite | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Functional Migration | XXS | Complex | 9 | 83128 | Very High | Critical | No | Medium | ESS/SRD | Vinh Van | Cloud | Freeport | APM0013204 | Dependencies in earlier wave |  | 2027-10-27 | No | 18.4 | 164.8 | 206.1333 | 34 | 7 | Maintenance SME 4 | 2027-01-20 | Approved | Turnaround window at site must be avoided during cutover.
APM0009572 | Portal Digitale Laufkarten Schwarzheide | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Functional Migration | XS | Simple | 30 | 695149 | Low | Low | No | High | ESS/TEM | Sandro Richter | Cloud | Schwarzheide |  | No dependencies |  |  | No | 18.4 | 180.4 | 206.8 | 69.8 | 2 | Maintenance SME 1 | 2026-10-12 | Not Started | Interface inventory to be confirmed with integration team.
APM0011787 | Pragma OnKey (South Africa) | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Data Migration Only | S | Complex | 43 | 4478519 | High | Critical | No | High | E-EDE/OAS | Patrick Perumal | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 324.7 | 438.0333 | 37 | 7 | Maintenance SME 2 | 2026-11-28 | In Workshop | Interface inventory to be confirmed with integration team.
APM0013517 | PruefuebersichtKleinhebezeuge | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Functional Migration | XS | Complex | 12 | 643639 | Very High | Medium | No | High | ESO/ES | Marton Sarosi | Cloud | Freeport |  | No dependencies |  |  | Yes | 26.4 | 292.1 | 357.4333 | 48.8 |  | Maintenance SME 3 | 2026-12-16 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0004152 | RACE | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides), Provide E&I Engineering (Provides) | Functional Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | XS | Complex | 19 | 1053866 | Medium | Medium | No | Mission Critical | ESO/SE | Andreas Hinkel | On Premise | Nanjing | APM0008617 | Dependencies in earlier wave |  | 2028-04-19 | No | 26.4 | 310.5 | 375.8333 | 53 | 4 | Maintenance SME 4 | 2027-01-01 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0008909 | ROTATION DB | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Data Migration Only | XS | Medium | 12 | 1098891 | High | Low | No | High | ESO/SR | Peter Horst | On Premise | Sao Paulo |  | No dependencies | 2027-02-10 |  | No | 26.4 | 132.8 | 177.8 | 60 | 2 | Maintenance SME 1 | 2027-01-01 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0010330 | ReBuild | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | XXS | Medium | 10 | 141210 | Medium | High | No | High | ESO/B | Steffen Neu | Hybrid | Singapore | APM0006761 | Dependencies in same wave |  |  | No | 18.4 | 86.8 | 115.8 | 43.8 | 3 | Maintenance SME 2 | 2027-01-02 | Pending BASF Review | Awaiting confirmation of site-local process variations.
APM0008066 | S Anywhere BPCN | Harmonize Maintenance Management Systems | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | M | Medium | 54 | 51289766 | Very High | Medium | No | High | EMX/HN | Thomas Kruft | On Premise | Ludwigshafen | APM0009278 | Dependencies in earlier wave |  |  | No | 74.4 | 497.1 | 638.1 | 37.3 | 5 | Maintenance SME 3 | 2027-01-02 | In Workshop
APM0010218 | SAP Fitness-Check | Harmonize Maintenance Management Systems | Provide Maintenance Master Data (Provides) | Functional Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Functional Migration | S | Very Complex | 33 | 6275378 | High | High | No | Medium | GDD/DG | Frank Tillwick | On Premise | Global |  | No dependencies |  |  | No | 42.4 | 620.1 | 765.4333 | 45.8 | 7 | Maintenance SME 4 | 2026-11-02 | Approved
APM0009755 | SAP PM Services Tools | Harmonize Maintenance Management Systems | Provide Maintenance Master Data (Provides) | Functional Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | M | Medium | 56 | 63021825 | High | Low | No | High | GDD/DG | Frank Tillwick | On Premise | Singapore | APM0001139 | Dependencies in earlier wave |  |  | No | 74.4 | 653.9 | 794.9 | 48.5 | 3 | Maintenance SME 1 | 2026-10-06 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0010149 | Scout Platform | Harmonize Maintenance Management Systems | BI, Reporting & Analytics (Provides) | Data Migration Only | Yes | Overlapping maintenance management systems functionality across sites; harmonising onto SAP PM / Standard MMS removes redundant support effort and standardises process. | Harmonize | SAP PM / Standard MMS | Data Migration Only | L | Medium | 100 | 684781824 | Very High | Critical | No | Mission Critical | ESO/SL | Peter Welter | Hybrid | Geismar | APM0011156 | Dependencies in earlier wave | 2027-11-24 |  | No | 106.4 | 667.8 | 872.8 | 17.5 | 8 | Maintenance SME 2 | 2026-10-29 | Not Started | Vendor licence expires mid-programme; align cutover accordingly.
APM0012694 | Sushi Sensor App | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | L | Medium | 87 | 1424232097 | Medium | Medium | No | High | ESP/UMO | Mathias De Dobbelaere | Mobile App | Schwarzheide | APM0004861; APM0013203 | Dependencies in same wave | 2027-03-10 | 2027-10-20 | No | 106.4 | 1215.3 | 1420.3 | 37.8 | 5 | Maintenance SME 3 | 2026-11-20 | In Workshop | Data retention requirement to be validated before decommissioning.
APM0011187 | TE-Partner SAP PM Interface | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Data Migration Only | XS | Medium | 22 | 783611 | Medium | Medium | Yes | Mission Critical | ESO/MT | Antonio Pellicane | Hybrid | Global | APM0011787 | Dependencies in same wave |  | 2028-11-14 | No | 26.4 | 154.6 | 199.6 | 72 | 1 | Maintenance SME 4 | 2026-12-10 | Pending BASF Review
APM0012892 | TPC Training | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Functional Migration | XS | Medium | 28 | 1477570 | Low | Medium | Yes | Medium | N-CMN/PM | Tuan Truong | Third Party Hosted | Global |  | No dependencies |  |  | No | 26.4 | 252.7 | 297.7 | 90.5 | 1 | Maintenance SME 1 | 2026-12-19 | Approved
APM0012769 | Track-It Software | Harmonize Maintenance Management Systems | Provide Plant Maintenance (Provides) | Data Migration Only | Yes | Application delivers a subset of SAP PM / Standard MMS capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP PM / Standard MMS | Data Migration Only | S | Complex | 42 | 6950092 | Medium | Medium | No | High | NAG/U | Kaitlin Sevin | On Premise | Antwerp |  | No dependencies |  |  | Yes | 42.4 | 341.8 | 455.1333 | 56.3 |  | Maintenance SME 2 | 2026-10-27 | Approved
APM0013200 | Vega Tools | Harmonize Maintenance Management Systems | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Site-local maintenance management systems duplicates capability already provided by SAP PM / Standard MMS; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP PM / Standard MMS | Functional Migration | XS | Complex | 13 | 1260171 | Medium | High | No | High | ESP/IMA | Kristof Lauman | Mobile App | Nanjing |  | No dependencies |  |  | No | 26.4 | 280.1 | 345.4333 | 52.3 | 5 | Maintenance SME 3 | 2026-11-29 | Not Started
APM0011677 | Wochenplan | Harmonize Maintenance Management Systems | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Fragmented maintenance management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP PM / Standard MMS is the agreed target state. | Harmonize | SAP PM / Standard MMS | Data Migration Only | S | Medium | 42 | 4770224 | Very High | High | No | High | ESS/SRD | Andreas Wiederhold | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 260.7 | 337.7 | 38.8 | 5 | Maintenance SME 4 | 2026-12-14 | Pending BASF Review
APM0010226 | ACTUS | Harmonize Operations Platform | Incident Management (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 62 | 76339098 | Medium | Critical | No | High | GBW/US-M | Leandro Cabrera | Cloud | Ludwigshafen |  | No dependencies | 2027-04-06 |  | No | 74.4 | 1323.9 | 1597.2333 | 38.3 | 8 | Operations SME 1 | 2026-12-24 | Approved | Turnaround window at site must be avoided during cutover.
APM0007392 | ALLCLEAR | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | M | Very Complex | 63 | 85126926 | Very High | High | No | High | N-PMN/OW | Kenneth Slowik | On Premise | Ludwigshafen | APM0010226 | Dependencies in earlier wave |  |  | No | 74.4 | 784.8 | 1058.1333 | 30.3 | 9 | Operations SME 2 | 2026-10-07 | Pending BASF Review | Awaiting confirmation of site-local process variations.
APM0004798 | ARCHIV GAHD | Harmonize Operations Platform | IT Incident Management (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | XXL | Medium | 399 | 98363205312 | High | Low | No | High | GDB/ZH | Andreas Grosche | On Premise | Sao Paulo |  | No dependencies |  |  | No | 170.4 | 1504 | 1837 | 42 | 5 | Operations SME 3 | 2027-01-13 | Approved | Data retention requirement to be validated before decommissioning.
APM0001502 | AUTOTAS-QMSOFT | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | S | Simple | 42 | 6218412 | High | Medium | Yes | High | ESO/MZ | Jonas Graef | On Premise | Freeport |  | No dependencies |  | 2028-05-04 | No | 18.4 | 304.3 | 322.7 | 76 | 1 | Operations SME 4 | 2026-12-28 | Pending BASF Review | Awaiting confirmation of site-local process variations.
APM0013374 | Access control system | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Medium | 66 | 95322860 | High | Medium | No | Low | PM/LA | Youngchul Jang | On Premise | Freeport | APM0001502; APM0007392; APM0004798 | Dependencies in same wave | 2027-01-11 |  | No | 74.4 | 420.2 | 561.2 | 39.8 | 6 | Operations SME 1 | 2026-12-31 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0013069 | Access control system 门禁系统 | Harmonize Operations Platform | Process Safety (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | M | Very Complex | 52 | 113392748 | High | Medium | No | Medium | EMX/AC | Jian Zhen SONG | Third Party Hosted | Antwerp | APM0010226 | Dependencies in same wave |  |  | No | 74.4 | 770 | 1043.3333 | 38.3 | 7 | Operations SME 2 | 2026-10-09 | Approved | Data retention requirement to be validated before decommissioning.
APM0012394 | Alert Cascade | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides), Incident Management (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | XS | Medium | 18 | 1158670 | Low | Medium | No | Mission Critical | GBE/UU-G | Richard Newsome | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 26.4 | 229.8 | 274.8 | 62 | 2 | Operations SME 3 | 2026-10-16 | Approved
APM0012896 | Ariscu | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | No | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | S | Complex | 46 | 6731741 | Medium | Critical | No | Mission Critical | GBE/UA | Fernando Pienaar | Cloud | Global | APM0012394 | Dependencies in earlier wave |  |  | No | 42.4 | 579.2 | 692.5333 | 36 | 7 | Operations SME 4 | 2026-11-01 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0012354 | Audiodokumentation integrierte Leitstelle LU | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | S | Medium | 43 | 4017223 | Medium | High | No | High | ESE/EC | Michael Heintz | On Premise | Geismar |  | No dependencies |  |  | No | 42.4 | 248.1 | 325.1 | 49.3 | 4 | Operations SME 1 | 2027-01-18 | Approved | Interface inventory to be confirmed with integration team.
APM0013181 | Azure Services Hub - Cloud Platform | Harmonize Operations Platform | IT Incident Management (Provides) | Data Migration Only | No | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | L | Complex | 81 | 1190682455 | Very High | Medium | No | High | GDA/JH | Ruben Imbers | Third Party Hosted | Geismar |  | No dependencies |  |  | No | 106.4 | 981 | 1286.3333 | 37.8 | 7 | Operations SME 2 | 2026-11-24 | Not Started | Awaiting confirmation of site-local process variations.
APM0011789 | BACH Personal Positioning System | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | S | Very Complex | 39 | 3841545 | High | Critical | No | High | ACO/S/EHS | Wei Xin LI | Cloud | Geismar | APM0012896; APM0013181 | Dependencies in earlier wave |  |  | No | 42.4 | 769.4 | 914.7333 | 32.5 | 8 | Operations SME 3 | 2026-10-25 | Pending BASF Review | Awaiting confirmation of site-local process variations.
APM0011784 | BACH Personnel Pisitioning System(PolyTHF Complex) | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | S | Complex | 47 | 5951142 | Medium | High | No | Low | A-CIA/OP | Yong ZHANG | Cloud | Sao Paulo | APM0011789 | Dependencies in same wave | 2027-02-05 |  | No | 42.4 | 380.6 | 493.9333 | 42 | 6 | Operations SME 4 | 2027-01-10 | Approved | Data retention requirement to be validated before decommissioning.
APM0001318 | BAG_REPORTING | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | L | Medium | 136 | 1373505843 | Medium | Medium | No | High | GBE/SW | Patrick Keller | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 768.8 | 973.8 | 48.3 | 4 | Operations SME 1 | 2026-10-07 | Not Started
APM0013349 | BAPN_ACS | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | XL | Very Complex | 162 | 7617831654 | Medium | High | No | High | A-PMA/OS | Yi Fu HU | On Premise | Global | APM0010226 | Dependencies in earlier wave |  |  | No | 138.4 | 1964.6 | 2493.9333 | 33.8 | 9 | Operations SME 2 | 2027-01-04 | Approved
APM0008031 | BASANT Brandblusapparaten | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | S | Complex | 34 | 4725234 | Medium | High | No | Mission Critical | ESA/PF | Gert Van Bortel | On Premise | Ludwigshafen |  | No dependencies |  |  | Yes | 42.4 | 338 | 451.3333 | 47.5 |  | Operations SME 3 | 2026-12-18 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0004216 | BASANT OBSERVANT | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Complex | 20 | 1474399 | Medium | Medium | No | High | ESP/T | Marc Romy | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 26.4 | 191.1 | 256.4333 | 59.3 | 4 | Operations SME 4 | 2026-12-29 | Not Started | Shadow IT usage suspected; confirm true user base in workshop.
APM0004244 | BASF DOCs Report | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | XXS | Complex | 8 | 80250 | Medium | High | No | Mission Critical | GBW/US-M | Lucas Pujol | On Premise | Antwerp |  | No dependencies |  | 2028-05-19 | No | 18.4 | 181.5 | 222.8333 | 52.5 | 5 | Operations SME 1 | 2026-11-07 | Approved | Interface inventory to be confirmed with integration team.
APM0012939 | BASF DOCs Report Script | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | XXL | Complex | 371 | 162173505157 | Very High | High | No | Mission Critical | GBW/US-M | Lucas Pujol | On Premise | Antwerp | APM0011789; APM0004216 | Dependencies in earlier wave |  |  | No | 170.4 | 2314.6 | 2811.9333 | 17.5 | 9 | Operations SME 2 | 2026-10-24 | Approved
APM0010064 | BASF PD Site Contractor Safety Management system | Harmonize Operations Platform | Track employee training and match it to operational requirements (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | XXS | Medium | 10 | 96713 | Very High | Medium | No | High | ACO/R/E | Zhi Rui SHEN | Cloud | Nanjing | APM0013374; APM0001502 | Dependencies in same wave |  |  | No | 18.4 | 137.4 | 166.4 | 40.3 | 4 | Operations SME 3 | 2026-12-16 | Not Started
APM0010737 | BCJC - Digital EHS Management Platform | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Very Complex | 68 | 68056884 | Medium | Medium | No | High | G-EDM/OC | Ran Ran XU | Cloud | Antwerp |  | No dependencies |  |  | No | 74.4 | 708.1 | 981.4333 | 52.3 | 7 | Operations SME 4 | 2026-10-08 | Approved
APM0007117 | BEACHWOOD ACCESS SERVICE FOR CHEMICAL INVENTORY AND SDS | Harmonize Operations Platform | Manage Safety Data Sheet (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Very Complex | 69 | 115800630 | Very High | High | No | High | RGC/CN | David Disantis | On Premise | Global |  | No dependencies | 2026-10-25 |  | No | 74.4 | 741.3 | 1014.6333 | 34.8 | 8 | Operations SME 1 | 2027-01-08 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0011496 | BIG Field Safety Observation | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 17 | 1465049 | High | Medium | Yes | Mission Critical | AMC/OEO | Zhan Jie LONG | Cloud | Singapore |  | No dependencies |  |  | No | 26.4 | 159.4 | 204.4 | 77.3 | 1 | Operations SME 2 | 2026-12-31 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0012548 | BIG Kaleidos | Harmonize Operations Platform | Incident Management (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 66 | 69987126 | Low | High | No | Medium | ESA/PF | Tom Engels | Mobile App | Geismar |  | No dependencies |  | 2028-12-06 | No | 74.4 | 1203.7 | 1477.0333 | 51.5 | 7 | Operations SME 3 | 2026-11-02 | Pending BASF Review
APM0010020 | BIG Smart Visitor Management | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | XL | Complex | 191 | 10246777838 | Medium | High | No | Mission Critical | AMC/OES | Rui ZHANG | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 138.4 | 2105.3 | 2506.6333 | 36.5 | 7 | Operations SME 4 | 2026-10-10 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0012225 | BIG Smart Visitor Management System | Harmonize Operations Platform | Manage Site Security (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | M | Complex | 73 | 106847821 | Low | High | No | Medium | AMC/OES | Rui ZHANG | Cloud | Tarragona | APM0001318 | Dependencies in earlier wave |  |  | No | 74.4 | 644.9 | 854.2333 | 47 | 6 | Operations SME 1 | 2026-12-01 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0012674 | BIG incident management system | Harmonize Operations Platform | Incident Management (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | S | Very Complex | 36 | 3740349 | Medium | Medium | No | Mission Critical | AMC/OEO | Zhan Jie LONG | Cloud | Ludwigshafen | APM0004216 | Dependencies in earlier wave |  |  | No | 42.4 | 737.1 | 882.4333 | 50 | 7 | Operations SME 2 | 2027-01-17 | Disputed | Data retention requirement to be validated before decommissioning.
APM0003491 | BOSSA - BASF Occupational Safety in SAP | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | M | Very Complex | 71 | 89499723 | Low | Medium | No | Low | GBI/UP | Bernhard Jaecker | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 769.9 | 1043.2333 | 60 | 6 | Operations SME 3 | 2027-01-14 | Pending BASF Review
APM0013189 | BOSSA Access right request platform | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | S | Complex | 45 | 4687516 | Medium | High | No | High | GBI/UE-S | Remi Tirfoin | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 533 | 646.3333 | 49.3 | 6 | Operations SME 4 | 2026-10-18 | Pending BASF Review
APM0011268 | BOSSA Safety Instruction Scanner | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | XXL | Very Complex | 441 | 199853955161 | Very High | High | No | High | GBI/UP | Bernhard Jaecker | Cloud | Global |  | No dependencies | 2026-10-10 |  | No | 170.4 | 4220.8 | 4878.1333 | 23.8 | 8 | Operations SME 1 | 2026-12-26 | Approved | Data retention requirement to be validated before decommissioning.
APM0012847 | BPC Automated Locker | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Complex | 30 | 846764 | Low | Medium | No | Medium | CPK/OC | David Freddy Boyong David Freddy | On Premise | Antwerp | APM0011789; APM0010737 | Dependencies in same wave |  |  | No | 26.4 | 208.6 | 273.9333 | 55 | 4 | Operations SME 2 | 2026-11-27 | In Workshop
APM0011208 | BPC BowTieXP | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | L | Complex | 95 | 1121842378 | Medium | Medium | No | High | CPK/SH | Amiruddin Abu Bakar | On Premise | Tarragona | APM0004216 | Dependencies in earlier wave | 2026-10-10 |  | No | 106.4 | 1520.2 | 1825.5333 | 43.8 | 6 | Operations SME 3 | 2026-10-27 | In Workshop | Awaiting confirmation of site-local process variations.
APM0013081 | BSMJ 5in1 system | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | L | Medium | 89 | 1117562921 | Medium | Medium | No | Medium | A-EDA/PT | Jing Ji QI | Mobile App | Ludwigshafen |  | No dependencies | 2027-09-19 |  | No | 106.4 | 774.9 | 979.9 | 50 | 4 | Operations SME 4 | 2026-10-11 | Not Started
APM0013083 | BSMJ PPS system | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | L | Very Complex | 89 | 1474659756 | High | Medium | No | Mission Critical | A-EDA/PT | Jing Ji QI | On Premise | Nanjing | APM0013349 | Dependencies in same wave |  |  | No | 106.4 | 2063.7 | 2465.0333 | 30.8 | 8 | Operations SME 1 | 2026-10-17 | Approved | Turnaround window at site must be avoided during cutover.
APM0013082 | BSMJ e-PTW | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | S | Medium | 36 | 4756433 | Low | High | No | Medium | A-EDA/PT | Jing Ji QI | On Premise | Nanjing | APM0003491 | Dependencies in same wave | 2027-10-21 |  | No | 42.4 | 438.7 | 515.7 | 45 | 3 | Operations SME 2 | 2026-11-28 | Approved | Awaiting confirmation of site-local process variations.
APM0008944 | BSNJ SIMS system | Harmonize Operations Platform | Manage Site Landscape (Provides), Maintain Emergency Response Readiness (Provides) | Data Migration Only | No | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | XL | Very Complex | 183 | 12946073463 | Very High | Low | No | Medium | ACO/N/OS | Xu GAO | On Premise | Global | APM0011789 | Dependencies in same wave | 2027-08-25 |  | No | 138.4 | 1919.7 | 2449.0333 | 32 | 8 | Operations SME 3 | 2027-01-04 | In Workshop | Interface inventory to be confirmed with integration team.
APM0003840 | BYC PEOPLEBYAREA | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 72 | 105361042 | Medium | Low | No | Mission Critical | ACN CGA/I | Mingxing CHEN | On Premise | Freeport |  | No dependencies |  |  | No | 74.4 | 1264.5 | 1537.8333 | 56.5 | 6 | Operations SME 4 | 2026-12-27 | Approved
APM0008791 | BYC RAPID ROLL CALL | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | L | Complex | 126 | 1275400334 | High | Medium | No | High | ACN CGA/I | Mingxing CHEN | On Premise | Global |  | No dependencies |  |  | No | 106.4 | 962.6 | 1267.9333 | 43 | 6 | Operations SME 1 | 2026-12-25 | Approved
APM0003834 | BYC SAPBS | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | L | Complex | 108 | 741339779 | Medium | Medium | No | Mission Critical | ACN CGA/I | Cheng HUANG | On Premise | Geismar |  | No dependencies | 2027-08-30 |  | No | 106.4 | 1593 | 1898.3333 | 46.5 | 6 | Operations SME 2 | 2026-10-05 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0008261 | BYC SPIM 5IN1 | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | L | Very Complex | 143 | 1344495770 | High | Critical | No | High | ACN CGA/I | Cheng HUANG | Cloud | Ludwigshafen |  | No dependencies | 2027-06-22 |  | No | 106.4 | 1387.8 | 1789.1333 | 29 | 8 | Operations SME 3 | 2026-10-17 | Approved
APM0009450 | BYC ePermit | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | L | Simple | 82 | 924886732 | Medium | Medium | No | Medium | ACN CGA/I | Cheng HUANG | Cloud | Freeport |  | No dependencies |  |  | No | 18.4 | 626.7 | 733.1 | 50 | 3 | Operations SME 4 | 2026-12-06 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0010583 | CCTV | Harmonize Operations Platform | Manage Site Security (Provides), IT Audit and Risk Management (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | L | Medium | 91 | 984764402 | High | Medium | No | High | GBE/WU-Y | Christopher Skurray | Cloud | Nanjing | APM0003840 | Dependencies in same wave |  |  | No | 106.4 | 1099.5 | 1304.5 | 32.5 | 5 | Operations SME 1 | 2026-10-10 | Pending BASF Review
APM0012604 | CCTV for Singapore Jurong Island | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | S | Very Complex | 39 | 4175925 | Very High | High | No | High | EVM/AJ | Tamillselvam Letchmanan | On Premise | Antwerp | APM0013081 | Dependencies in earlier wave | 2026-10-23 |  | No | 42.4 | 444.7 | 590.0333 | 34.3 | 8 | Operations SME 2 | 2026-11-17 | In Workshop | Vendor licence expires mid-programme; align cutover accordingly.
APM0012125 | CSR (Customer Specific Requirement) | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | L | Very Complex | 91 | 1261951231 | Very High | High | No | High | E-PME/Q | Kathrin Holz | On Premise | Antwerp |  | No dependencies |  |  | No | 106.4 | 2009.1 | 2410.4333 | 30.8 | 8 | Operations SME 3 | 2026-12-29 | Not Started
APM0002937 | Canada DSL IU | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 72 | 52480408 | High | High | No | Medium | GBI/UN | Dean FitzGerald | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 74.4 | 1257.7 | 1531.0333 | 41.8 | 8 | Operations SME 4 | 2026-12-08 | Not Started | Data retention requirement to be validated before decommissioning.
APM0010351 | Certificate Tool | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 50 | 77496252 | Low | High | No | Mission Critical | COR/RQ | Thorsten Guenzel | On Premise | Freeport | APM0013081 | Dependencies in same wave |  |  | Yes | 74.4 | 1063.7 | 1273.0333 | 37.5 |  | Operations SME 1 | 2026-11-06 | Approved
APM0010717 | ChineseGovDataExchange | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | No | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | M | Medium | 55 | 75555452 | High | Low | No | High | G-EDM/OC | Ran Ran XU | Cloud | Antwerp | APM0012225 | Dependencies in same wave |  |  | No | 74.4 | 507.6 | 648.6 | 42.5 | 3 | Operations SME 2 | 2026-10-11 | Approved | Turnaround window at site must be avoided during cutover.
APM0012176 | Compliance Managementsystem Recht im Betrieb | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | M | Complex | 62 | 144935705 | Low | Low | No | High | EVM/ELS | Matthias Filthaus | On Premise | Tarragona |  | No dependencies |  |  | Yes | 74.4 | 553.5 | 762.8333 | 62.8 |  | Operations SME 3 | 2026-12-27 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0009452 | Crisam (Operational Risk Management) | Harmonize Operations Platform | Manage Periodic Closing Activities (Provides), Group Risk Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Medium | 70 | 100043237 | Medium | Low | No | High | CFP/PM | Matthias Hanselmann | Cloud | Global |  | No dependencies | 2027-11-21 |  | No | 74.4 | 495.3 | 636.3 | 58.3 | 3 | Operations SME 4 | 2026-10-26 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0003513 | DAMARIS | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | S | Medium | 42 | 6996967 | Low | Medium | Yes | Mission Critical | RG/PE | Jessica Bender | On Premise | Ludwigshafen | APM0012354; APM0012176 | Dependencies in same wave |  |  | No | 42.4 | 284.7 | 361.7 | 73.5 | 1 | Operations SME 1 | 2026-12-31 | Not Started | Historical data volume to be re-measured prior to sizing sign-off.
APM0013535 | Dakota Proactivity EHS Software | Harmonize Operations Platform | Manage Emissions (Provides) | Data Migration Only | Yes | No active users identified during discovery; retire and archive the XXL dataset. | Modernize | BASF Operations Platform | Data Migration Only | XXL | Complex | 369 | 86889242748 | High | High | No | High | GBW/UN | Peter Dulik | Third Party Hosted | Ludwigshafen |  | No dependencies | 2027-06-01 | 2027-07-09 | No | 170.4 | 2249.5 | 2746.8333 | 29 |  | Operations SME 2 | 2027-01-02 | In Workshop
APM0002096 | Dangerous Goods (GELOG) | Harmonize Operations Platform | Manage Hazardous Substances (Provides), Manage Dangerous Goods (Provides) | Functional Migration Only | No | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 70 | 115126647 | Medium | High | No | Mission Critical | GBI/UP | Daniela Nuehlen-Hoevel | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 1052.5 | 1261.8333 | 43.5 | 6 | Operations SME 3 | 2026-10-20 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0004220 | Datenbank Richtlinien und Regelwerke / Kompendium Arbeitsschutz | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | M | Medium | 50 | 125842099 | High | High | No | Medium | ESE/SE | Zaklina Seibert | Cloud | Sao Paulo | APM0010020; APM0004798; APM0012939 | Dependencies in same wave |  | 2028-08-08 | No | 74.4 | 665.8 | 806.8 | 31.3 | 6 | Operations SME 4 | 2026-12-08 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0013425 | Dekra-AdaptiveBBS | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | No | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 71 | 110297254 | Very High | Medium | No | High | GBW/US-M | Cecilia Loriente | Third Party Hosted | Global |  | No dependencies |  |  | No | 74.4 | 867.1 | 1076.4333 | 41.8 | 6 | Operations SME 1 | 2026-12-30 | Pending BASF Review
APM0012438 | Desigo cc | Harmonize Operations Platform | Incident Management (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 50 | 143789036 | Medium | Critical | No | Low | ESP/TIC | Jan Smet | On Premise | Global | APM0012847; APM0013081 | Dependencies in earlier wave |  |  | No | 74.4 | 1184.5 | 1457.8333 | 37 | 8 | Operations SME 2 | 2026-12-01 | Approved | Awaiting confirmation of site-local process variations.
APM0009113 | Digital Work Permit - South America | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Data Migration Only | Yes | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | BASF Operations Platform | Data Migration Only | S | Simple | 48 | 6230691 | High | Medium | No | Medium | GDD/CF | Lee Hardee | Hybrid | Global | APM0013374 | Dependencies in earlier wave |  |  | No | 18.4 | 194.2 | 236.6 | 48.3 |  | Operations SME 3 | 2026-11-16 | In Workshop
APM0012897 | DoorKeeper | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | No | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 20 | 1332517 | Medium | Low | Yes | Medium | GBE/PA-ASG | Cindy Mahlangu | Hybrid | Ludwigshafen |  | No dependencies |  |  | No | 26.4 | 144.1 | 189.1 | 92 | 1 | Operations SME 4 | 2027-01-01 | Approved
APM0004203 | ECM - Enterprise Controlling and Monitoring BPCN | Harmonize Operations Platform | IT Incident Management (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | XS | Complex | 29 | 1126185 | Medium | Medium | No | High | EMX/HL | Daniela Fechner | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 26.4 | 279.6 | 344.9333 | 59.3 | 4 | Operations SME 1 | 2027-01-14 | Approved
APM0012891 | EHS Peformance v.2.0 | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | S | Very Complex | 44 | 5068851 | Medium | High | No | Low | S-ED/SPS | Rodrigo Alejandro Farina Flores | Cloud | Global |  | No dependencies |  |  | No | 42.4 | 435 | 580.3333 | 52.5 | 7 | Operations SME 2 | 2026-10-28 | Approved | Awaiting confirmation of site-local process variations.
APM0001263 | EHS UML DOCUMENTATION | Harmonize Operations Platform | Manage Product Compliance Master Data (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 23 | 1013125 | Low | Medium | Yes | High | GDE/FE | Michael Grimmeisen | On Premise | Tarragona | APM0013082; APM0003834; APM0012125 | Dependencies in same wave |  |  | No | 26.4 | 161.3 | 206.3 | 78.3 | 1 | Operations SME 3 | 2026-10-30 | Disputed | Awaiting confirmation of site-local process variations.
APM0008566 | EM APMESS | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | BASF Operations Platform | Data Migration Only | L | Medium | 135 | 1194781576 | High | Medium | No | High | EMX/EG | Elke Polley | On Premise | Global |  | No dependencies | 2027-05-21 |  | No | 106.4 | 830.5 | 1035.5 | 43 |  | Operations SME 4 | 2026-10-05 | Pending BASF Review | Awaiting confirmation of site-local process variations.
APM0002141 | EMAS | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | BASF Operations Platform | Data Migration Only | M | Medium | 65 | 123458617 | Medium | Medium | No | Medium | ESE/ML | Markus Hammermann | On Premise | Ludwigshafen |  | No dependencies | 2026-10-16 |  | No | 74.4 | 419.6 | 560.6 | 54 |  | Operations SME 1 | 2026-12-24 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0001720 | EMPOWER3 BHX | Harmonize Operations Platform | Product, Production Process and System Innovation Management (Provides), Manage Operational Quality System aligned with EHS (Provides), Laboratory Data specific Systems (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 15 | 718945 | Low | Medium | Yes | Mission Critical | G-ENP/PI | Jacqueline Garcia | On Premise | Antwerp | APM0012354; APM0012225 | Dependencies in same wave |  |  | No | 26.4 | 146.9 | 191.9 | 76.5 | 1 | Operations SME 2 | 2026-11-21 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0003412 | EREIGNIS-DB (ESL) | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | No | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | L | Medium | 91 | 1294898116 | Very High | Medium | No | High | ESE/SE | Matthias Messmer | On Premise | Antwerp | APM0001318 | Dependencies in earlier wave | 2027-02-04 | 2028-04-11 | No | 106.4 | 823.7 | 1028.7 | 33.3 | 6 | Operations SME 3 | 2026-12-18 | Not Started | Data retention requirement to be validated before decommissioning.
APM0013166 | Eked Pro , Loto Pro | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | L | Complex | 83 | 667433541 | High | Medium | No | High | E-EDE/OT | Ibrahim Oz | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 1602.6 | 1907.9333 | 43 | 6 | Operations SME 4 | 2026-12-25 | Not Started | Awaiting confirmation of site-local process variations.
APM0003078 | EnmasLight | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | S | Very Complex | 44 | 6452673 | Very High | High | No | Mission Critical | ESE/EC | Gerhard Woelk | On Premise | Geismar |  | No dependencies | 2027-05-16 |  | No | 42.4 | 408.7 | 554.0333 | 37 | 8 | Operations SME 1 | 2026-12-09 | Pending BASF Review
APM0009496 | EtQ V2020 | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | M | Medium | 61 | 130450446 | High | Low | No | Medium | E-CMP/OA | Laurent Pardieu | Cloud | Geismar | APM0011789; APM0003840 | Dependencies in same wave | 2026-10-20 |  | No | 74.4 | 440.7 | 581.7 | 44.3 | 4 | Operations SME 2 | 2026-11-06 | Approved
APM0008578 | GC EHS Information Platform 5in1+e-RC | Harmonize Operations Platform | Incident Management (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | S | Complex | 34 | 6993620 | Medium | Low | No | Mission Critical | GDD/EF | Xiao Guang LU | Cloud | Sao Paulo |  | No dependencies |  |  | No | 42.4 | 567.6 | 680.9333 | 60.5 | 4 | Operations SME 3 | 2026-12-09 | Disputed | Turnaround window at site must be avoided during cutover.
APM0009901 | GC EHS Regulatory & Compliance Management System | Harmonize Operations Platform | Manage Water Protection (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | L | Medium | 101 | 974438251 | High | Medium | No | High | GBA/UX | Xin LI | On Premise | Sao Paulo | APM0012438 | Dependencies in same wave |  |  | No | 106.4 | 1232.1 | 1338.5 | 32.5 | 5 | Operations SME 4 | 2027-01-07 | Approved | Data retention requirement to be validated before decommissioning.
APM0008965 | GC ePTW EX | Harmonize Operations Platform | Process Safety (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | S | Medium | 42 | 6051366 | Low | Medium | Yes | High | GDD/EF | Xiao Guang LU | On Premise | Global |  | No dependencies |  |  | No | 42.4 | 261 | 338 | 85.8 | 1 | Operations SME 1 | 2026-11-22 | Approved
APM0010943 | GC_I5G_IMP | Harmonize Operations Platform | IT Incident Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 25 | 608638 | Low | Low | No | Mission Critical | GDD/CH | Wei ZHANG | On Premise | Ludwigshafen |  | No dependencies |  | 2028-07-29 | No | 26.4 | 140.8 | 185.8 | 68 | 2 | Operations SME 2 | 2026-12-28 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0004245 | GEDWeb | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | XS | Complex | 15 | 826772 | Medium | Medium | No | Mission Critical | GBE/UE | CARLA MARIA TROCCOLI | On Premise | Singapore |  | No dependencies |  |  | No | 26.4 | 302.3 | 367.6333 | 57.5 | 4 | Operations SME 3 | 2026-12-29 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0009531 | GID - Global Incident Database | Harmonize Operations Platform | Incident Management (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 71 | 95895643 | High | High | No | High | COR/OR | Michael Burkard | On Premise | Antwerp | APM0003412 | Dependencies in earlier wave |  |  | No | 74.4 | 1068.7 | 1278.0333 | 35.5 | 7 | Operations SME 4 | 2027-01-02 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0008450 | GID - Global Incident Database (BW) | Harmonize Operations Platform | Incident Management (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | S | Very Complex | 35 | 4660211 | High | High | No | High | COR/OR | Michael Burkard | On Premise | Schwarzheide | APM0013069; APM0011208 | Dependencies in earlier wave |  |  | No | 42.4 | 727.2 | 872.5333 | 39.5 | 8 | Operations SME 1 | 2027-01-05 | In Workshop
APM0002814 | GLOBAL ATS | Harmonize Operations Platform | Execute Operations/Safety MOC (Provides) | Data Migration Only | Yes | No active users identified during discovery; retire and archive the XL dataset. | Modernize | BASF Operations Platform | Data Migration Only | XL | Medium | 198 | 10528238946 | Very High | Low | No | Medium | G-EVP/QM | Alexander-Klaus Adleff | On Premise | Antwerp |  | No dependencies |  |  | No | 138.4 | 993.6 | 1262.6 | 42.5 |  | Operations SME 2 | 2027-01-08 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0001529 | GLOBAL_QUALITY_DATABASE_EM | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | L | Very Complex | 125 | 537774659 | High | High | No | Medium | GEC/OD | Peter Janach | On Premise | Nanjing | APM0004203; APM0012939 | Dependencies in same wave | 2026-10-10 |  | No | 106.4 | 1901.2 | 2302.5333 | 27.3 | 8 | Operations SME 3 | 2027-01-07 | Approved | Awaiting confirmation of site-local process variations.
APM0013192 | Global Safety culture toolbox | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | M | Simple | 64 | 85808698 | High | Low | No | High | GBI/UE-S | Remi Tirfoin | On Premise | Sao Paulo |  | No dependencies |  |  | No | 18.4 | 331.1 | 405.5 | 53 | 2 | Operations SME 4 | 2026-10-11 | Pending BASF Review
APM0013383 | HikCentral Professional | Harmonize Operations Platform | Execute Operations/Safety MOC (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | L | Complex | 106 | 874644703 | High | Critical | No | High | GDA/DH | Gert Pantke | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 1087.9 | 1393.2333 | 29 | 7 | Operations SME 1 | 2026-10-26 | Approved
APM0011316 | IAM (Institute of Advance Motoring) | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by BASF Operations Platform; retain as-is for this programme and reassess at the next portfolio review. | Modernize | BASF Operations Platform | Data Migration Only | L | Medium | 99 | 1124673353 | Medium | Medium | No | High | GBE/UU-G | Richard Newsome | Cloud | Ludwigshafen | APM0010583 | Dependencies in earlier wave |  |  | No | 106.4 | 715.8 | 920.8 | 43.8 |  | Operations SME 2 | 2026-10-10 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0011641 | IBOZ.sk - e-learning platform for initial and regular EHS trainings | Harmonize Operations Platform | Track employee training and match it to operational requirements (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 65 | 148310249 | Medium | Critical | No | Mission Critical | GBE/EC-F | Anna Filkova Harvanikova | Cloud | Global |  | No dependencies |  |  | No | 74.4 | 1090.2 | 1299.5333 | 36.5 | 7 | Operations SME 3 | 2026-11-16 | Approved | Awaiting confirmation of site-local process variations.
APM0011061 | ID-Digitalform-Public | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | XXL | Complex | 317 | 100265782718 | High | High | No | High | A-EDA/PT | Stephanus Subagio | Cloud | Freeport |  | No dependencies |  |  | No | 170.4 | 3297.5 | 3794.8333 | 29 | 7 | Operations SME 4 | 2027-01-09 | Approved
APM0009210 | IKT-OTOBO | Harmonize Operations Platform | IT Incident Management (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | XS | Medium | 19 | 702011 | Very High | Medium | Yes | Medium | ESO/SE | Kevin Worschech | On Premise | Global | APM0013069 | Dependencies in same wave |  |  | No | 26.4 | 210.4 | 255.4 | 65 | 2 | Operations SME 1 | 2026-11-16 | Approved
APM0011007 | IM_Work Tasks SA_5S | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | No | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 71 | 148837627 | Medium | Critical | No | Medium | GDD/CF | Suelen Cristian de Freitas Morais | Mobile App | Ludwigshafen |  | No dependencies |  |  | No | 74.4 | 1116.7 | 1390.0333 | 40 | 8 | Operations SME 2 | 2026-10-31 | Approved
APM0012785 | IN-ROAD E-PTW (Permit-To-Work) Singapore | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 56 | 73631012 | Medium | High | No | Medium | G-EDM/OQ | Jing Yin Leung | Third Party Hosted | Ludwigshafen | APM0012891 | Dependencies in earlier wave |  |  | No | 74.4 | 1386.6 | 1659.9333 | 42.5 | 8 | Operations SME 3 | 2026-11-22 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0013538 | INFRARED DETECTION DEVICE FOR SITE SECURITY | Harmonize Operations Platform | IT Incident Management (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 63 | 126032446 | High | Medium | No | Low | A-CMA/OSH | Sang-Sik Lee | Third Party Hosted | Singapore |  | No dependencies | 2027-10-08 |  | No | 74.4 | 951.1 | 1160.4333 | 50.3 | 6 | Operations SME 4 | 2026-11-10 | Approved | Interface inventory to be confirmed with integration team.
APM0002866 | INTRANET HSC | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | No | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 25 | 695715 | Medium | High | No | Mission Critical | ESE/SE | Frank Dierschke | On Premise | Geismar |  | No dependencies |  |  | No | 26.4 | 141.7 | 186.7 | 50.5 | 3 | Operations SME 1 | 2026-10-14 | Approved | Interface inventory to be confirmed with integration team.
APM0007757 | IT Service Management | Harmonize Operations Platform | IT Service Catalog Management (Provides), IT Request Management (Provides), IT Problem Management (Provides), IT Incident Management (Provides), IT Change Management (Provides), Continuous Improvement of IT Services (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | XXL | Medium | 444 | 74354357489 | High | High | No | High | GDA/L | Nina Bayerle | Cloud | Schwarzheide |  | No dependencies | 2027-04-16 |  | No | 170.4 | 2738.6 | 3071.6 | 29 | 6 | Operations SME 2 | 2026-10-09 | Not Started | Interface inventory to be confirmed with integration team.
APM0013067 | In-road e permit system | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 72 | 116567563 | Medium | Medium | No | Mission Critical | EMX/AC | Guo Yong YU | Mobile App | Freeport |  | No dependencies | 2026-11-17 |  | No | 74.4 | 1077.2 | 1286.5333 | 50.5 | 5 | Operations SME 3 | 2026-12-19 | Disputed | Data retention requirement to be validated before decommissioning.
APM0008949 | Integra | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | M | Medium | 63 | 66582360 | Very High | Medium | No | High | ES/TSO | JOSE MARIA LAPUENTE | On Premise | Freeport |  | No dependencies |  |  | No | 74.4 | 665.5 | 806.5 | 41.8 | 5 | Operations SME 4 | 2027-01-15 | Approved
APM0008394 | Integrum Management Systems | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | S | Medium | 42 | 5796035 | High | Low | Yes | High | GBA/UA | Syed Muhammad Murtaza Zaidi | On Premise | Geismar | APM0012548 | Dependencies in same wave |  |  | No | 42.4 | 284.1 | 361.1 | 71.5 | 1 | Operations SME 1 | 2027-01-17 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0009808 | JEDERMANN PLATFORM | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 16 | 759351 | High | Medium | Yes | High | ESE/SE | Zaklina Seibert | On Premise | Antwerp |  | No dependencies |  |  | No | 26.4 | 147.7 | 192.7 | 79 | 1 | Operations SME 2 | 2026-10-17 | Approved
APM0009436 | LCP EHS Tool | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | L | Simple | 149 | 1289207167 | High | Low | No | High | GEM/EM | Jan-Philip Buchholz | Cloud | Global | APM0002937 | Dependencies in same wave |  |  | No | 18.4 | 535.2 | 641.6 | 38.5 | 3 | Operations SME 3 | 2026-11-20 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0012136 | LIVE Audit | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 60 | 130627020 | Very High | Critical | No | High | PM/LO | Anja Biedermann | On Premise | Ludwigshafen | APM0009808 | Dependencies in earlier wave |  |  | No | 74.4 | 1362.3 | 1635.6333 | 23.3 | 8 | Operations SME 4 | 2026-12-28 | Approved | Turnaround window at site must be avoided during cutover.
APM0011607 | Localization deployment of hazardous waste standardized management projects | Harmonize Operations Platform | Manage Waste (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | XXS | Medium | 5 | 146959 | Medium | Medium | No | Medium | A-CMA/SE | Wei LU | Cloud | Geismar |  | No dependencies |  |  | No | 18.4 | 135.8 | 164.8 | 63 | 2 | Operations SME 1 | 2026-11-23 | Approved
APM0008848 | MOC DASHBOARD | Harmonize Operations Platform | Execute Operations/Safety MOC (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | L | Very Complex | 139 | 531745747 | Very High | Critical | No | Mission Critical | GEM/TI | Martin Liebig | Cloud | Nanjing |  | No dependencies |  |  | No | 106.4 | 1208.7 | 1610.0333 | 22 | 8 | Operations SME 2 | 2026-12-28 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0003228 | MPPD - Multiple-Path Particle Dosimetry | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 55 | 142900347 | High | High | No | Medium | GBI/UR | Steffen Bade | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 977.3 | 1186.6333 | 41.8 | 7 | Operations SME 3 | 2026-11-16 | Not Started | Interface inventory to be confirmed with integration team.
APM0013179 | MSDS management system for BCCS | Harmonize Operations Platform | Manage Safety Data Sheet (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | M | Medium | 72 | 124296781 | Medium | Critical | No | High | EMX/AC | Xiang Yang YE | Cloud | Antwerp | APM0008031 | Dependencies unresolved |  |  | No | 74.4 | 666.7 | 807.7 | 23.3 | 6 | Operations SME 4 | 2027-01-22 | Approved
APM0012620 | MSDS management system for Pudong sites | Harmonize Operations Platform | Manage Safety Data Sheet (Provides), Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Simple | 51 | 109005978 | High | Medium | No | High | ACO/R/E | Zhi Rui SHEN | Cloud | Global | APM0013192; APM0011268 | Dependencies in earlier wave |  |  | Yes | 18.4 | 365.8 | 440.2 | 42.5 |  | Operations SME 1 | 2026-11-02 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0012400 | Mango QHSE Software (part of EcoOnline Global) | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides), Incident Management (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | XS | Medium | 11 | 1098880 | Medium | Critical | No | Medium | GBE/UA | Fernando Pienaar | Cloud | Nanjing |  | No dependencies |  |  | No | 26.4 | 265 | 310 | 47 | 4 | Operations SME 2 | 2027-01-18 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0004428 | ManualMaster | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | L | Simple | 97 | 1356778796 | Medium | Critical | No | Mission Critical | E-EDE/QM | Niels Kuil | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 545.4 | 651.8 | 32.5 | 5 | Operations SME 3 | 2027-01-06 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0002676 | MyPortal Doc Management | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | L | Complex | 87 | 630900683 | High | Critical | No | Mission Critical | G-EVC/ON | Dorle Werfelmann | On Premise | Nanjing | APM0009808 | Dependencies in earlier wave |  |  | No | 106.4 | 1495 | 1800.3333 | 22.8 | 8 | Operations SME 4 | 2026-11-20 | In Workshop | Data retention requirement to be validated before decommissioning.
APM0010895 | NA EHS(AIMS) Reporting System | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | No | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | BASF Operations Platform | Data Migration Only | M | Very Complex | 54 | 87655579 | Low | Medium | No | High | GBW/UN-I | Lisa Harlow | On Premise | Geismar |  | No dependencies | 2027-06-21 |  | No | 74.4 | 799.5 | 1072.8333 | 56.8 |  | Operations SME 1 | 2026-12-24 | In Workshop
APM0008483 | NA SARA 313 | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | XXS | Medium | 8 | 80268 | Very High | High | No | High | GBI/UN | Dean FitzGerald | On Premise | Schwarzheide | APM0013538 | Dependencies in same wave |  | 2027-10-27 | No | 18.4 | 72.9 | 101.9 | 33.3 | 5 | Operations SME 2 | 2026-12-29 | Not Started | Shadow IT usage suspected; confirm true user base in workshop.
APM0008484 | NA Where Used Reporting | Harmonize Operations Platform | Manage Product Compliance Master Data (Provides), Execute Operations/Safety MOC (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | XXS | Complex | 9 | 97949 | Very High | Medium | No | High | GBI/UN | Dean FitzGerald | On Premise | Schwarzheide | APM0012604 | Dependencies in same wave |  |  | No | 18.4 | 116.1 | 157.4333 | 40.3 | 6 | Operations SME 3 | 2026-12-15 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0010155 | Operational Technology Service Management | Harmonize Operations Platform | Network Management (Provides), IT Incident Management (Provides), IT Change Management (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | XS | Very Complex | 30 | 624089 | Medium | Medium | No | Mission Critical | GDD/CD | Carmen Mendizabal | Cloud | Ludwigshafen |  | No dependencies | 2026-12-05 |  | No | 26.4 | 419.6 | 500.9333 | 57.5 | 6 | Operations SME 4 | 2026-11-06 | In Workshop | Historical data volume to be re-measured prior to sizing sign-off.
APM0010285 | PD Smart EHS Platform (5in1) | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 19 | 863559 | Medium | Low | No | Mission Critical | ACO/R/E | Zhi Rui SHEN | Cloud | Nanjing |  | No dependencies |  |  | No | 26.4 | 155.5 | 200.5 | 63.5 | 2 | Operations SME 1 | 2026-11-19 | Pending BASF Review
APM0004672 | Passage Grenzach - Unterweisungs-Software | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | M | Complex | 51 | 73710035 | High | Critical | No | Mission Critical | EMX/EG | Ralf Bogenschneider | On Premise | Ludwigshafen |  | No dependencies |  | 2028-03-17 | No | 74.4 | 576.8 | 786.1333 | 31.3 | 7 | Operations SME 2 | 2026-10-25 | Approved | Awaiting confirmation of site-local process variations.
APM0009881 | QM DB system for Yeosu | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | XL | Complex | 194 | 6432439501 | High | High | No | Medium | A-CMA/OMQ | SoYun Park | On Premise | Schwarzheide |  | No dependencies |  |  | No | 138.4 | 2543.9 | 2945.2333 | 34.8 | 7 | Operations SME 3 | 2027-01-13 | Approved
APM0009404 | QR code Mass download Tool | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Data Migration Only | No | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | XL | Medium | 167 | 6246212238 | High | Medium | No | Medium | GB/ST-A | Mei HUANG | Cloud | Antwerp | APM0011268; APM0003840 | Dependencies in same wave |  |  | No | 138.4 | 1002.1 | 1271.1 | 31.3 | 5 | Operations SME 4 | 2026-10-27 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0011634 | Quality Guard | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 61 | 120045553 | Medium | Critical | No | High | GBW/US-M | Fernanda Las Chiaramonte | Cloud | Global |  | No dependencies |  |  | No | 74.4 | 986.6 | 1195.9333 | 38.3 | 7 | Operations SME 1 | 2027-01-21 | Approved
APM0011524 | Quentic EHS Management | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | S | Complex | 34 | 5630251 | Medium | Critical | No | Medium | ED/BT I | Christoph Hesse | Cloud | Geismar |  | No dependencies |  |  | No | 42.4 | 539.2 | 652.5333 | 44 | 7 | Operations SME 2 | 2026-12-03 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0013190 | RAMP Training platform | Harmonize Operations Platform | Execute Operations/Safety MOC (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | XL | Complex | 195 | 13813877100 | High | Critical | No | Mission Critical | GBI/UE-S | Remi Tirfoin | Cloud | Antwerp | APM0008848 | Dependencies in same wave |  | 2028-04-17 | No | 138.4 | 1495.2 | 1896.5333 | 13.8 | 8 | Operations SME 3 | 2026-10-06 | Not Started
APM0003387 | REACTOR MoC | Harmonize Operations Platform | Manage Product Compliance Master Data (Provides), Execute Operations/Safety MOC (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 54 | 97965594 | Medium | Critical | No | Mission Critical | GBI/UN | Dean FitzGerald | On Premise | Tarragona |  | No dependencies |  |  | No | 74.4 | 1326.2 | 1599.5333 | 36.5 | 8 | Operations SME 4 | 2027-01-07 | Pending BASF Review | Vendor licence expires mid-programme; align cutover accordingly.
APM0002248 | REHSA EHS-REPORTING | Harmonize Operations Platform | Manage Emissions (Provides), Comply with Sustainability Reporting (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Very Complex | 74 | 102351641 | Very High | High | No | Mission Critical | COR/OR | Claudia Teusch | Cloud | Geismar |  | No dependencies | 2027-09-13 |  | No | 74.4 | 789.3 | 1062.6333 | 33 | 8 | Operations SME 1 | 2026-10-20 | Approved
APM0003585 | RSA ARCHER | Harmonize Operations Platform | Supplier Security (Provides), Secure Monitoring & Threat Hunting (Provides), Risk Management (Provides), IT Asset Discovery (Provides), Governance Management (Provides), Crisis Management, Business Continuity and Disaster Recovery (BC&DR) (Provides), Compute Provisioning and Operations Management (Provides), Compliance Management and Assessments (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | S | Medium | 50 | 5275367 | High | High | No | Mission Critical | GDS/A | Stephan Beck | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 263.6 | 340.6 | 42.3 | 4 | Operations SME 2 | 2026-11-19 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0003384 | Rapid Ranking | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | L | Medium | 120 | 508863732 | High | High | No | High | ESA/PP | Guy Willemsen | On Premise | Global | APM0013083; APM0011268 | Dependencies in same wave |  |  | No | 106.4 | 762.6 | 967.6 | 25.5 | 6 | Operations SME 3 | 2026-11-30 | Pending BASF Review
APM0010141 | Rever Score | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | S | Medium | 43 | 3023240 | Low | Low | Yes | Medium | EMX/PC | JOSE LUIS RIVERO | Cloud | Antwerp | APM0001720; APM0007757 | Dependencies in same wave |  |  | No | 42.4 | 428.3 | 505.3 | 83 | 2 | Operations SME 4 | 2027-01-09 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0010207 | Revver | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | BASF Operations Platform | Data Migration Only | M | Very Complex | 62 | 63141767 | Medium | Medium | No | High | GBA/FA-A | Daniel Higgins | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 74.4 | 800.2 | 1073.5333 | 52.3 |  | Operations SME 1 | 2026-12-05 | Approved | Data retention requirement to be validated before decommissioning.
APM0003363 | RiAnT | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Medium | 29 | 652495 | Very High | High | No | High | ESA/PP | Kyra Van Ael | On Premise | Antwerp |  | No dependencies |  |  | No | 26.4 | 155.7 | 200.7 | 41.8 | 5 | Operations SME 2 | 2026-10-28 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0008906 | SAFETY VIEW TOOL | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | S | Medium | 31 | 4095446 | High | Low | Yes | Low | ESE/SO | Frank Haerthe | On Premise | Freeport |  | No dependencies |  |  | No | 42.4 | 229.5 | 306.5 | 85.3 | 1 | Operations SME 3 | 2026-10-11 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0002242 | SAFETY_PERMIT_DATABASE | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Data Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | S | Very Complex | 43 | 3987874 | Low | High | No | Low | NAG | Cara Madzy | On Premise | Antwerp | APM0012897 | Dependencies in earlier wave |  |  | No | 42.4 | 394.7 | 540.0333 | 52.5 | 7 | Operations SME 4 | 2026-12-14 | In Workshop
APM0002031 | SAFEWORK_ORM | Harmonize Operations Platform | Execute Permit-to-Work (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | S | Complex | 41 | 5971728 | Medium | Medium | No | Medium | GDD/EF | Jeffrey Heffinger | On Premise | Ludwigshafen | APM0011316 | Dependencies unresolved |  |  | No | 42.4 | 506.5 | 619.8333 | 43 | 5 | Operations SME 1 | 2026-10-17 | Approved
APM0012413 | SAM von SECOVA | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | S | Complex | 36 | 5134230 | Very High | High | No | High | ESL/WD | Juergen Mattler | Cloud | Singapore |  | No dependencies |  |  | No | 42.4 | 352.7 | 466.0333 | 38.8 | 7 | Operations SME 2 | 2026-11-29 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0008664 | SAR Dashboard | Harmonize Operations Platform | Process Safety (Provides), Incident Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Very Complex | 55 | 109915366 | High | High | No | Low | GDD/EF | Olivia Centeno | Cloud | Schwarzheide |  | No dependencies |  |  | No | 74.4 | 870.5 | 1143.8333 | 43.3 | 8 | Operations SME 3 | 2027-01-09 | Pending BASF Review | Interface inventory to be confirmed with integration team.
APM0003944 | SDS PORTAL | Harmonize Operations Platform | Manage Safety Data Sheet (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | M | Medium | 55 | 50360054 | Medium | High | No | Low | GBI/UP-B | Ralf Hogenmueller | On Premise | Nanjing |  | No dependencies |  |  | No | 74.4 | 693.6 | 834.6 | 48.5 | 4 | Operations SME 4 | 2026-11-02 | Approved
APM0010690 | SD_CC_LACI | Harmonize Operations Platform | IT Incident Management (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | S | Complex | 38 | 6708991 | High | Medium | No | High | GDA/GI | Thomas Weber | Cloud | Freeport | APM0011316 | Dependencies unresolved |  |  | No | 42.4 | 516.2 | 629.5333 | 36 | 6 | Operations SME 1 | 2026-12-22 | Approved | Data retention requirement to be validated before decommissioning.
APM0010691 | SD_CC_SDI | Harmonize Operations Platform | IT Incident Management (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by BASF Operations Platform; retain as-is for this programme and reassess at the next portfolio review. | Modernize | BASF Operations Platform | Data Migration Only | M | Simple | 61 | 71927959 | Medium | High | No | Medium | GDA/GI | Thomas Weber | Cloud | Global |  | No dependencies | 2027-10-17 |  | No | 18.4 | 376.4 | 450.8 | 47 |  | Operations SME 2 | 2026-12-24 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0003454 | SINDA | Harmonize Operations Platform | Manage Hazardous Substances (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | L | Medium | 109 | 703918632 | High | Medium | No | High | ESE/PA | Rebekka Jaszcza | On Premise | Nanjing | APM0013166 | Dependencies in same wave |  |  | No | 106.4 | 1206.8 | 1411.8 | 32.5 | 5 | Operations SME 3 | 2026-12-26 | Approved | Awaiting confirmation of site-local process variations.
APM0003675 | SIPO | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | S | Medium | 42 | 5749467 | High | Medium | Yes | High | ESO/CS | Michael Seelinger | On Premise | Schwarzheide | APM0007392; APM0011316 | Dependencies in same wave | 2026-10-07 |  | No | 42.4 | 265.4 | 342.4 | 65.5 | 2 | Operations SME 4 | 2026-11-05 | In Workshop
APM0001810 | SMARTSOLVE TRANSFER TOOL | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | XS | Complex | 10 | 1292400 | High | High | No | High | ENT/QG | Antonia Deutsch | On Premise | Ludwigshafen | APM0003585; APM0012604 | Dependencies in same wave |  |  | No | 26.4 | 299.1 | 364.4333 | 36.5 | 6 | Operations SME 1 | 2026-10-07 | In Workshop | Historical data volume to be re-measured prior to sizing sign-off.
APM0002241 | STATURE | Harmonize Operations Platform | Process Safety (Provides), Manage Hazardous Substances (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | M | Simple | 63 | 64183502 | High | Low | No | High | COR/OP | Bertram Wendt | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 308.4 | 382.8 | 53 | 2 | Operations SME 2 | 2026-10-19 | Approved | Turnaround window at site must be avoided during cutover.
APM0007601 | SWIFT | Harmonize Operations Platform | Perform Isolation Management (Provides), Manage Risk Assessment/Processes (Provides), Manage HIRA (Provides), Incident Management (Provides), Execute Permit-to-Work (Provides), Execute Operations/Safety MOC (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | S | Complex | 33 | 4441974 | Medium | Medium | No | Low | GDD/EH | Joel Dave Lourdes | Cloud | Antwerp | APM0011316 | Dependencies unresolved |  |  | No | 42.4 | 341.9 | 455.2333 | 44.5 | 5 | Operations SME 3 | 2026-11-07 | In Workshop
APM0010151 | Safety Confirmation System Ocrenger | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | L | Very Complex | 93 | 820256003 | Medium | High | No | High | GBA/UJ | Koji Shiota | Cloud | Freeport |  | No dependencies | 2026-12-05 |  | No | 106.4 | 2003.9 | 2110.3 | 41.3 | 7 | Operations SME 4 | 2026-11-28 | Pending BASF Review
APM0010819 | Safety Monopoly Game | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | M | Complex | 54 | 130214092 | High | High | No | High | GBA/UC | Xiang Ping ZHOU | Cloud | Freeport |  | No dependencies |  |  | No | 74.4 | 623.4 | 832.7333 | 40 | 7 | Operations SME 1 | 2027-01-08 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0003775 | Safety Production Information Management Platform Of Greater China | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | No | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | S | Simple | 30 | 4449593 | Medium | High | No | Medium | GDD/EF | Xiao Guang LU | Hybrid | Global |  | No dependencies |  |  | No | 18.4 | 192.3 | 234.7 | 51 | 3 | Operations SME 2 | 2026-11-27 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0010584 | Safetyhub | Harmonize Operations Platform | Track employee training and match it to operational requirements (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | XS | Medium | 14 | 877460 | High | Medium | Yes | High | GBE/WU-Y | Christopher Skurray | Cloud | Sao Paulo |  | No dependencies |  | 2027-09-16 | No | 26.4 | 209.8 | 254.8 | 79 | 1 | Operations SME 3 | 2026-11-27 | Approved | Turnaround window at site must be avoided during cutover.
APM0010031 | SampleRetention | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides) | Data Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Data Migration Only | M | Medium | 66 | 119856392 | High | High | No | Medium | EVM/NM | Dawn Johnson | Cloud | Antwerp | APM0012354; APM0010351 | Dependencies in earlier wave |  |  | Yes | 74.4 | 500.4 | 641.4 | 37.3 |  | Operations SME 4 | 2027-01-19 | Approved | Data retention requirement to be validated before decommissioning.
APM0004341 | ServiceNow | Harmonize Operations Platform | IT Service Reporting (Provides), IT Service Catalog Management (Provides), IT Request Management (Provides), IT Problem Management (Provides), IT Incident Management (Provides), IT Change Management (Provides), IT Application Portfolio Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | L | Medium | 95 | 771827608 | High | High | No | Mission Critical | GDB/DI | Thomas Punzo | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 679.3 | 884.3 | 34.3 | 6 | Operations SME 1 | 2026-12-05 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0011904 | Smart management platform on safety risk | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides), Execute Permit-to-Work (Provides) | Data Migration Only | No | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | L | Medium | 122 | 1146647195 | Very High | Medium | No | Medium | A-EDA/PT | Jin Cai ZENG | Cloud | Ludwigshafen | APM0004244 | Dependencies in earlier wave |  |  | Yes | 106.4 | 701.9 | 906.9 | 35 |  | Operations SME 2 | 2026-11-04 | Approved | Awaiting confirmation of site-local process variations.
APM0008841 | SpillGuard Connect | Harmonize Operations Platform | Provide Plant Maintenance (Provides), Incident Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Complex | 51 | 54804890 | Very High | High | No | Mission Critical | E-PME/OW | Lutz Sorge | On Premise | Nanjing | APM0012136 | Dependencies in same wave | 2027-04-27 |  | No | 74.4 | 612.5 | 821.8333 | 22.5 | 7 | Operations SME 3 | 2027-01-12 | Approved | Awaiting confirmation of site-local process variations.
APM0008060 | Statistical Group Report | Harmonize Operations Platform | Incident Management (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | M | Very Complex | 51 | 79011938 | High | Medium | No | Mission Critical | COR/OR | Steven De Regter | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 1390.4 | 1663.7333 | 45.3 | 7 | Operations SME 4 | 2027-01-06 | Pending BASF Review | Interface inventory to be confirmed with integration team.
APM0011379 | SturzMelder | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Data Migration Only | M | Medium | 59 | 86031635 | Medium | High | No | Mission Critical | ESE/SO | Dominik Daniel Deutsch | Mobile App | Ludwigshafen |  | No dependencies | 2027-08-18 |  | No | 74.4 | 414.7 | 555.7 | 43.5 | 4 | Operations SME 1 | 2027-01-11 | Not Started
APM0003910 | TENFORCE_BASANT | Harmonize Operations Platform | Incident Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | M | Medium | 55 | 143405597 | Medium | Low | No | High | ESA/VIO | Yannick Brandt | Cloud | Singapore | APM0009496 | Dependencies in same wave |  |  | No | 74.4 | 511 | 652 | 47.8 | 3 | Operations SME 2 | 2026-11-20 | In Workshop | Interface inventory to be confirmed with integration team.
APM0010358 | Tools for Contractor - Upgrade HIVE | Harmonize Operations Platform | Occupational Health (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 71 | 62898423 | High | High | No | Mission Critical | GBW/US-P1 | FERNANDA APARECIDA CESARETTI | Cloud | Nanjing | APM0011789; APM0008031 | Dependencies in same wave |  | 2027-10-15 | No | 74.4 | 930 | 1139.3333 | 27.8 | 7 | Operations SME 3 | 2026-11-25 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0003455 | UBIS | Harmonize Operations Platform | Manage Hazardous Substances (Provides), Manage Emissions (Provides) | Functional Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Functional Migration | S | Complex | 32 | 4395751 | Low | Medium | No | Mission Critical | ESE/MU | Josef Schorr | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 490 | 603.3333 | 59 | 4 | Operations SME 4 | 2026-12-21 | Pending BASF Review
APM0011880 | VisionSecurity 4.5.1 | Harmonize Operations Platform | Manage Operational Quality System aligned with EHS (Provides), Manage BASF QM Process Documentation (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | XS | Medium | 27 | 655741 | Medium | Low | Yes | Medium | ENT/QC | Uwe Haeussel | On Premise | Global |  | No dependencies |  | 2027-07-23 | No | 26.4 | 263.4 | 308.4 | 92 | 1 | Operations SME 1 | 2026-11-08 | Approved
APM0011294 | Visitor management system for Kaohsiung Site | Harmonize Operations Platform | Provide Emergency Response Communications/Tools (Provides) | Data Migration Only | No | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Data Migration Only | XS | Simple | 22 | 581709 | Very High | Low | Yes | High | EMX/SA | Chih Feng Shih | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 102 | 128.4 | 79.8 | 1 | Operations SME 2 | 2026-12-05 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0011543 | Vodafone Self Service Portal (COVE) | Harmonize Operations Platform | IT Incident Management (Provides), Industrial Communication Infrastructure (Provides) | Functional Migration Only | Yes | Overlapping operations platform functionality across sites; harmonising onto BASF Operations Platform removes redundant support effort and standardises process. | Harmonize | BASF Operations Platform | Functional Migration | XL | Medium | 194 | 10703168689 | Very High | Medium | No | Mission Critical | GDD/CD | Anca-Veronica Iacob | Cloud | Freeport | APM0011007; APM0001502 | Dependencies in same wave | 2027-03-12 | 2028-08-19 | No | 138.4 | 1670.4 | 1939.4 | 22.5 | 6 | Operations SME 3 | 2026-12-01 | Not Started | Interface inventory to be confirmed with integration team.
APM0009181 | Wellcome | Harmonize Operations Platform | Manage Site Security (Provides), Execute Permit-to-Work (Provides) | Functional Migration Only | Yes | Application delivers a subset of BASF Operations Platform capability with no differentiating function; retire after migration to the standard platform. | Harmonize | BASF Operations Platform | Functional Migration | M | Complex | 68 | 59744605 | Medium | High | No | High | GBE/UT-E | Ali Onur Kasarci | Cloud | Geismar | APM0001502; APM0003228; APM0008848 | Dependencies in same wave |  |  | No | 74.4 | 1026 | 1235.3333 | 34.8 | 6 | Operations SME 4 | 2026-12-02 | Approved
APM0004526 | e Yellow card system | Harmonize Operations Platform | Manage Risk Assessment/Processes (Provides) | Functional Migration Only | Yes | Site-local operations platform duplicates capability already provided by BASF Operations Platform; consolidate to reduce licence, hosting and support cost. | Harmonize | BASF Operations Platform | Functional Migration | S | Complex | 46 | 6896280 | Medium | Medium | No | High | A-PMA/OS | Keng Hui WU | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 564.8 | 678.1333 | 56.3 | 5 | Operations SME 1 | 2027-01-22 | Approved
APM0013010 | trinamiX Zoho IT Helpdesk | Harmonize Operations Platform | IT Incident Management (Provides) | Data Migration Only | Yes | Fragmented operations platform landscape drives inconsistent data and duplicated interfaces; consolidation onto BASF Operations Platform is the agreed target state. | Harmonize | BASF Operations Platform | Data Migration Only | L | Simple | 77 | 1116260371 | Medium | High | No | High | TRINAMIX | Tim Rau | Cloud | Nanjing |  | No dependencies |  |  | No | 18.4 | 522.8 | 629.2 | 41.3 | 4 | Operations SME 2 | 2026-11-22 | Approved
APM0011947 | Aconex | Harmonize Project Collaboration & Handover Tools | Provide Turnaround Management (Provides) | Functional Migration Only | Yes | Site-local project collaboration & handover tools duplicates capability already provided by Project Collaboration Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Project Collaboration Standard | Functional Migration | L | Medium | 134 | 912934742 | Medium | Low | No | Medium | GEC/OD | DeShandra Irvin Lawrence | Cloud | Antwerp |  | No dependencies |  |  | No | 106.4 | 1307.9 | 1512.9 | 56 | 3 | Project SME 1 | 2026-11-27 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0010102 | AutoWBS Tool | Harmonize Project Collaboration & Handover Tools | Settle projects (Provides) | Functional Migration Only | Yes | Fragmented project collaboration & handover tools landscape drives inconsistent data and duplicated interfaces; consolidation onto Project Collaboration Standard is the agreed target state. | Harmonize | Project Collaboration Standard | Functional Migration | L | Medium | 76 | 526246817 | Medium | Medium | No | Medium | GBE/VL-B | Marcel Schario | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 1243.4 | 1448.4 | 50 | 4 | Project SME 2 | 2026-10-11 | In Workshop | Interface inventory to be confirmed with integration team.
APM0008950 | Autodesk Construction Cloud | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides), Provide Piping Engineering (Provides), Provide Construction (Provides), Provide Civil Engineering (Provides) | Data Migration Only | No | Site-local project collaboration & handover tools duplicates capability already provided by Project Collaboration Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Project Collaboration Standard | Data Migration Only | XXS | Medium | 10 | 67371 | Medium | Low | Yes | Medium | ESO/EO | Henning Fehrmann | Cloud | Tarragona |  | No dependencies |  |  | No | 18.4 | 82 | 111 | 94 | 1 | Project SME 3 | 2026-10-31 | Approved
APM0010433 | BASANT Field Change Index | Harmonize Project Collaboration & Handover Tools | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Overlapping project collaboration & handover tools functionality across sites; harmonising onto Project Collaboration Standard removes redundant support effort and standardises process. | Harmonize | Project Collaboration Standard | Data Migration Only | S | Medium | 48 | 3612194 | Low | High | No | Mission Critical | ESP/TM | Tamara van Geel | Cloud | Singapore |  | No dependencies |  |  | No | 42.4 | 265.9 | 342.9 | 52 | 3 | Project SME 4 | 2026-10-29 | Pending BASF Review
APM0005366 | BASANT PROMINEO | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Data Migration Only | No | Fragmented project collaboration & handover tools landscape drives inconsistent data and duplicated interfaces; consolidation onto Project Collaboration Standard is the agreed target state. | Harmonize | Project Collaboration Standard | Data Migration Only | M | Complex | 62 | 127039158 | High | High | No | High | ESP/TE13 | Christoph De Keulenaer | Cloud | Freeport | APM0011947 | Dependencies in earlier wave |  | 2028-11-17 | No | 74.4 | 662.6 | 871.9333 | 35.5 | 7 | Project SME 1 | 2026-10-31 | Approved
APM0007996 | BASANT PSO | Harmonize Project Collaboration & Handover Tools | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Site-local project collaboration & handover tools duplicates capability already provided by Project Collaboration Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Project Collaboration Standard | Functional Migration | M | Medium | 65 | 145921717 | High | Medium | No | Low | ESP/TEP | Jean-Pierre Bulinckx | On Premise | Sao Paulo | APM0010102 | Dependencies in earlier wave |  | 2028-06-15 | No | 74.4 | 821.4 | 962.4 | 45.8 | 5 | Project SME 2 | 2026-12-22 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0010113 | BASANT PT QM Cockpit | Harmonize Project Collaboration & Handover Tools | Support Cooperation between all E&M Units in the Technical Community (Provides) | Data Migration Only | Yes | Fragmented project collaboration & handover tools landscape drives inconsistent data and duplicated interfaces; consolidation onto Project Collaboration Standard is the agreed target state. | Harmonize | Project Collaboration Standard | Data Migration Only | XS | Complex | 13 | 692845 | High | Medium | No | Medium | ESP/TE5 | Erik Morel | On Premise | Ludwigshafen | APM0010102 | Dependencies in earlier wave | 2027-02-18 |  | No | 26.4 | 219.5 | 284.8333 | 51.3 | 5 | Project SME 3 | 2026-12-14 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0009733 | BASF digital handover Wechat mini-program | Harmonize Project Collaboration & Handover Tools | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Site-local project collaboration & handover tools duplicates capability already provided by Project Collaboration Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Project Collaboration Standard | Data Migration Only | M | Medium | 66 | 144634567 | High | High | No | Low | GDD/DE | Jun CHEN | Mobile App | Global | APM0005366; APM0008950 | Dependencies in same wave |  |  | No | 74.4 | 453.1 | 594.1 | 32.8 | 5 | Project SME 4 | 2026-11-08 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0002686 | BENTLEY PROJECTWISE CACHING SERVER-FREEPORT | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Functional Migration Only | Yes | Application delivers a subset of Project Collaboration Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Project Collaboration Standard | Functional Migration | S | Medium | 48 | 4411662 | High | High | No | Medium | GEC/OD | Adriana Pena | On Premise | Antwerp |  | No dependencies |  |  | No | 42.4 | 413.4 | 490.4 | 45.8 | 4 | Project SME 1 | 2026-10-19 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0002687 | BENTLEY PROJECTWISE CACHING SERVER-GEISMAR | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Functional Migration Only | Yes | Site-local project collaboration & handover tools duplicates capability already provided by Project Collaboration Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Project Collaboration Standard | Functional Migration | S | Medium | 36 | 5627818 | Low | Medium | Yes | Low | GEC/OD | Adriana Pena | On Premise | Nanjing |  | No dependencies |  |  | No | 42.4 | 420.4 | 497.4 | 89 | 1 | Project SME 2 | 2026-10-18 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0002688 | BENTLEY PROJECTWISE DESIGN INTEGRATION SERVER-RALEIGH | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Data Migration Only | No | Fragmented project collaboration & handover tools landscape drives inconsistent data and duplicated interfaces; consolidation onto Project Collaboration Standard is the agreed target state. | Harmonize | Project Collaboration Standard | Data Migration Only | S | Medium | 43 | 4271133 | Very High | Medium | Yes | High | GEC/OD | Adriana Pena | On Premise | Ludwigshafen | APM0010113 | Dependencies in earlier wave | 2027-11-06 |  | Yes | 42.4 | 286.5 | 363.5 | 66.3 |  | Project SME 3 | 2026-11-10 | Approved | Historical data volume to be re-measured prior to sizing sign-off.
APM0005099 | CoConsole | Harmonize Project Collaboration & Handover Tools | Provide Construction (Provides) | Data Migration Only | Yes | Fragmented project collaboration & handover tools landscape drives inconsistent data and duplicated interfaces; consolidation onto Project Collaboration Standard is the agreed target state. | Harmonize | Project Collaboration Standard | Data Migration Only | XXS | Medium | 9 | 53912 | Medium | High | No | Low | GEM/EM | Patrick Char | Cloud | Antwerp |  | No dependencies |  |  | No | 18.4 | 83.2 | 112.2 | 57.5 | 3 | Project SME 4 | 2027-01-02 | Disputed | Historical data volume to be re-measured prior to sizing sign-off.
APM0007038 | Cost Engineering Software Suite | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by Project Collaboration Standard; retain as-is for this programme and reassess at the next portfolio review. | Modernize | Project Collaboration Standard | Data Migration Only | M | Very Complex | 53 | 134307564 | High | Medium | No | Low | GEM/ES | Lukasz Hady | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 74.4 | 704.7 | 978.0333 | 50.3 |  | Project SME 1 | 2027-01-16 | Approved
APM0001338 | DECISION TOOLS SUITE | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Data Migration Only | Yes | Fragmented project collaboration & handover tools landscape drives inconsistent data and duplicated interfaces; consolidation onto Project Collaboration Standard is the agreed target state. | Harmonize | Project Collaboration Standard | Data Migration Only | L | Complex | 108 | 1383319346 | High | Medium | No | Low | GEM/ES | Werner Pehlke | On Premise | Sao Paulo |  | No dependencies |  |  | No | 106.4 | 916 | 1221.3333 | 46.3 | 6 | Project SME 2 | 2026-10-23 | In Workshop | Shadow IT usage suspected; confirm true user base in workshop.
APM0003230 | Multimediadatenbank | Harmonize Project Collaboration & Handover Tools | Provide Construction (Provides) | Functional Migration Only | Yes | Site-local project collaboration & handover tools duplicates capability already provided by Project Collaboration Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Project Collaboration Standard | Functional Migration | S | Medium | 46 | 5110355 | High | Medium | Yes | Mission Critical | E-CMP/NM | Uwe Eike Krueger | On Premise | Antwerp | APM0002686 | Dependencies in same wave |  |  | No | 42.4 | 429.6 | 506.6 | 63.8 | 2 | Project SME 3 | 2026-12-07 | Approved | Turnaround window at site must be avoided during cutover.
APM0009957 | NEO | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides), Provide Piping Engineering (Provides), Provide E&I Engineering (Provides), Provide Construction (Provides), Provide Civil Engineering (Provides) | Data Migration Only | Yes | Overlapping project collaboration & handover tools functionality across sites; harmonising onto Project Collaboration Standard removes redundant support effort and standardises process. | Harmonize | Project Collaboration Standard | Data Migration Only | S | Medium | 42 | 3751669 | High | Medium | No | Medium | GEM/ES | Patrick Tilly | Cloud | Antwerp |  | No dependencies |  |  | No | 42.4 | 239.2 | 316.2 | 52.8 | 3 | Project SME 4 | 2026-12-01 | Not Started | Awaiting confirmation of site-local process variations.
APM0010466 | NewPETs | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Functional Migration Only | No | Overlapping project collaboration & handover tools functionality across sites; harmonising onto Project Collaboration Standard removes redundant support effort and standardises process. | Harmonize | Project Collaboration Standard | Functional Migration | M | Simple | 58 | 92309398 | Medium | Low | No | Medium | GEA/E | Yan Jun ZHU | Cloud | Ludwigshafen | APM0003230 | Dependencies in earlier wave |  |  | Yes | 18.4 | 513.4 | 587.8 | 55.5 |  | Project SME 1 | 2026-10-15 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0010209 | P2Mi | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Data Migration Only | Yes | Overlapping project collaboration & handover tools functionality across sites; harmonising onto Project Collaboration Standard removes redundant support effort and standardises process. | Harmonize | Project Collaboration Standard | Data Migration Only | XS | Medium | 26 | 833739 | High | Medium | Yes | Low | GEA/E | Yan Jun ZHU | Cloud | Ludwigshafen | APM0009957 | Dependencies in same wave | 2027-02-05 |  | No | 26.4 | 138.5 | 183.5 | 71.8 | 1 | Project SME 2 | 2026-10-09 | Pending BASF Review
APM0010210 | PC2i | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Data Migration Only | Yes | Overlapping project collaboration & handover tools functionality across sites; harmonising onto Project Collaboration Standard removes redundant support effort and standardises process. | Harmonize | Project Collaboration Standard | Data Migration Only | XXS | Simple | 6 | 138260 | Medium | Low | No | Low | GEA/E | Yan Jun ZHU | Cloud | Nanjing | APM0002687 | Dependencies in earlier wave | 2027-01-03 |  | No | 18.4 | 62.9 | 81.3 | 66 | 2 | Project SME 3 | 2026-11-13 | In Workshop
APM0004532 | PIRS | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides), Provide Piping Engineering (Provides), Provide E&I Engineering (Provides), Provide Construction (Provides), Provide Civil Engineering (Provides) | Data Migration Only | Yes | Application delivers a subset of Project Collaboration Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Project Collaboration Standard | Data Migration Only | XS | Complex | 15 | 687344 | Low | High | No | Low | GEM/ES | Oliver Hoeffle | Cloud | Ludwigshafen | APM0011947 | Dependencies in earlier wave |  |  | No | 26.4 | 186 | 251.3333 | 55.5 | 5 | Project SME 4 | 2027-01-17 | Approved
APM0001085 | PROJECT WISE - BR | Harmonize Project Collaboration & Handover Tools | Support Cooperation between all E&M Units in the Technical Community (Provides) | Data Migration Only | Yes | Fragmented project collaboration & handover tools landscape drives inconsistent data and duplicated interfaces; consolidation onto Project Collaboration Standard is the agreed target state. | Harmonize | Project Collaboration Standard | Data Migration Only | M | Medium | 55 | 125499247 | High | Medium | No | High | GE/OSD1 | EDMILSON PATRICIO DOS SANTOS | On Premise | Geismar |  | No dependencies |  |  | No | 74.4 | 495.1 | 636.1 | 47 | 4 | Project SME 1 | 2026-11-16 | Not Started
APM0008826 | Project Wise RTP | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Functional Migration Only | No | Application delivers a subset of Project Collaboration Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Project Collaboration Standard | Functional Migration | XXS | Complex | 10 | 113980 | Low | Critical | No | Low | GEC/OD | Adriana Pena | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 155.8 | 197.1333 | 55 | 5 | Project SME 2 | 2026-11-22 | Pending BASF Review
APM0002917 | SAPRIMA | Harmonize Project Collaboration & Handover Tools | Establishment/Maintenance of Guidelines, Standards, Methods & Tools (Provides) | Data Migration Only | Yes | Fragmented project collaboration & handover tools landscape drives inconsistent data and duplicated interfaces; consolidation onto Project Collaboration Standard is the agreed target state. | Harmonize | Project Collaboration Standard | Data Migration Only | M | Medium | 64 | 148733166 | Medium | Medium | No | High | GEM/ES | Nicole Arndt | On Premise | Freeport |  | No dependencies |  |  | No | 74.4 | 481.2 | 622.2 | 52.3 | 3 | Project SME 3 | 2026-10-20 | Approved
APM0008702 | Staffing Plan System - Greater China | Harmonize Project Collaboration & Handover Tools | Provide Process Engineering (Provides) | Data Migration Only | Yes | Business-differentiating capability not covered by Project Collaboration Standard; retain as-is for this programme and reassess at the next portfolio review. | Modernize | Project Collaboration Standard | Data Migration Only | S | Complex | 41 | 4153634 | Medium | High | No | Medium | GEA/E | Lu Yan ZHANG | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 324.6 | 437.9333 | 51 |  | Project SME 4 | 2026-10-06 | Approved
APM0009539 | zvsp-dh-training | Harmonize Project Collaboration & Handover Tools | Knowledge Management (Provides) | Data Migration Only | Yes | Site-local project collaboration & handover tools duplicates capability already provided by Project Collaboration Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Project Collaboration Standard | Data Migration Only | XS | Medium | 11 | 988366 | Low | Low | No | High | GDD/DE | Jun CHEN | Cloud | Singapore |  | No dependencies |  |  | No | 26.4 | 156.1 | 201.1 | 69.8 | 2 | Project SME 1 | 2027-01-06 | Approved
APM0011073 | 3219-Schwingungsdiagnostik | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Data Migration Only | XS | Simple | 17 | 1311709 | Low | Low | Yes | Mission Critical | ESS/SRT | Torsten Schoenfeld | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 112.1 | 138.5 | 93 | 1 | ReliabilityC SME 1 | 2026-10-30 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0013426 | ABB Augmented Operator Testanwendung | Harmonize ReliabilityCenter | Monitoring of conditions (Provides) | Data Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Data Migration Only | S | Medium | 32 | 4189336 | High | High | No | Medium | GEM/TA | Nils Richter | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 247.7 | 324.7 | 45.8 | 4 | ReliabilityC SME 2 | 2026-12-03 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0003614 | AMS DATA | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Functional Migration | S | Very Complex | 30 | 6829967 | Medium | High | No | High | GEC/OD | DeShandra Irvin Lawrence | On Premise | Nanjing | APM0013426 | Dependencies in earlier wave | 2027-09-09 | 2028-12-11 | No | 42.4 | 692.5 | 837.8333 | 44.8 | 7 | ReliabilityC SME 3 | 2026-10-12 | Approved
APM0008404 | AMS HANNIBAL | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Data Migration Only | S | Simple | 45 | 5762371 | Medium | Low | No | Medium | GEC/OD | DeShandra Irvin Lawrence | On Premise | Nanjing |  | No dependencies | 2027-09-11 |  | No | 18.4 | 174.3 | 216.7 | 64 | 2 | ReliabilityC SME 4 | 2027-01-05 | Disputed
APM0012017 | AMS Machine Works | Harmonize ReliabilityCenter | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Functional Migration | M | Complex | 56 | 61470886 | Medium | Low | No | Low | GEC/OD | DeShandra Irvin Lawrence | On Premise | Nanjing |  | No dependencies | 2026-12-02 |  | No | 74.4 | 975.4 | 1184.7333 | 61.5 | 4 | ReliabilityC SME 1 | 2026-11-04 | In Workshop | Vendor licence expires mid-programme; align cutover accordingly.
APM0009230 | AMS Machine Works - Geismar | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Functional Migration Only | No | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Functional Migration | M | Complex | 71 | 111715851 | High | High | No | Medium | GEC/OG | Damien Parson | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 74.4 | 1018.6 | 1227.9333 | 41.8 | 7 | ReliabilityC SME 2 | 2026-12-07 | Approved | Turnaround window at site must be avoided during cutover.
APM0012186 | AMS Machine Works - Port Arthur | Harmonize ReliabilityCenter | Provide Rotating Equipment Technology (Provides) | Data Migration Only | No | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Data Migration Only | S | Complex | 33 | 4855854 | Medium | Medium | No | Medium | N-CPN/PS | Ryan Rusch | On Premise | Freeport | APM0009230; APM0012017 | Dependencies in same wave |  | 2028-10-11 | No | 42.4 | 323.7 | 437.0333 | 47.5 | 5 | ReliabilityC SME 3 | 2026-11-19 | Pending BASF Review
APM0001852 | AMS Machinery Health Manager | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Data Migration Only | S | Complex | 42 | 5052180 | Medium | High | No | High | GEC/OD | DeShandra Irvin Lawrence | On Premise | Global | APM0009230; APM0003614 | Dependencies in same wave |  |  | No | 42.4 | 380 | 493.3333 | 38.8 | 7 | ReliabilityC SME 4 | 2026-10-28 | Pending BASF Review | Turnaround window at site must be avoided during cutover.
APM0011213 | AMS Machinery Health Manager - Beaumont | Harmonize ReliabilityCenter | Provide Plant Maintenance (Provides) | Data Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Data Migration Only | XS | Medium | 28 | 848095 | Low | High | No | Low | GEC/OD | DeShandra Irvin Lawrence | On Premise | Ludwigshafen | APM0001852; APM0003614; APM0013426 | Dependencies in same wave |  |  | No | 26.4 | 162.7 | 207.7 | 49.5 | 4 | ReliabilityC SME 1 | 2026-11-23 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0002889 | AMS_MHM_GSM | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Functional Migration | L | Simple | 79 | 1346801852 | Very High | Medium | No | High | GEC/OD | DeShandra Irvin Lawrence | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 831.4 | 937.8 | 37.8 | 4 | ReliabilityC SME 2 | 2026-11-30 | Pending BASF Review
APM0012259 | Acoem Shaft Alignment | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Functional Migration Only | No | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Functional Migration | XS | Simple | 26 | 1308672 | Low | Medium | No | High | ESP/UI | Gert Coppens | Mobile App | Global |  | No dependencies |  | 2028-01-05 | No | 18.4 | 183.7 | 210.1 | 63.8 | 2 | ReliabilityC SME 3 | 2027-01-06 | Pending BASF Review | Historical data volume to be re-measured prior to sizing sign-off.
APM0010121 | BACH Predictive Maintenance Platform | Harmonize ReliabilityCenter | Maintenance Operations Management (ISA 95) (Provides) | Functional Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Functional Migration | XS | Simple | 25 | 1000850 | Medium | Medium | No | High | ACO/S/PM/E | Wei XU | Cloud | Global |  | No dependencies |  | 2028-11-21 | No | 18.4 | 164.6 | 191 | 59.3 | 2 | ReliabilityC SME 4 | 2026-11-16 | Approved
APM0004170 | BASANT ETS TRIL ANTWERP | Harmonize ReliabilityCenter | Provide Rotating Equipment Technology (Provides) | Functional Migration Only | No | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Functional Migration | L | Medium | 120 | 567952818 | Very High | Medium | No | Low | ESP/TWO | Wouter Pintjens | On Premise | Global |  | No dependencies | 2027-09-23 |  | No | 106.4 | 1233.6 | 1438.6 | 41 | 5 | ReliabilityC SME 1 | 2026-11-07 | Pending BASF Review
APM0008864 | BASANT SKF TRIL | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Data Migration Only | S | Medium | 40 | 6552112 | High | Medium | No | High | ESP/TWO | Wouter Pintjens | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 277.1 | 354.1 | 51 | 3 | ReliabilityC SME 2 | 2026-11-18 | Disputed
APM0012269 | BASF SFJ ATLAS Smartlink application | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides), Monitoring of conditions (Provides), Manage and control production assets and their status (Provides) | Data Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Data Migration Only | S | Medium | 32 | 6550074 | Medium | Low | Yes | High | G-ENP/PO | Morten Gulbrandsen | Cloud | Geismar |  | No dependencies |  |  | No | 42.4 | 283 | 360 | 87.3 | 1 | ReliabilityC SME 3 | 2027-01-13 | In Workshop
APM0010731 | BMC Predictive Maintenance Platform | Harmonize ReliabilityCenter | Maintenance Operations Management (ISA 95) (Provides) | Functional Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Functional Migration | M | Complex | 67 | 98217333 | Medium | High | No | Low | A-CPA/OM | Ye LIU | Cloud | Ludwigshafen | APM0012269 | Dependencies in earlier wave |  | 2028-02-22 | No | 74.4 | 883.3 | 1092.6333 | 44 | 6 | ReliabilityC SME 4 | 2026-11-26 | In Workshop | Interface inventory to be confirmed with integration team.
APM0006519 | BPC AMS Machinery Manager | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Data Migration Only | XXL | Simple | 314 | 61491751361 | Very High | Low | No | Low | CPK/SR | Wan Mohamad Amirul Abdul Manaf | On Premise | Antwerp | APM0010731 | Dependencies in same wave | 2027-07-06 |  | No | 18.4 | 1259.1 | 1429.5 | 29.5 | 4 | ReliabilityC SME 1 | 2027-01-22 | Approved
APM0009900 | BPC EasyRCA | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Functional Migration | L | Complex | 112 | 1368970942 | Medium | High | No | Medium | CPK/SR | Hazri Dahalan Md Razip | Cloud | Geismar |  | No dependencies |  | 2027-11-17 | No | 106.4 | 1745 | 2050.3333 | 43 | 7 | ReliabilityC SME 2 | 2026-11-13 | In Workshop
APM0012166 | BPC Schaeffler Optime Viewer | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Functional Migration Only | No | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Functional Migration | XS | Complex | 14 | 535867 | Low | Critical | No | High | CPK/SR | Muhammad Iqbal Shafiq Mohd Shaufi | On Premise | Sao Paulo | APM0002889 | Dependencies in earlier wave |  |  | No | 26.4 | 316.4 | 381.7333 | 45.3 | 6 | ReliabilityC SME 3 | 2026-11-23 | Approved
APM0013150 | BPC-Inductosense | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Data Migration Only | XS | Simple | 23 | 1032491 | Very High | High | No | High | CPK/ST | King Vee Chew | Cloud | Singapore | APM0011213; APM0012186 | Dependencies in same wave |  |  | No | 18.4 | 108.1 | 134.5 | 31.3 | 5 | ReliabilityC SME 4 | 2027-01-07 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0011289 | BYC LDPE Predictive Maintenance Platform | Harmonize ReliabilityCenter | BI, Reporting & Analytics (Provides) | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | Reliability Center Standard | Data Migration Only | S | Very Complex | 39 | 6434056 | Medium | High | No | Medium | ACN CGA/I | Cheng HUANG | On Premise | Nanjing | APM0001852 | Dependencies in earlier wave |  |  | Yes | 42.4 | 393.5 | 435.9 | 46.5 |  | ReliabilityC SME 1 | 2026-12-13 | Approved
APM0012876 | DynaPredict | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Functional Migration | XXS | Medium | 7 | 115922 | Medium | Low | Yes | High | S-CP/SPM3 | Ricardo dos Santos de Souza | Mobile App | Antwerp | APM0012269 | Dependencies in same wave |  |  | No | 18.4 | 131.4 | 160.4 | 81.8 | 1 | ReliabilityC SME 2 | 2026-12-18 | Not Started
APM0009272 | EPC vibration BASF | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides) | Functional Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Functional Migration | L | Medium | 83 | 940439516 | Medium | Medium | No | Medium | A-PMA/OM | Fei Fei PENG | Cloud | Ludwigshafen |  | No dependencies |  |  | No | 106.4 | 1117.9 | 1322.9 | 50 | 4 | ReliabilityC SME 3 | 2026-11-30 | Pending BASF Review | Data retention requirement to be validated before decommissioning.
APM0011331 | ES-TA_BN_PDH | Harmonize ReliabilityCenter | Provide Automation Technology (Provides) | Functional Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Functional Migration | S | Medium | 38 | 6901129 | Low | Medium | Yes | High | E-CPB/OP | LUIS GABINO SANCHEZ | On Premise | Ludwigshafen |  | No dependencies | 2027-01-13 |  | No | 42.4 | 397.7 | 474.7 | 85.8 | 1 | ReliabilityC SME 4 | 2026-11-27 | Approved
APM0004440 | Emerson Optics | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides), Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Functional Migration | L | Simple | 121 | 834985785 | High | High | No | Medium | E-EDE/OT | Turgay Cok | On Premise | Ludwigshafen | APM0012166; APM0011073; APM0008404 | Dependencies in same wave |  |  | No | 18.4 | 897.8 | 1004.2 | 27.3 | 5 | ReliabilityC SME 1 | 2026-11-18 | Not Started | Interface inventory to be confirmed with integration team.
APM0009451 | Fleet Management System | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides), IT Audit and Risk Management (Provides) | Functional Migration Only | No | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Functional Migration | M | Simple | 73 | 65007468 | Very High | Critical | No | Mission Critical | A-CIA/OP | Zhong Min LIU | Cloud | Freeport |  | No dependencies |  |  | No | 18.4 | 494.5 | 568.9 | 26 | 6 | ReliabilityC SME 2 | 2027-01-15 | Approved
APM0010526 | IFM Modules (BASF Antwerp) | Harmonize ReliabilityCenter | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Data Migration Only | M | Medium | 60 | 76918272 | High | Low | No | Medium | ESP/TWO | Nico Van den Broeck | On Premise | Geismar |  | No dependencies | 2027-02-01 |  | No | 74.4 | 509.4 | 650.4 | 54.8 | 3 | ReliabilityC SME 3 | 2026-10-15 | Approved | Data retention requirement to be validated before decommissioning.
APM0001278 | MACHINERY HEALTH MANAGER | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Functional Migration | L | Complex | 104 | 948968021 | High | Medium | No | High | N-CPN/PS | Joshua Bourque | On Premise | Singapore |  | No dependencies | 2027-02-11 |  | No | 106.4 | 1551.5 | 1856.8333 | 43 | 6 | ReliabilityC SME 4 | 2026-11-26 | Approved | Awaiting confirmation of site-local process variations.
APM0012894 | Mobile Operator 2020 | Harmonize ReliabilityCenter | Manage Risk Assessment/Processes (Provides) | Data Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Data Migration Only | S | Complex | 36 | 6599489 | Medium | Medium | No | Low | EMX/QW | Tracy Calder | Third Party Hosted | Global |  | No dependencies | 2027-05-09 | 2027-12-17 | No | 42.4 | 382.2 | 495.5333 | 59.5 | 5 | ReliabilityC SME 1 | 2027-01-23 | Pending BASF Review | Awaiting confirmation of site-local process variations.
APM0013497 | Monaca PA Vibration Monitoring | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Data Migration Only | L | Medium | 126 | 1196928698 | Medium | High | No | Medium | N-EDN/OM | Robert Hull | Third Party Hosted | Tarragona | APM0003614; APM0011331 | Dependencies in same wave |  |  | No | 106.4 | 799.7 | 1004.7 | 32.5 | 6 | ReliabilityC SME 2 | 2027-01-09 | Pending BASF Review
APM0004620 | NEST | Harmonize ReliabilityCenter | Provide Plant Maintenance (Provides) | Data Migration Only | No | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | Reliability Center Standard | Data Migration Only | M | Complex | 68 | 141634184 | Medium | Critical | No | Low | E-CMP/OA | Julien Kielwasser | On Premise | Geismar |  | No dependencies |  |  | No | 74.4 | 624.9 | 834.2333 | 41.5 |  | ReliabilityC SME 3 | 2026-10-17 | Approved | Interface inventory to be confirmed with integration team.
APM0009773 | PAT Server | Harmonize ReliabilityCenter | ProvideTechnical Inspection (Provides) | Data Migration Only | Yes | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Data Migration Only | S | Medium | 46 | 5319312 | Low | Medium | Yes | Medium | EMX/HS | Dirk Born | On Premise | Sao Paulo |  | No dependencies |  |  | No | 42.4 | 261.1 | 338.1 | 87.5 | 1 | ReliabilityC SME 4 | 2026-10-17 | Approved
APM0002247 | PSAIM (PROCESS SAFETY ASSET INTEGRITY MANAGEMENT) | Harmonize ReliabilityCenter | Provide Maintenance Management (Provides) | Functional Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Functional Migration | XS | Medium | 24 | 723633 | Low | Medium | Yes | Medium | GEC/OD | Adriana Pena | On Premise | Antwerp | APM0012259 | Dependencies in same wave |  |  | No | 26.4 | 254.6 | 299.6 | 80 | 1 | ReliabilityC SME 1 | 2027-01-19 | In Workshop | Data retention requirement to be validated before decommissioning.
APM0004870 | Predictive Maintenance Black Box | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Data Migration Only | Yes | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Data Migration Only | XS | Very Complex | 24 | 1020893 | High | High | No | Low | GDD/EA | Norman Volkert | Cloud | Nanjing |  | No dependencies |  |  | No | 26.4 | 267.1 | 348.4333 | 50.3 | 7 | ReliabilityC SME 2 | 2026-11-19 | In Workshop | Data retention requirement to be validated before decommissioning.
APM0001020 | REALITY_CHARTING | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Functional Migration | M | Medium | 66 | 83533716 | High | Low | No | High | GEC/OD | DeShandra Irvin Lawrence | On Premise | Global | APM0004870 | Dependencies in same wave |  |  | No | 74.4 | 652.6 | 793.6 | 42.5 | 3 | ReliabilityC SME 3 | 2026-10-06 | Approved | Interface inventory to be confirmed with integration team.
APM0008570 | ReliabilityCenter Acoem | Harmonize ReliabilityCenter | Provide Rotating Equipment Technology (Provides) | Functional Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Functional Migration | L | Medium | 100 | 765286046 | Medium | Low | No | High | GEM/TI | Michel Vorsprach | On Premise | Global |  | No dependencies |  | 2027-09-06 | No | 106.4 | 1206.9 | 1411.9 | 54.3 | 3 | ReliabilityC SME 4 | 2027-01-03 | Approved
APM0003213 | ReliabilityCenter AvevaPA | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Data Migration Only | No | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Data Migration Only | M | Medium | 70 | 108389895 | Medium | Low | No | High | GEM/TI | Marco Klaus Jaeger | On Premise | Antwerp | APM0009451 | Dependencies in same wave |  |  | No | 74.4 | 510 | 651 | 47.8 | 3 | ReliabilityC SME 1 | 2027-01-10 | Approved
APM0001165 | ReliabilityCenter BK Compass | Harmonize ReliabilityCenter | Provide Machining Technology (Provides) | Data Migration Only | Yes | Contractual obligation prevents change within the programme window; retain and revisit post-programme. | Modernize | Reliability Center Standard | Data Migration Only | S | Complex | 33 | 3704777 | Medium | Medium | No | High | GEM/TI | Marie Elisabeth Urbach | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 42.4 | 357.4 | 470.7333 | 56.3 |  | ReliabilityC SME 2 | 2026-11-08 | Pending BASF Review | Interface inventory to be confirmed with integration team.
APM0008575 | ReliabilityCenter Bently Nevada System1 | Harmonize ReliabilityCenter | Provide Rotating Equipment Technology (Provides) | Functional Migration Only | Yes | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Functional Migration | XXS | Complex | 7 | 117498 | Low | Medium | No | Medium | GEM/TI | Michel Vorsprach | On Premise | Nanjing | APM0003614 | Dependencies in same wave |  |  | No | 18.4 | 160.6 | 201.9333 | 57 | 4 | ReliabilityC SME 3 | 2026-12-22 | Pending BASF Review | Shadow IT usage suspected; confirm true user base in workshop.
APM0011713 | ReliabilityCenter Containerized Models | Harmonize ReliabilityCenter | Provide Automation Technology (Provides) | Functional Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Functional Migration | S | Simple | 42 | 3361010 | High | Medium | Yes | High | GEM/TI | Marco Klaus Jaeger | On Premise | Geismar | APM0001020 | Dependencies in same wave |  |  | No | 18.4 | 294.8 | 337.2 | 65.5 | 1 | ReliabilityC SME 4 | 2026-12-14 | In Workshop
APM0009402 | ReliabilityCenter Emerson PlantWeb | Harmonize ReliabilityCenter | Provide Maintenance Management (Provides) | Data Migration Only | No | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Data Migration Only | XXS | Simple | 5 | 100149 | Medium | Low | No | Medium | GEM/TI | Michel Vorsprach | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 64.6 | 83 | 69 | 2 | ReliabilityC SME 1 | 2027-01-23 | Approved
APM0012154 | ReliabilityCenter Emerson PlantWeb Insight (PWI) | Harmonize ReliabilityCenter | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Functional Migration | S | Complex | 43 | 3080616 | Medium | Low | No | High | GEM/TI | Michel Vorsprach | On Premise | Geismar |  | No dependencies |  |  | No | 42.4 | 579.2 | 692.5333 | 62.3 | 4 | ReliabilityC SME 2 | 2026-12-02 | Approved
APM0002077 | ReliabilityCenter IFM | Harmonize ReliabilityCenter | Provide Rotating Equipment Technology (Provides) | Functional Migration Only | Yes | Overlapping reliabilitycenter functionality across sites; harmonising onto Reliability Center Standard removes redundant support effort and standardises process. | Harmonize | Reliability Center Standard | Functional Migration | XL | Medium | 174 | 7912386538 | Very High | Medium | No | Medium | GEM/TI | Michel Vorsprach | On Premise | Freeport | APM0009773 | Dependencies in earlier wave |  |  | No | 138.4 | 1750.9 | 2019.9 | 32 | 6 | ReliabilityC SME 3 | 2026-10-08 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0011175 | ReliabilityCenter Ronds SuperCare Test | Harmonize ReliabilityCenter | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Functional Migration | S | Medium | 33 | 5571274 | Low | Low | No | Mission Critical | GEM/TI | Michel Vorsprach | On Premise | Nanjing | APM0011713 | Dependencies in earlier wave |  |  | No | 42.4 | 367 | 444 | 60.5 | 2 | ReliabilityC SME 4 | 2026-11-26 | Approved | Shadow IT usage suspected; confirm true user base in workshop.
APM0011438 | ReliabilityCenter SKF @ptitude Observer | Harmonize ReliabilityCenter | Provide Rotating Equipment Technology (Provides) | Functional Migration Only | No | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Functional Migration | M | Simple | 69 | 90653428 | High | Medium | No | High | GEM/TI | Alexander Walzenbach | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 590.8 | 665.2 | 47 | 3 | ReliabilityC SME 1 | 2026-10-15 | Not Started | Awaiting confirmation of site-local process variations.
APM0010609 | Reliasoft | Harmonize ReliabilityCenter | Provide Technical Documentation + Standards (Provides) | Data Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Data Migration Only | M | Medium | 74 | 51362452 | Low | High | No | Medium | GE/OST | LUIZ FERNANDO OLIVEIRA RAMOS | On Premise | Global |  | No dependencies |  | 2028-08-31 | No | 74.4 | 447.9 | 588.9 | 51.5 | 4 | ReliabilityC SME 2 | 2026-11-29 | Disputed | Vendor licence expires mid-programme; align cutover accordingly.
APM0013487 | Reliasoft GC Access | Harmonize ReliabilityCenter | Provide Maintenance Management (Provides) | Data Migration Only | No | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Data Migration Only | S | Medium | 41 | 5255241 | Very High | High | No | High | ACO/OO | Qing TU | On Premise | Geismar |  | No dependencies |  |  | No | 42.4 | 271.7 | 348.7 | 38.8 | 5 | ReliabilityC SME 3 | 2026-10-22 | Approved
APM0012609 | SKF quickcollect | Harmonize ReliabilityCenter | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Functionality superseded and user base migrated to an existing platform; decommission with data archived per retention policy. | Modernize | Reliability Center Standard | Data Migration Only | XXS | Medium | 6 | 97049 | Low | Medium | No | Low | EVM/AJ | Chek Kuan Ang | Mobile App | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 72.6 | 101.6 | 69 |  | ReliabilityC SME 4 | 2026-11-02 | Approved
APM0011229 | ZVS ReliabilityCenter Bently Nevada OrbitStudio | Harmonize ReliabilityCenter | Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Application delivers a subset of Reliability Center Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Reliability Center Standard | Functional Migration | L | Medium | 129 | 1084468385 | High | Low | No | Medium | GEA/TM | Hai Yan DU | On Premise | Tarragona | APM0013487 | Dependencies in same wave |  | 2028-12-15 | No | 106.4 | 1234.9 | 1439.9 | 40.3 | 4 | ReliabilityC SME 1 | 2026-11-16 | Pending BASF Review
APM0011200 | ZVS ReliabilityCenter Bently Nevada System1 | Harmonize ReliabilityCenter | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Data Migration Only | XL | Complex | 189 | 11684969135 | Medium | Critical | No | High | GEA/TM | Hai Yan DU | On Premise | Sao Paulo | APM0011073 | Dependencies in earlier wave | 2027-06-19 |  | No | 138.4 | 1449.6 | 1850.9333 | 26.8 | 8 | ReliabilityC SME 2 | 2026-11-12 | Pending BASF Review
APM0012720 | ZVS ReliabilityCenter Bently System1 Collector | Harmonize ReliabilityCenter | Provide Other Technical Services (Provides) | Functional Migration Only | Yes | Fragmented reliabilitycenter landscape drives inconsistent data and duplicated interfaces; consolidation onto Reliability Center Standard is the agreed target state. | Harmonize | Reliability Center Standard | Functional Migration | XS | Medium | 22 | 1206244 | Medium | Low | Yes | Medium | GEA/TM | Yang LAN | Mobile App | Ludwigshafen |  | No dependencies | 2027-05-12 |  | No | 26.4 | 237 | 282 | 92 | 1 | ReliabilityC SME 3 | 2026-12-31 | Approved | Data retention requirement to be validated before decommissioning.
APM0011242 | ZVS ReliabilityCenter Ronds SuperCare | Harmonize ReliabilityCenter | Provide Maintenance Management (Provides) | Data Migration Only | Yes | Site-local reliabilitycenter duplicates capability already provided by Reliability Center Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Reliability Center Standard | Data Migration Only | M | Simple | 64 | 127074478 | Very High | Medium | No | High | GEA/TM | Hai Yan DU | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 18.4 | 328.7 | 403.1 | 41.8 | 3 | ReliabilityC SME 4 | 2026-12-19 | Approved | Awaiting confirmation of site-local process variations.
APM0011160 | INTERFLEX 6040 SWITZERLAND | Harmonize Time Management Systems | Support Clock-in/Clock-out Systems (Provides) | Data Migration Only | No | Fragmented time management systems landscape drives inconsistent data and duplicated interfaces; consolidation onto SAP Time Management is the agreed target state. | Harmonize | SAP Time Management | Data Migration Only | L | Very Complex | 139 | 1421563953 | Low | High | No | Medium | GBE/PS-R | Benjamin Kipka | Hybrid | Schwarzheide |  | No dependencies |  |  | No | 106.4 | 1387.9 | 1789.2333 | 47.5 | 7 | Time SME 1 | 2026-12-04 | Disputed | Shadow IT usage suspected; confirm true user base in workshop.
APM0012552 | INTERFLEX Austria | Harmonize Time Management Systems | Support Clock-in/Clock-out Systems (Provides) | Data Migration Only | Yes | Application delivers a subset of SAP Time Management capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP Time Management | Data Migration Only | S | Medium | 50 | 6002345 | Low | High | No | Low | GBE/PS-E | Anna Gstoettner | On Premise | Singapore |  | No dependencies |  |  | No | 42.4 | 229.2 | 306.2 | 57 | 3 | Time SME 2 | 2026-10-12 | Approved | Turnaround window at site must be avoided during cutover.
APM0004459 | INTERFLEX FRANCE | Harmonize Time Management Systems | Support Clock-in/Clock-out Systems (Provides), Manage Site Security (Provides) | Functional Migration Only | Yes | Overlapping time management systems functionality across sites; harmonising onto SAP Time Management removes redundant support effort and standardises process. | Harmonize | SAP Time Management | Functional Migration | XL | Simple | 151 | 8326649877 | Very High | Low | No | Mission Critical | GDA/DF | BENOIT LANCE | On Premise | Schwarzheide |  | No dependencies |  |  | Yes | 18.4 | 1364.8 | 1503.2 | 39 |  | Time SME 3 | 2026-10-29 | In Workshop | Awaiting confirmation of site-local process variations.
APM0001859 | INTERFLEX IF6040 SPAIN | Harmonize Time Management Systems | Support Site Access (Provides), Support Clock-in/Clock-out Systems (Provides), Manage Site Security (Provides) | Data Migration Only | No | Site-local time management systems duplicates capability already provided by SAP Time Management; consolidate to reduce licence, hosting and support cost. | Harmonize | SAP Time Management | Data Migration Only | M | Simple | 58 | 110852902 | Very High | Medium | No | High | ES/TI | EDUARD SEBASTIA BARRAU | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 306.2 | 380.6 | 41.8 | 3 | Time SME 4 | 2026-10-16 | Approved | Turnaround window at site must be avoided during cutover.
APM0010500 | INTERFLEX IF6040-2 ITALY | Harmonize Time Management Systems | Provide Facility Services (Provides) | Functional Migration Only | Yes | Application delivers a subset of SAP Time Management capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP Time Management | Functional Migration | XS | Simple | 30 | 1465765 | Low | Low | No | Medium | GBE/WI-Y | Paolo Radice | On Premise | Antwerp |  | No dependencies |  |  | No | 18.4 | 186.8 | 213.2 | 71.5 | 2 | Time SME 1 | 2026-10-11 | Approved | Interface inventory to be confirmed with integration team.
APM0001127 | INTERFLEX POLYURETHANES | Harmonize Time Management Systems | Support Clock-in/Clock-out Systems (Provides), Manage Site Security (Provides) | Data Migration Only | Yes | Overlapping time management systems functionality across sites; harmonising onto SAP Time Management removes redundant support effort and standardises process. | Harmonize | SAP Time Management | Data Migration Only | XS | Simple | 17 | 1335275 | Medium | Medium | Yes | Mission Critical | PM/LHP | Werner Pajonk | On Premise | Geismar |  | No dependencies |  |  | No | 18.4 | 114.9 | 141.3 | 82.5 | 1 | Time SME 2 | 2027-01-19 | Pending BASF Review
APM0011902 | Interflex Lampertheim | Harmonize Time Management Systems | Support Clock-in/Clock-out Systems (Provides), Manage Site Security (Provides) | Data Migration Only | Yes | Application delivers a subset of SAP Time Management capability with no differentiating function; retire after migration to the standard platform. | Harmonize | SAP Time Management | Data Migration Only | S | Simple | 41 | 5584031 | Medium | High | No | High | EVM/ELX | Tim Blaschke | On Premise | Singapore | APM0012552 | Dependencies in same wave | 2026-11-29 |  | No | 18.4 | 196 | 238.4 | 38.8 | 3 | Time SME 3 | 2026-12-03 | Pending BASF Review
APM0009299 | Trust Base (BPDD) | Harmonize Trust Base (BPDD) | Perform Risk Assessment (Provides), Perform Compliance Controls (Provides), Manage Suppliers (Provides) | Functional Migration Only | Yes | Fragmented trust base (bpdd) landscape drives inconsistent data and duplicated interfaces; consolidation onto Trust Base (BPDD) Standard is the agreed target state. | Harmonize | Trust Base (BPDD) Standard | Functional Migration | S | Complex | 31 | 4289488 | Medium | Medium | No | High | CLS/DO | Hans-Juergen Dietrich | Cloud | Antwerp |  | No dependencies |  |  | No | 42.4 | 502.9 | 616.2333 | 56.3 | 5 | Trust SME 1 | 2027-01-09 | Approved
APM0003619 | ABSTELLDATENBANK | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Data Migration Only | Yes | Application delivers a subset of Turnaround Management Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Turnaround Management Standard | Data Migration Only | M | Complex | 73 | 89933348 | High | Medium | No | High | ESM/CS | Eberhard Fuchs | On Premise | Antwerp |  | No dependencies |  |  | No | 74.4 | 670.9 | 880.2333 | 47 | 6 | Turnaround SME 1 | 2026-11-27 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0012158 | Advanced Turnaround System | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Data Migration Only | Yes | Application delivers a subset of Turnaround Management Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Turnaround Management Standard | Data Migration Only | XL | Medium | 151 | 6640259661 | High | Medium | No | High | GEA/TC | Bai Ling JIANG | Cloud | Global |  | No dependencies |  |  | No | 138.4 | 988.5 | 1257.5 | 40 | 5 | Turnaround SME 2 | 2027-01-14 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0010554 | BASANT MOBILE DigiTAR | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Data Migration Only | No | Fragmented turnaround management landscape drives inconsistent data and duplicated interfaces; consolidation onto Turnaround Management Standard is the agreed target state. | Harmonize | Turnaround Management Standard | Data Migration Only | S | Medium | 30 | 5634434 | High | Low | Yes | Medium | ESA/VIO | Yannick Brandt | On Premise | Schwarzheide | APM0012158 | Dependencies in same wave | 2027-07-09 |  | No | 42.4 | 268.7 | 345.7 | 73.3 | 1 | Turnaround SME 3 | 2026-12-29 | Approved | Data retention requirement to be validated before decommissioning.
APM0011223 | BASANT PLUTOS Afstellingsdatabank | Harmonize Turnaround Management | Provide Plant Maintenance (Provides) | Functional Migration Only | No | Overlapping turnaround management functionality across sites; harmonising onto Turnaround Management Standard removes redundant support effort and standardises process. | Harmonize | Turnaround Management Standard | Functional Migration | M | Complex | 53 | 88757391 | Medium | Medium | No | High | ESA/VIS | Tom Hugens | On Premise | Schwarzheide |  | No dependencies |  |  | No | 74.4 | 1019.1 | 1228.4333 | 52.3 | 5 | Turnaround SME 4 | 2026-10-08 | Approved
APM0011776 | BASF Seneca Turnover | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Functional Migration Only | Yes | Fragmented turnaround management landscape drives inconsistent data and duplicated interfaces; consolidation onto Turnaround Management Standard is the agreed target state. | Harmonize | Turnaround Management Standard | Functional Migration | M | Medium | 60 | 100145593 | Medium | Low | No | High | G-EVC/OC | Nicholas Finch | Cloud | Nanjing | APM0003619 | Dependencies in same wave |  |  | No | 74.4 | 714.5 | 855.5 | 47.8 | 3 | Turnaround SME 1 | 2026-10-09 | Approved | Vendor licence expires mid-programme; align cutover accordingly.
APM0004223 | DATENBANK CMP/NM | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Data Migration Only | Yes | Site-local turnaround management duplicates capability already provided by Turnaround Management Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Turnaround Management Standard | Data Migration Only | XS | Medium | 26 | 1334232 | High | Low | No | High | E-CMP/NM | Stefan Knies | On Premise | Ludwigshafen | APM0011223 | Dependencies in earlier wave |  |  | Yes | 26.4 | 145.7 | 190.7 | 55.5 |  | Turnaround SME 2 | 2026-11-28 | Approved
APM0001704 | PRIMAVERA - GEISMAR | Harmonize Turnaround Management | Provide Process Engineering (Provides) | Functional Migration Only | No | Fragmented turnaround management landscape drives inconsistent data and duplicated interfaces; consolidation onto Turnaround Management Standard is the agreed target state. | Harmonize | Turnaround Management Standard | Functional Migration | M | Complex | 64 | 100206158 | Medium | Critical | No | Mission Critical | GEC/OD | DeShandra Irvin Lawrence | On Premise | Ludwigshafen |  | No dependencies |  | 2027-07-07 | No | 74.4 | 940.9 | 1150.2333 | 36.5 | 7 | Turnaround SME 3 | 2026-12-19 | Approved | Data retention requirement to be validated before decommissioning.
APM0003252 | PRIMAVERA - PA | Harmonize Turnaround Management | Provide Plant Maintenance (Provides), Provide Maintenance Management (Provides) | Data Migration Only | Yes | Fragmented turnaround management landscape drives inconsistent data and duplicated interfaces; consolidation onto Turnaround Management Standard is the agreed target state. | Harmonize | Turnaround Management Standard | Data Migration Only | S | Medium | 31 | 3486205 | Medium | High | No | Mission Critical | N-CPN/PX | Paul Montes | On Premise | Antwerp | APM0011776; APM0010554 | Dependencies in earlier wave | 2027-03-16 |  | No | 42.4 | 227.9 | 304.9 | 43 | 4 | Turnaround SME 4 | 2027-01-06 | Approved
APM0004354 | PRIMAVERA P6 - RTP | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Data Migration Only | Yes | Site-local turnaround management duplicates capability already provided by Turnaround Management Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Turnaround Management Standard | Data Migration Only | S | Medium | 34 | 5531680 | Medium | High | No | Mission Critical | GEC/EP | Michael Shubrook | On Premise | Sao Paulo |  | No dependencies |  |  | No | 42.4 | 230.4 | 307.4 | 47.5 | 4 | Turnaround SME 1 | 2026-10-23 | Pending BASF Review
APM0001705 | PRIMAVERA P6 GEM/OP | Harmonize Turnaround Management | Provide Process Engineering (Provides), Provide Piping Engineering (Provides), Provide Construction (Provides), Provide Civil Engineering (Provides) | Data Migration Only | Yes | Overlapping turnaround management functionality across sites; harmonising onto Turnaround Management Standard removes redundant support effort and standardises process. | Harmonize | Turnaround Management Standard | Data Migration Only | S | Very Complex | 32 | 4351090 | High | Medium | No | High | GEM/ES | Alexander Neumann | On Premise | Schwarzheide |  | No dependencies |  |  | No | 42.4 | 467.8 | 613.1333 | 51 | 7 | Turnaround SME 2 | 2026-11-12 | Pending BASF Review | Interface inventory to be confirmed with integration team.
APM0001934 | PRIMAVERA RMS | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Functional Migration Only | Yes | Fragmented turnaround management landscape drives inconsistent data and duplicated interfaces; consolidation onto Turnaround Management Standard is the agreed target state. | Harmonize | Turnaround Management Standard | Functional Migration | M | Simple | 56 | 126071904 | High | Low | No | High | ESO/CT | Andreas Damm | On Premise | Tarragona |  | No dependencies |  |  | No | 18.4 | 481.2 | 555.6 | 53 | 2 | Turnaround SME 3 | 2026-10-21 | Approved | Interface inventory to be confirmed with integration team.
APM0001706 | PRIMAVERA-RMSe Spain | Harmonize Turnaround Management | Provide Turnaround Management (Provides), Provide Plant Maintenance (Provides) | Functional Migration Only | Yes | Application delivers a subset of Turnaround Management Standard capability with no differentiating function; retire after migration to the standard platform. | Harmonize | Turnaround Management Standard | Functional Migration | M | Very Complex | 60 | 59714769 | High | High | No | Medium | E-CPB/O | JOSE MANUEL GONZALEZ | On Premise | Tarragona |  | No dependencies |  |  | No | 74.4 | 1243.9 | 1517.2333 | 41.8 | 8 | Turnaround SME 4 | 2026-11-17 | Approved | Interface inventory to be confirmed with integration team.
APM0011053 | PTAProdWebSchd | Harmonize Turnaround Management | Provide Maintenance Management (Provides) | Functional Migration Only | Yes | Fragmented turnaround management landscape drives inconsistent data and duplicated interfaces; consolidation onto Turnaround Management Standard is the agreed target state. | Harmonize | Turnaround Management Standard | Functional Migration | L | Medium | 138 | 710637394 | Very High | Low | No | Medium | N-CPN/PO | Mark Foster | On Premise | Global |  | No dependencies |  |  | No | 106.4 | 1350.4 | 1555.4 | 45.5 | 4 | Turnaround SME 1 | 2026-11-11 | In Workshop
APM0008824 | Primavera Freeport | Harmonize Turnaround Management | Provide Turnaround Management (Provides), Provide Construction (Provides) | Data Migration Only | Yes | Site-local turnaround management duplicates capability already provided by Turnaround Management Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Turnaround Management Standard | Data Migration Only | M | Simple | 55 | 112426513 | Medium | Medium | No | High | N-CMN/PA | Joshua Glasgow | On Premise | Singapore |  | No dependencies |  |  | No | 18.4 | 376.6 | 451 | 52.3 | 2 | Turnaround SME 2 | 2026-11-24 | Approved | Turnaround window at site must be avoided during cutover.
APM0003942 | Primavera P6 EPPM - GI | Harmonize Turnaround Management | Provide Construction (Provides) | Data Migration Only | Yes | No active users identified during discovery; retire and archive the M dataset. | Modernize | Turnaround Management Standard | Data Migration Only | M | Medium | 55 | 126687463 | Medium | High | No | Mission Critical | AMP/OC | Ram Anilkumar Venkateshwarlu MEDA | On Premise | Ludwigshafen |  | No dependencies |  |  | No | 74.4 | 477.1 | 618.1 | 43.5 |  | Turnaround SME 3 | 2026-12-25 | In Workshop | Turnaround window at site must be avoided during cutover.
APM0002245 | RMSE | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Functional Migration Only | Yes | Overlapping turnaround management functionality across sites; harmonising onto Turnaround Management Standard removes redundant support effort and standardises process. | Harmonize | Turnaround Management Standard | Functional Migration | S | Complex | 37 | 6436226 | Very High | High | No | Mission Critical | ESO/CT | Kristian Vukelic | On Premise | Ludwigshafen | APM0004223 | Dependencies unresolved |  | 2028-08-31 | No | 42.4 | 609.5 | 722.8333 | 22 | 7 | Turnaround SME 4 | 2026-12-25 | Approved
APM0003847 | RMSEORA | Harmonize Turnaround Management | Provide Turnaround Management (Provides), Provide Plant Maintenance (Provides) | Functional Migration Only | No | Overlapping turnaround management functionality across sites; harmonising onto Turnaround Management Standard removes redundant support effort and standardises process. | Harmonize | Turnaround Management Standard | Functional Migration | XS | Complex | 12 | 1099568 | Medium | Medium | No | Medium | ESO/CT | Kristian Vukelic | On Premise | Nanjing | APM0011053 | Dependencies in earlier wave |  |  | No | 26.4 | 306.8 | 372.1333 | 56.5 | 5 | Turnaround SME 1 | 2026-10-27 | Pending BASF Review
APM0010325 | Toadfly SW Suite for Turnarounds | Harmonize Turnaround Management | Provide Turnaround Management (Provides), Provide Plant Maintenance (Provides) | Data Migration Only | Yes | Site-local turnaround management duplicates capability already provided by Turnaround Management Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Turnaround Management Standard | Data Migration Only | S | Medium | 30 | 3828029 | High | Critical | No | High | GEC/DA | Gabriela Lugo | Cloud | Global |  | No dependencies |  |  | No | 42.4 | 282.4 | 359.4 | 37 | 5 | Turnaround SME 2 | 2026-12-03 | In Workshop | Interface inventory to be confirmed with integration team.
APM0001950 | Turnaround Management System (TMS) | Harmonize Turnaround Management | Provide Turnaround Management (Provides) | Data Migration Only | Yes | Site-local turnaround management duplicates capability already provided by Turnaround Management Standard; consolidate to reduce licence, hosting and support cost. | Harmonize | Turnaround Management Standard | Data Migration Only | XXS | Simple | 9 | 149553 | High | Low | Yes | High | ESP/TVS | Wannes Vincentie | On Premise | Singapore |  | No dependencies | 2027-06-04 |  | No | 18.4 | 53.7 | 72.1 | 87 | 1 | Turnaround SME 3 | 2027-01-19 | In Workshop | Historical data volume to be re-measured prior to sizing sign-off.
APM0001850 | IPMS | Modernize IPMS-Anaqua | Manage Intellectual Property (Provides) | Full Consolidation | Yes | Legacy technology stack is out of vendor support and cannot meet current security baseline; re-platform onto Anaqua IPMS. | Modernize | Anaqua IPMS | Modernization | M | Very Complex | 66 | 112926819 | Medium | Critical | No | High | GBI/DO-IA | Bianca Hedtke | On Premise | Global |  | No dependencies |  |  | No | 74.4 | 1729.7 | 2003.0333 | 38.3 | 8 | IPMS-Anaqua SME 1 | 2026-12-28 | Approved
APM0007994 | PAuL | Modernize PAuL (Personal, Anlagen und Logistik) | Track employee training and match it to operational requirements (Provides), Schedule plant equipment and assign it to production (Provides), Report on manufacturing operations (Provides) | Full Consolidation | Yes | Medium data structures and unsupported runtime prevent cloud adoption; re-architect onto PAuL Target Architecture. | Modernize | PAuL Target Architecture | Modernization | L | Medium | 87 | 830025685 | High | Medium | No | High | G-PM/AOL | Bastian Brehme | On Premise | Singapore |  | No dependencies |  |  | No | 106.4 | 1523.1 | 1728.1 | 43 | 5 | PAuL SME 1 | 2026-11-07 | Pending BASF Review

## Topic_Summary
Topic Summary — scope, effort and completeness
All figures calculate from Wave_Plan_Input.
Topic | Applications | Size Captured | Complexity Captured | Rationale Captured | % Complete | Assessment Effort (hrs) | Total Effort (hrs) | Quick Wins
AMS for Oracle APEX | 38 | 38 | 38 | 38 | 100% | 1123.2 | 11217.0998 | 0
Harmonize 2D Plant Design Tooling | 9 | 9 | 9 | 9 | 100% | 381.6 | 5543.1666 | 5
Harmonize 3D Plant Design & Site Scanning | 17 | 17 | 17 | 17 | 100% | 1408.8 | 20847.9996 | 0
Harmonize Alarm Management Solutions | 16 | 16 | 16 | 16 | 100% | 542.4 | 6564.7664 | 0
Harmonize Archiving Solutions | 4 | 4 | 4 | 4 | 100% | 185.6 | 3027.2666 | 0
Harmonize E+I Tool Landscape | 26 | 26 | 26 | 26 | 100% | 1238.4 | 15484.6996 | 2
Harmonize E+M Data Integration & Viewing Tools | 27 | 27 | 27 | 27 | 100% | 1456.8 | 17492.133 | 4
Harmonize Enterprise Portal (Fasihi) | 70 | 70 | 70 | 70 | 100% | 2264 | 29006.8328 | 21
Harmonize Integration platform | 2 | 2 | 2 | 2 | 100% | 148.8 | 2664.5666 | 0
Harmonize Kafka Hosting | 2 | 2 | 2 | 2 | 100% | 156.8 | 1948.1666 | 0
Harmonize MES-Solutions | 37 | 37 | 37 | 37 | 100% | 2472.8 | 36262.0659 | 3
Harmonize Maintenance Management Systems | 68 | 68 | 68 | 68 | 100% | 3259.2 | 41870.2325 | 7
Harmonize Operations Platform | 150 | 150 | 150 | 150 | 100% | 10208 | 149052.3639 | 16
Harmonize Project Collaboration & Handover Tools | 25 | 25 | 25 | 25 | 100% | 1260 | 13812.5331 | 5
Harmonize ReliabilityCenter | 52 | 52 | 52 | 52 | 100% | 2636.8 | 36229.7328 | 8
Harmonize Time Management Systems | 7 | 7 | 7 | 7 | 100% | 240.8 | 4572.1333 | 1
Harmonize Trust Base (BPDD) | 1 | 1 | 1 | 1 | 100% | 42.4 | 616.2333 | 0
Harmonize Turnaround Management | 19 | 19 | 19 | 19 | 100% | 1053.6 | 13357.5331 | 2
Modernize IPMS-Anaqua | 1 | 1 | 1 | 1 | 100% | 74.4 | 2003.0333 | 0
Modernize PAuL (Personal, Anlagen und Logistik) | 1 | 1 | 1 | 1 | 100% | 106.4 | 1728.1 | 0
TOTAL | 572 | 572 | 572 | 572 | 100% | 30260.8 | 413300.6588 | 74